## PlannedQuantityList
S.NO. | PROGRAM GROUP | TRANSFORMATION | ACTIVITY ID | ACTIVITY DESCRIPTION | START DATE | END DATE | UNIT | PLANNED QTY | YEAR | MONTH
1 | BLD-2248-D-PW¦A¦1¦A | PILING WORK | 1583 | P&C bored cast in-situ pile-600mm /97 T | 14-12-2019 | 25-06-2020 | M | 1987.5 | 2020 | 8
2 | BLD-2248-D-PW¦A¦1¦B | PILING WORK | 1584 | P&C bored cast in-situ pile-750mm /158 T | 14-12-2019 | 25-06-2020 | M | 24963 | 2020 | 8
3 | BLD-2248-D-PW¦A¦2 | PILING WORK | 1585 | P&F reinf steel incl tran/strght/cut/Bnd | 14-12-2019 | 25-06-2020 | MT | 1525 | 2020 | 8
4 | BLD-2248-D-PW¦A¦3¦A¦I | PILING WORK | 1586 | Vertical load test/ 600 mm/ 97 T | 20-02-2020 | 30-05-2020 | EA | 1 | 2020 | 8
5 | BLD-2248-D-PW¦A¦3¦A¦II | PILING WORK | 1587 | Vertical load test/ 600 mm/ 158 T | 20-02-2020 | 30-05-2020 | EA | 2 | 2020 | 8
6 | BLD-2248-D-PW¦A¦3¦B¦I | PILING WORK | 1588 | Dynamic load test/ 600 mm/ 97 T | 20-02-2020 | 30-05-2020 | EA | 1 | 2020 | 8
7 | BLD-2248-D-PW¦A¦3¦B¦II | PILING WORK | 1589 | Dynamic load test/ 750 mm/ 158 T | 20-02-2020 | 30-05-2020 | EA | 7 | 2020 | 8
8 | BLD-2248-D-PW¦A¦4¦I | PILING WORK | 1590 | Pile Integrity test/ 600 mm/ 97 T | 20-02-2020 | 30-05-2020 | EA | 5 | 2020 | 8
9 | BLD-2248-D-PW¦A¦4¦II | PILING WORK | 1591 | Pile Integrity test/ 750 mm/ 158 T | 20-02-2020 | 30-05-2020 | EA | 50 | 2020 | 8
10 | BLD-2248-D-PW¦A¦5 | PILING WORK | 1592 | Break pile head manually incl remv debrs | 30-01-2020 | 09-07-2020 | M3 | 437 | 2020 | 8
11 | BLD-2248-D-EW¦B¦1¦I | EARTH WORK | 1593 | Mech Excavation upto 1.5M | 30-01-2020 | 09-07-2020 | M3 | 8431 | 2020 | 8
12 | BLD-2248-D-EW¦B¦1¦II | EARTH WORK | 1594 | Mech Excavation upto 1.5M-3.0M | 30-01-2020 | 09-07-2020 | M3 | 8341 | 2020 | 8
13 | BLD-2248-D-EW¦B¦1¦III | EARTH WORK | 1595 | Mech Excavation upto 3.0M-4.5M | 30-01-2020 | 09-07-2020 | M3 | 6517 | 2020 | 8
14 | BLD-2248-D-EW¦B¦1¦IV | EARTH WORK | 1596 | Mech Excavation upto 4.5M & above | 30-01-2020 | 09-07-2020 | M3 | 2080 | 2020 | 8
15 | BLD-2248-D-EW¦B¦2 | EARTH WORK | 1597 | Filling avail excavated earth 20cm layer | 30-01-2020 | 09-07-2020 | M3 | 8059 | 2020 | 8
16 | BLD-2248-D-EW¦B¦3 | EARTH WORK | 1598 | Sup & Fill river sand/compaction-min 90% | 03-10-2020 | 16-11-2020 | M3 | 1137 | 2020 | 8
17 | BLD-2248-D-EW¦B¦4 | EARTH WORK | 1599 | Carriage & disposal of surplus earth | 03-10-2020 | 16-11-2020 | M3 | 9000 | 2020 | 8
18 | BLD-2248-D-ATT¦B¦5¦A | ANTI TERMITE TREATMENT | 1600 | ATT in Fdn wall & vert surf @7.5Lit/M2 | 30-01-2020 | 07-09-2020 | M2 | 2273 | 2020 | 8
19 | BLD-2248-D-ATT¦B¦5¦B | ANTI TERMITE TREATMENT | 1601 | ATT in top surf within plinth @5Lit/M2 | 30-01-2020 | 07-09-2020 | M2 | 4245 | 2020 | 8
20 | BLD-2248-D-ATT¦B¦5¦C | ANTI TERMITE TREATMENT | 1602 | ATT to outside of Fdn@ 1.75L/M & 0.5L/M | 30-01-2020 | 07-09-2020 | M | 1490 | 2020 | 8
21 | BLD-2248-D-CO¦C¦1¦A | CONCRETE WORK | 1603 | Concrete (1:3:6) upto plinth | 14-03-2020 | 10-07-2020 | M3 | 735 | 2020 | 8
22 | BLD-2248-D-CO¦C¦2¦A | CONCRETE WORK | 1604 | Conc.(1:2:4)-Fdn,Plinth,Sup Str incl F/W | 12-11-2020 | 01-12-2020 | M3 | 1680 | 2020 | 8
23 | BLD-2248-D-CO¦C¦3¦I | CONCRETE WORK | 1605 | Conc.(1:4:8)with fly/burn brick incl F/W | 12-11-2020 | 01-12-2020 | M3 | 685 | 2020 | 8
24 | BLD-2248-D-CO¦C¦4 | CONCRETE WORK | 1606 | Precast (1:2:4) incl F/W & Reinf | 12-11-2020 | 01-12-2020 | M2 | 50 | 2020 | 8
25 | BLD-2248-D-CO¦C¦5 | CONCRETE WORK | 1607 | P&L DPC (1:2:4)-40 mm thick | 12-11-2020 | 01-12-2020 | M2 | 190 | 2020 | 8
26 | BLD-2248-D-CO¦C¦6 | CONCRETE WORK | 1608 | E/R-Mix WP material in Concrete work | 12-11-2020 | 01-12-2020 | 102 | 2864 | 2020 | 8
27 | BLD-2248-D-CO¦C¦7 | CONCRETE WORK | 1609 | Apply Petrlm Bitumen (VG-10) @1.7kg/M2 | 12-11-2020 | 01-12-2020 | M2 | 190 | 2020 | 8
28 | BLD-2248-D-CO¦C¦8 | CONCRETE WORK | 1610 | Plinth Protection (1:3:6)- 50mm Thick | 12-11-2020 | 01-12-2020 | M2 | 385 | 2020 | 8
29 | BLD-2248-D-RCC¦D¦1¦A | REINFORCEMNT CONCRETE WORK | 1611 | RCC (M:45)- Upto Plinth | 20-07-2020 | 20-08-2020 | M3 | 14210 | 2020 | 8
30 | BLD-2248-D-RCC¦D¦1¦B | REINFORCEMNT CONCRETE WORK | 1612 | RCC (M:45)-Plinth to Floor V | 15-07-2020 | 08-11-2020 | M3 | 8419 | 2020 | 8
31 | BLD-2248-D-RCC¦D¦1¦C | REINFORCEMNT CONCRETE WORK | 1613 | RCC (M:45)-Floor V to IX | 08-11-2020 | 03-01-2021 | M3 | 5865 | 2020 | 8
32 | BLD-2248-D-RCC¦D¦1¦D | REINFORCEMNT CONCRETE WORK | 1614 | RCC (M:45)-Floor IX to XIII | 03-01-2021 | 27-02-2021 | M3 | 5627 | 2020 | 8
33 | BLD-2248-D-RCC¦D¦1¦E | REINFORCEMNT CONCRETE WORK | 1615 | RCC (M:45)-Floor XIII to XVII | 27-02-2021 | 19-04-2021 | M3 | 5587 | 2020 | 8
34 | BLD-2248-D-RCC¦D¦1¦F | REINFORCEMNT CONCRETE WORK | 1616 | RCC (M:45)-Floor XVII to XXI | 19-04-2021 | 13-06-2021 | M3 | 4359 | 2020 | 8
35 | BLD-2248-D-RCC¦D¦1¦G | REINFORCEMNT CONCRETE WORK | 1617 | RCC (M:45)-above Floor XXI | 13-06-2021 | 24-07-2021 | M3 | 2954 | 2020 | 8
36 | BLD-2248-D-RCC¦D¦2¦A | REINFORCEMNT CONCRETE WORK | 1618 | RCC (M:35)- Upto Plinth | 12-12-2019 | 17-03-2022 | M3 | 233 | 2020 | 8
37 | BLD-2248-D-RCC¦D¦2¦B | REINFORCEMNT CONCRETE WORK | 1619 | RCC (M:35)-Plinth to Floor V | 12-12-2019 | 17-03-2022 | M3 | 400 | 2020 | 8
38 | BLD-2248-D-RCC¦D¦3¦A | REINFORCEMNT CONCRETE WORK | 1620 | RCC (M:30)- Upto Plinth | 12-12-2019 | 17-03-2022 | M3 | 80 | 2020 | 8
39 | BLD-2248-D-RCC¦D¦4¦A | REINFORCEMNT CONCRETE WORK | 1621 | RCC (M:25)- Upto Plinth | 12-12-2019 | 17-03-2022 | M3 | 740 | 2020 | 8
40 | BLD-2248-D-SFW¦D¦5¦A | FORM WORK | 1622 | Sys F/W-Upto Plinth | 12-12-2019 | 17-03-2022 | M2 | 5423 | 2020 | 8
41 | BLD-2248-D-SFW¦D¦5¦B | FORM WORK | 1623 | Sys F/W-Upto Plinth (Vertical) | 12-12-2019 | 17-03-2022 | M2 | 59480 | 2020 | 8
42 | BLD-2248-D-SFW¦D¦5¦E | FORM WORK | 1624 | Sys F/W-Above plinth (Horizon) | 12-12-2019 | 17-03-2022 | M2 | 97400 | 2020 | 8
43 | BLD-2248-D-DPC¦D¦6 | POLYTHENE SHEET | 1625 | S&L Polythene Sheet (150gm/Sqm) over DPC | 12-12-2019 | 17-03-2022 | M2 | 4400 | 2020 | 8
44 | BLD-2248-D-RE¦D¦7¦A | REINFORCEMENT STEEL WORK | 1626 | Reinforcement work (Fe 500D) | 12-12-2019 | 17-03-2022 | MT | 7588 | 2020 | 8
45 | BLD-2248-D-DR¦D¦8 | DOOR WORK | 1627 | Install Strong room door incl lift,Erec | 12-12-2019 | 17-03-2022 | JOB | 2 | 2020 | 8
46 | BLD-2248-D-RE¦D¦9 | REINFORCEMENT STEEL WORK | 1628 | H,C,Lift & Placing MS Tang Bar b/w Reinf | 12-12-2019 | 17-03-2022 | M | 4200 | 2020 | 8
47 | BLD-2248-D-PT¦D¦10 | POST TENTIONING WORK | 1629 | Design & Exec. of Post Tensioning works | 12-12-2019 | 17-03-2022 | M2 | 51500 | 2020 | 8
48 | BLD-2248-D-WP¦E¦1¦A | WATER PROOFING TREATMENT | 1630 | P&L WP membrane (APP 5 layer)- 3mm thk | 12-12-2019 | 17-03-2022 | M2 | 6011 | 2020 | 8
49 | BLD-2248-D-WP¦E¦2¦C | WATER PROOFING TREATMENT | 1631 | P&A spray applied WP membrane-2mm Thk | 12-12-2019 | 17-03-2022 | M2 | 4600 | 2020 | 8
50 | BLD-2248-D-WP¦E¦3 | WATER PROOFING TREATMENT | 1632 | E/R-Cover top membrane with Geotextile | 12-12-2019 | 17-03-2022 | M2 | 4483 | 2020 | 8
51 | BLD-2248-D-WP¦E¦4 | WATER PROOFING TREATMENT | 1633 | S&L Screed Conc. (M:15)- 50mm Thk | 12-12-2019 | 17-03-2022 | M2 | 100 | 2020 | 8
52 | BLD-2248-D-WP¦E¦5I_IV | WATER PROOFING TREATMENT | 1634 | P&L Garden Drain Board & Geotextile | 12-12-2019 | 17-03-2022 | M2 | 180 | 2020 | 8
53 | BLD-2248-D-WP¦E¦6 | WATER PROOFING TREATMENT | 1635 | P&L WP treatment-sunken part of WC,Bath | 12-12-2019 | 17-03-2022 | M2 | 2900 | 2020 | 8
54 | BLD-2248-D-WP¦E¦7 | WATER PROOFING TREATMENT | 1636 | P&M integral crystalline admix. for WP | 12-12-2019 | 17-03-2022 | KG | 6000 | 2020 | 8
55 | BLD-2248-D-WP¦E¦8 | WATER PROOFING TREATMENT | 1637 | P&A fibre reinf elastomeric liquid WP | 12-12-2019 | 17-03-2022 | M2 | 100 | 2020 | 8
56 | BLD-2248-D-WP¦E¦9 | WATER PROOFING TREATMENT | 1638 | WP Treatment by inject grout material | 12-12-2019 | 17-03-2022 | M2 | 1350 | 2020 | 8
57 | BLD-2248-D-WP¦E¦10¦A | WATER PROOFING TREATMENT | 1639 | Roof WP Treatment with Conc.(1:2:4) | 12-12-2019 | 17-03-2022 | M3 | 460 | 2020 | 8
58 | BLD-2248-D-WP¦E¦11 | WATER PROOFING TREATMENT | 1640 | P&F Heat Resistant Terrace Tile(300x300) | 12-12-2019 | 17-03-2022 | M2 | 2800 | 2020 | 8
59 | BLD-2248-D-B¦W¦F¦1¦A | BRICK WORK | 1641 | B/W (Morter- 1:6) in Fdn & Plinth | 12-12-2019 | 17-03-2022 | M3 | 270 | 2020 | 8
60 | BLD-2248-D-B¦W¦F¦2¦A | BRICK WORK | 1642 | B/W (Morter- 1:6) Plinth to Floor V | 12-12-2019 | 17-03-2022 | M3 | 1500 | 2020 | 8
61 | BLD-2248-D-B¦W¦F¦2¦B | BRICK WORK | 1643 | B/W (Morter- 1:6) above Floor V to IX | 12-12-2019 | 17-03-2022 | M3 | 842 | 2020 | 8
62 | BLD-2248-D-B¦W¦F¦2¦C | BRICK WORK | 1644 | B/W (Morter- 1:6) above Floor IX to XIII | 12-12-2019 | 17-03-2022 | M3 | 1427 | 2020 | 8
63 | BLD-2248-D-B¦W¦F¦2¦D | BRICK WORK | 1645 | B/W (Morter- 1:6) abv Floor XIII to XVII | 12-12-2019 | 17-03-2022 | M3 | 1475 | 2020 | 8
64 | BLD-2248-D-B¦W¦F¦2¦E | BRICK WORK | 1646 | B/W (Morter- 1:6) abv Floor XVII to XXI | 12-12-2019 | 17-03-2022 | M3 | 1034 | 2020 | 8
65 | BLD-2248-D-B¦W¦F¦2¦F | BRICK WORK | 1647 | B/W (Morter- 1:6) above Floor XXI | 12-12-2019 | 17-03-2022 | M3 | 578 | 2020 | 8
66 | BLD-2248-D-H¦B¦W¦F¦3¦A | BRICK WORK | 1648 | Half B/W (1:4) Plinth to Floor V | 12-12-2019 | 17-03-2022 | M2 | 600 | 2020 | 8
67 | BLD-2248-D-H¦B¦W¦F¦3¦B | BRICK WORK | 1649 | Half B/W (1:4) above Floor V to IX | 12-12-2019 | 17-03-2022 | M2 | 482 | 2020 | 8
68 | BLD-2248-D-H¦B¦W¦F¦3¦C | BRICK WORK | 1650 | Half B/W (1:4) above Floor IX to XIII | 12-12-2019 | 17-03-2022 | M2 | 1174 | 2020 | 8
69 | BLD-2248-D-H¦B¦W¦F¦3¦D | BRICK WORK | 1651 | Half B/W (1:4) abv Floor XIII to XVII | 12-12-2019 | 17-03-2022 | M2 | 1306.5 | 2020 | 8
70 | BLD-2248-D-H¦B¦W¦F¦3¦E | BRICK WORK | 1652 | Half B/W (1:4) abv Floor XVII to XXI | 12-12-2019 | 17-03-2022 | M2 | 752 | 2020 | 8
71 | BLD-2248-D-H¦B¦W¦F¦3¦F | BRICK WORK | 1653 | Half B/W (1:4) above Floor XXI | 12-12-2019 | 17-03-2022 | M2 | 408 | 2020 | 8
72 | BLD-2248-D-B¦W¦F¦4¦A | BRICK WORK | 1654 | P&L AAC Block Plinth to Floor V | 12-12-2019 | 17-03-2022 | M3 | 10 | 2020 | 8
73 | BLD-2248-D-B¦W¦F¦4¦B | BRICK WORK | 1655 | P&L AAC Block above Floor V to IX | 12-12-2019 | 17-03-2022 | M3 | 45 | 2020 | 8
74 | BLD-2248-D-B¦W¦F¦4¦C | BRICK WORK | 1656 | P&L AAC Block above Floor IX to XIII | 12-12-2019 | 17-03-2022 | M3 | 200 | 2020 | 8
75 | BLD-2248-D-B¦W¦F¦4¦D | BRICK WORK | 1657 | P&L AAC Block above Floor XIII to XVII | 12-12-2019 | 17-03-2022 | M3 | 220 | 2020 | 8
76 | BLD-2248-D-B¦W¦F¦4¦E | BRICK WORK | 1658 | P&L AAC Block above Floor XVII to XXI | 12-12-2019 | 17-03-2022 | M3 | 90 | 2020 | 8
77 | BLD-2248-D-B¦W¦F¦4¦F | BRICK WORK | 1659 | P&L AAC Block above Floor XXI | 12-12-2019 | 17-03-2022 | M3 | 10 | 2020 | 8
78 | BLD-2248-D-B¦W¦F¦5¦A | BRICK WORK | 1660 | String course with 15mm Plaster (1:4) | 12-12-2019 | 17-03-2022 | M | 476 | 2020 | 8
79 | BLD-2248-D-B¦W¦F¦6 | BRICK WORK | 1661 | Single Brick soling of jhama bricks | 12-12-2019 | 17-03-2022 | M2 | 4464 | 2020 | 8
80 | BLD-2248-D-FL¦G¦1¦A | FLOORING WORK | 1662 | Conc. Floor (1:2:4)- 40mm Thk | 12-12-2019 | 17-03-2022 | M2 | 50 | 2020 | 8
81 | BLD-2248-D-FL¦G¦2 | FLOORING WORK | 1663 | Conc. Floor with Hardener (1:2:4)-52mm | 12-12-2019 | 17-03-2022 | M2 | 23423.4004 | 2020 | 8
82 | BLD-2248-D-FL¦G¦3¦A | FLOORING WORK | 1664 | Cement Plaster Skirting (1:3)-18 mm Thk | 12-12-2019 | 17-03-2022 | M2 | 2490 | 2020 | 8
83 | BLD-2248-D-FL¦G¦4¦A | FLOORING WORK | 1665 | Kota flooring (1:4) in slab- 25 mm Thk | 12-12-2019 | 17-03-2022 | M2 | 110 | 2020 | 8
84 | BLD-2248-D-FL¦G¦5 | FLOORING WORK | 1666 | Kota Skirt,Dado,Stair (1:3)- 20 mm Thk | 12-12-2019 | 17-03-2022 | M2 | 59 | 2020 | 8
85 | BLD-2248-D-FL¦G¦6 | FLOORING WORK | 1667 | E/R for Nosing in Kota stone tread | 12-12-2019 | 17-03-2022 | M | 268 | 2020 | 8
86 | BLD-2248-D-FL¦G¦7 | FLOORING WORK | 1668 | P&L Pol Granite flooring (1:4)-20 mm Thk | 12-12-2019 | 17-03-2022 | M2 | 2741.78 | 2020 | 8
87 | BLD-2248-D-FL¦G¦8¦A | FLOORING WORK | 1669 | Edge moulding in Granite work | 12-12-2019 | 17-03-2022 | M | 3340 | 2020 | 8
88 | BLD-2248-D-FL¦G¦9 | FLOORING WORK | 1670 | E/R-Serrated granite/kota floor (1:4) | 12-12-2019 | 17-03-2022 | M2 | 1765 | 2020 | 8
89 | BLD-2248-D-FL¦G¦10 | FLOORING WORK | 1671 | P&L Granite flooring (1:4)-18 mm Thk | 12-12-2019 | 17-03-2022 | M2 | 170 | 2020 | 8
90 | BLD-2248-D-FL¦G¦11 | FLOORING WORK | 1672 | P&L Anti skid exter grade Vitrified Tile | 12-12-2019 | 17-03-2022 | M2 | 1860 | 2020 | 8
91 | BLD-2248-D-FL¦G¦12 | FLOORING WORK | 1673 | P&L Tactile tile 300x300x9.8mm (1:4) | 12-12-2019 | 17-03-2022 | M2 | 60 | 2020 | 8
92 | BLD-2248-D-FL¦G¦13I_IV | FLOORING WORK | 1674 | P&L Polyurethene car deck Floor Top Coat | 12-12-2019 | 17-03-2022 | M2 | 18600 | 2020 | 8
93 | BLD-2248-D-PL¦H¦1¦B | PLASTERING WORK | 1675 | 15 mm Int. Plaster (1:6) above plinth | 12-12-2019 | 17-03-2022 | M2 | 91518.6328 | 2020 | 8
94 | BLD-2248-D-PL¦H¦2¦A | PLASTERING WORK | 1676 | 20 mm Ext. Plaster (1:4) upto plinth | 12-12-2019 | 17-03-2022 | M2 | 1750 | 2020 | 8
95 | BLD-2248-D-PL¦H¦2¦B | PLASTERING WORK | 1677 | 20 mm Ext. Plaster (1:4) in Supr Str. | 12-12-2019 | 17-03-2022 | M2 | 1250 | 2020 | 8
96 | BLD-2248-D-PL¦H¦3 | PLASTERING WORK | 1678 | 10 mm Ceiling Plaster (1:3) in Supr Str. | 12-12-2019 | 17-03-2022 | M2 | 28512 | 2020 | 8
97 | BLD-2248-D-PL¦H¦4¦A | PLASTERING WORK | 1679 | 15 mm Ext Plaster (1:4) upto plinth | 12-12-2019 | 17-03-2022 | M2 | 442 | 2020 | 8
98 | BLD-2248-D-PL¦H¦4¦B | PLASTERING WORK | 1680 | 15 mm Ext Plaster (1:4) plinth-Floor V | 12-12-2019 | 17-03-2022 | M2 | 4141 | 2020 | 8
99 | BLD-2248-D-PL¦H¦4¦C | PLASTERING WORK | 1681 | 15 mm Ext Plaster (1:4) Floor V-IX | 12-12-2019 | 17-03-2022 | M2 | 1792 | 2020 | 8
100 | BLD-2248-D-PL¦H¦4¦D | PLASTERING WORK | 1682 | 15 mm Ext Plaster (1:4) Floor IX-XIII | 12-12-2019 | 17-03-2022 | M2 | 2347.8 | 2020 | 8
101 | BLD-2248-D-PL¦H¦4¦E | PLASTERING WORK | 1683 | 15 mm Ext Plaster (1:4) Floor XIII-XVII | 12-12-2019 | 17-03-2022 | M2 | 2277 | 2020 | 8
102 | BLD-2248-D-PL¦H¦4¦F | PLASTERING WORK | 1684 | 15 mm Ext Plaster (1:4) Floor XVII-XXI | 12-12-2019 | 17-03-2022 | M2 | 2708 | 2020 | 8
103 | BLD-2248-D-PL¦H¦4¦G | PLASTERING WORK | 1685 | 15 mm Ext Plaster (1:4) above floor XXI | 12-12-2019 | 17-03-2022 | M2 | 2303 | 2020 | 8
104 | BLD-2248-D-PL¦H¦5 | PLASTERING WORK | 1686 | E/R- P&M WP material in plaster | 12-12-2019 | 17-03-2022 | 102 | 2275 | 2020 | 8
105 | BLD-2248-D-PL¦H¦6 | PLASTERING WORK | 1687 | E/R-Synthetic Polyester fibre in plaster | 12-12-2019 | 17-03-2022 | 102 | 2275 | 2020 | 8
106 | BLD-2248-D-PL¦H¦7 | PLASTERING WORK | 1688 | Cement Punning 1.5mm-Wall,Dado,Floor | 12-12-2019 | 17-03-2022 | M2 | 3676 | 2020 | 8
107 | BLD-2248-D-PL¦H¦8 | PLASTERING WORK | 1689 | S&A 3 coat food grade (Sika Guard 67) | 12-12-2019 | 17-03-2022 | M2 | 1250 | 2020 | 8
108 | BLD-2248-D-FD¦I¦1 | FIRE RESISTANT DOOR WORK | 1690 | P&F Fire Resistant door frame (H & V) | 12-12-2019 | 17-03-2022 | M | 1130 | 2020 | 8
109 | BLD-2248-D-FD¦I¦2 | FIRE RESISTANT DOOR WORK | 1691 | P&F Glazed fire resistant door Shutter | 12-12-2019 | 17-03-2022 | M2 | 545 | 2020 | 8
110 | BLD-2248-D-FD¦I¦3 | FIRE RESISTANT DOOR WORK | 1692 | P&F Glazing in Fire resist door shutter | 12-12-2019 | 17-03-2022 | M2 | 325 | 2020 | 8
111 | BLD-2248-D-STEEL¦J¦1 | STRUCTURAL STEEL WORK | 1693 | Sup,Fab & Erec of Structural Steel | 12-12-2019 | 17-03-2022 | KG | 75880 | 2020 | 8
112 | BLD-2248-D-STEEL¦J¦2 | STRUCTURAL STEEL WORK | 1694 | P&F Pressed Steel Door frame | 12-12-2019 | 17-03-2022 | M2 | 2715 | 2020 | 8
113 | BLD-2248-D-STEEL¦J¦3 | STRUCTURAL STEEL WORK | 1695 | P&F Safety foot rest (6mm)Plastic coated | 12-12-2019 | 17-03-2022 | EA | 150 | 2020 | 8
114 | BLD-2248-D-STEEL¦J¦4¦A | STRUCTURAL STEEL WORK | 1696 | S&F Rolling shutter | 12-12-2019 | 17-03-2022 | M2 | 110 | 2020 | 8
115 | BLD-2248-D-STEEL¦J¦5 | STRUCTURAL STEEL WORK | 1697 | E/R- Provide Grilled Rolling Shutter | 12-12-2019 | 17-03-2022 | M2 | 20 | 2020 | 8
116 | BLD-2248-D-STEEL¦J¦6 | STRUCTURAL STEEL WORK | 1698 | E/R-Provide mech. device(10-16.8 M2) | 12-12-2019 | 17-03-2022 | M2 | 100 | 2020 | 8
117 | BLD-2248-D-STEEL¦J¦7 | STRUCTURAL STEEL WORK | 1699 | P&F SS Railing | 12-12-2019 | 17-03-2022 | KG | 13500 | 2020 | 8
118 | BLD-2248-D-STEEL¦J¦8 | STRUCTURAL STEEL WORK | 1700 | P&F Precoated galvanised iron sheets | 12-12-2019 | 17-03-2022 | M2 | 285 | 2020 | 8
119 | BLD-2248-D-STEEL¦J¦9 | STRUCTURAL STEEL WORK | 1701 | S&F polycarbonate panel (UV Protected) | 12-12-2019 | 17-03-2022 | M2 | 300 | 2020 | 8
120 | BLD-2248-D-PA¦K¦1¦A | PRIMER WORK | 1702 | P&A primer with pink/grey on wood work | 12-12-2019 | 17-03-2022 | M2 | 50 | 2020 | 8
121 | BLD-2248-D-PA¦K¦1¦B | PRIMER WORK | 1703 | P&A primer with red oxide on steel/Iron | 12-12-2019 | 17-03-2022 | M2 | 350 | 2020 | 8
122 | BLD-2248-D-PA¦K¦1¦C | PRIMER WORK | 1704 | P&A cement thinnable primer on wall | 12-12-2019 | 17-03-2022 | M2 | 50 | 2020 | 8
123 | BLD-2248-D-PA¦K¦2¦A | PRIMER WORK | 1705 | P&A synthetic enamel paint (2 Coats) | 12-12-2019 | 17-03-2022 | M2 | 350 | 2020 | 8
124 | BLD-2248-D-PA¦K¦3¦A | PRIMER WORK | 1706 | P&A Premium Acrylic exterior paint | 12-12-2019 | 17-03-2022 | M2 | 15945 | 2020 | 8
125 | BLD-2248-D-PA¦K¦4¦A | PRIMER WORK | 1707 | P&A water proofing cement paint | 12-12-2019 | 17-03-2022 | M2 | 31120 | 2020 | 8
126 | BLD-2248-D-MISC¦L¦1 | MISCELLANEOUS WORK | 1708 | Dismantling B/W with Plaster for Opening | 12-12-2019 | 17-03-2022 | M3 | 10 | 2020 | 8
127 | BLD-2248-D-MISC¦L¦2 | MISCELLANEOUS WORK | 1709 | Dismant RCC/PCC incl stack,cut,cln Reinf | 12-12-2019 | 17-03-2022 | M3 | 5 | 2020 | 8
128 | BLD-2248-D-MISC¦L¦3¦I | MISCELLANEOUS WORK | 1710 | Chase cutting & Making in RCC surface | 12-12-2019 | 17-03-2022 | M2 | 25 | 2020 | 8
129 | BLD-2248-D-MISC¦L¦3¦II | MISCELLANEOUS WORK | 1711 | Chase cutting & Making in Brick surface | 12-12-2019 | 17-03-2022 | M2 | 50 | 2020 | 8
130 | BLD-2248-D-MISC¦L¦4 | MISCELLANEOUS WORK | 1712 | Repairing Patch in Plaster with Mort 1:4 | 12-12-2019 | 17-03-2022 | M2 | 50 | 2020 | 8
131 | BLD-2248-D-MISC¦L¦5 | MISCELLANEOUS WORK | 1713 | Make Opening for Exhaust in B/W Mort 1:4 | 12-12-2019 | 17-03-2022 | EA | 180 | 2020 | 8
132 | BLD-2248-D-MISC¦L¦6¦I | MISCELLANEOUS WORK | 1714 | S&F Chem anchor fastener (L200mm,D16 mm) | 12-12-2019 | 17-03-2022 | EA | 250 | 2020 | 8
133 | BLD-2248-D-MISC¦L¦6¦II | MISCELLANEOUS WORK | 1715 | S&F Chem anchor fastener (L260mm,D20 mm) | 12-12-2019 | 17-03-2022 | EA | 250 | 2020 | 8
134 | BLD-2248-D-MISC¦L¦6¦III | MISCELLANEOUS WORK | 1716 | S&F Chem anchor fastener (L300mm,D24 mm) | 12-12-2019 | 17-03-2022 | EA | 300 | 2020 | 8
135 | BLD-2248-D-MISC¦L¦7¦I | MISCELLANEOUS WORK | 1717 | S&F Mech Exp anch. fast (L115mm,D12 mm) | 12-12-2019 | 17-03-2022 | EA | 100 | 2020 | 8
136 | BLD-2248-D-MISC¦L¦7¦II | MISCELLANEOUS WORK | 1718 | S&F Mech Exp anch. fast (L145mm,D16 mm) | 12-12-2019 | 17-03-2022 | EA | 100 | 2020 | 8
137 | BLD-2248-D-MISC¦L¦7¦III | MISCELLANEOUS WORK | 1719 | S&F Mech Exp anch. fast (L170mm,D20 mm) | 12-12-2019 | 17-03-2022 | EA | 120 | 2020 | 8
138 | BLD-2248-D-MISC¦L¦8¦I | MISCELLANEOUS WORK | 1720 | P&F Rebar- Dia 8mm, Embed Length-160mm | 12-12-2019 | 17-03-2022 | EA | 10 | 2020 | 8
139 | BLD-2248-D-MISC¦L¦8¦II | MISCELLANEOUS WORK | 1721 | P&F Rebar- Dia 10mm, Embed Length-200mm | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
140 | BLD-2248-D-MISC¦L¦8¦III | MISCELLANEOUS WORK | 1722 | P&F Rebar- Dia 12mm, Embed Length-240mm | 12-12-2019 | 17-03-2022 | EA | 50 | 2020 | 8
141 | BLD-2248-D-MISC¦L¦8¦IV | MISCELLANEOUS WORK | 1723 | P&F Rebar- Dia 16mm, Embed Length-320mm | 12-12-2019 | 17-03-2022 | EA | 50 | 2020 | 8
142 | BLD-2248-D-MISC¦L¦8¦V | MISCELLANEOUS WORK | 1724 | P&F Rebar- Dia 20mm, Embed Length-400mm | 12-12-2019 | 17-03-2022 | EA | 50 | 2020 | 8
143 | BLD-2248-D-MISC¦L¦8¦VI | MISCELLANEOUS WORK | 1725 | P&F Rebar- Dia 25mm, Embed Length-500mm | 12-12-2019 | 17-03-2022 | EA | 50 | 2020 | 8
144 | BLD-2248-D-MISC¦L¦9 | MISCELLANEOUS WORK | 1726 | P&F Anchor Fastener for door fix | 12-12-2019 | 17-03-2022 | EA | 100 | 2020 | 8
145 | BLD-2248-D-MISC¦L¦10 | MISCELLANEOUS WORK | 1727 | P&F Expansion joint (75x25mm) | 12-12-2019 | 17-03-2022 | M | 950 | 2020 | 8
146 | BLD-2248-D-MISC¦L¦11 | MISCELLANEOUS WORK | 1728 | P&F Alum Plain/Chaq plate cover-Exp. Jnt | 12-12-2019 | 17-03-2022 | M | 950 | 2020 | 8
147 | BLD-2248-D-MISC¦L¦12¦A | MISCELLANEOUS WORK | 1729 | S&I Fire Barriers Composite Sheet | 12-12-2019 | 17-03-2022 | M2 | 10 | 2020 | 8
148 | BLD-2248-D-MISC¦L¦12¦B | MISCELLANEOUS WORK | 1730 | S&I Fire Barriers Composite Sheet | 12-12-2019 | 17-03-2022 | M2 | 10 | 2020 | 8
149 | BLD-2248-D-MISC¦L¦12¦C | MISCELLANEOUS WORK | 1731 | S&I Fire stop mortar system | 12-12-2019 | 17-03-2022 | M2 | 50 | 2020 | 8
150 | BLD-2248-D-ED¦1¦I | EXTERNAL DEVELOPMENT WORK | 1732 | Mech Excavation upto 1.5M | 12-12-2019 | 17-03-2022 | M3 | 3265 | 2020 | 8
151 | BLD-2248-D-ED¦1¦II | EXTERNAL DEVELOPMENT WORK | 1733 | Mech Excavation upto 1.5M-3.0M | 12-12-2019 | 17-03-2022 | M3 | 1539 | 2020 | 8
152 | BLD-2248-D-ED¦1¦III | EXTERNAL DEVELOPMENT WORK | 1734 | Mech Excavation upto 3.0M-4.5M | 12-12-2019 | 17-03-2022 | M3 | 1065 | 2020 | 8
153 | BLD-2248-D-ED¦1¦IV | EXTERNAL DEVELOPMENT WORK | 1735 | Mech Excavation upto 4.5M & above | 12-12-2019 | 17-03-2022 | M3 | 650 | 2020 | 8
154 | BLD-2248-D-ED¦2 | EXTERNAL DEVELOPMENT WORK | 1736 | Filling avail excavated earth 20cm layer | 12-12-2019 | 17-03-2022 | M3 | 1500 | 2020 | 8
155 | BLD-2248-D-ED¦3 | EXTERNAL DEVELOPMENT WORK | 1737 | Sup & Fill river sand/compaction-min 90% | 12-12-2019 | 17-03-2022 | M3 | 1236 | 2020 | 8
156 | BLD-2248-D-ED¦4 | EXTERNAL DEVELOPMENT WORK | 1738 | P&I Hard sal bullah drivng pile D-150mm | 12-12-2019 | 17-03-2022 | M | 7000 | 2020 | 8
157 | BLD-2248-D-ED¦5¦A | EXTERNAL DEVELOPMENT WORK | 1739 | B/W (Morter- 1:6) in Fdn & Plinth | 12-12-2019 | 17-03-2022 | M3 | 27 | 2020 | 8
158 | BLD-2248-D-ED¦6¦A | EXTERNAL DEVELOPMENT WORK | 1740 | B/W (Morter- 1:6) Plinth to Floor V | 12-12-2019 | 17-03-2022 | M3 | 101 | 2020 | 8
159 | BLD-2248-D-ED¦7¦A | EXTERNAL DEVELOPMENT WORK | 1741 | Half B/W (1:4) Plinth to Floor V | 12-12-2019 | 17-03-2022 | M2 | 50 | 2020 | 8
160 | BLD-2248-D-ED¦8 | EXTERNAL DEVELOPMENT WORK | 1742 | Single Brick soling of jhama bricks | 12-12-2019 | 17-03-2022 | M2 | 1000 | 2020 | 8
161 | BLD-2248-D-ED¦9¦B | EXTERNAL DEVELOPMENT WORK | 1743 | 15 mm Int. Plaster (1:6) above plinth | 12-12-2019 | 17-03-2022 | M2 | 1100 | 2020 | 8
162 | BLD-2248-D-ED¦10¦A | EXTERNAL DEVELOPMENT WORK | 1744 | 20 mm Ext. Plaster (1:4) upto plinth | 12-12-2019 | 17-03-2022 | M2 | 782 | 2020 | 8
163 | BLD-2248-D-ED¦11 | EXTERNAL DEVELOPMENT WORK | 1745 | 10 mm Ceiling Plaster (1:3) in Supr Str. | 12-12-2019 | 17-03-2022 | M2 | 50 | 2020 | 8
164 | BLD-2248-D-ED¦12¦A | EXTERNAL DEVELOPMENT WORK | 1746 | 15 mm Ext Plaster (1:4) upto plinth | 12-12-2019 | 17-03-2022 | M2 | 520 | 2020 | 8
165 | BLD-2248-D-ED¦12¦B | EXTERNAL DEVELOPMENT WORK | 1747 | 15 mm Ext Plaster (1:4) plinth-Floor V | 12-12-2019 | 17-03-2022 | M2 | 900 | 2020 | 8
166 | BLD-2248-D-ED¦ | EXTERNAL DEVELOPMENT WORK | 1748 | Cement Punning 1.5mm-Wall,Dado,Floor | 12-12-2019 | 17-03-2022 | M2 | 1465 | 2020 | 8
167 | BLD-2248-D-ED¦14¦A | EXTERNAL DEVELOPMENT WORK | 1749 | Concrete (1:3:6) upto plinth | 12-12-2019 | 17-03-2022 | M3 | 172 | 2020 | 8
168 | BLD-2248-D-ED¦15¦A | EXTERNAL DEVELOPMENT WORK | 1750 | RCC (M:30)- Upto Plinth | 12-12-2019 | 17-03-2022 | M3 | 1500 | 2020 | 8
169 | BLD-2248-D-ED¦15¦B | EXTERNAL DEVELOPMENT WORK | 1751 | RCC (M:30)-Plinth to Floor V | 12-12-2019 | 17-03-2022 | M3 | 30 | 2020 | 8
170 | BLD-2248-D-ED¦16¦A | EXTERNAL DEVELOPMENT WORK | 1752 | F/W (Steel Plate)- Upto Plinth | 12-12-2019 | 17-03-2022 | M2 | 3500 | 2020 | 8
171 | BLD-2248-D-ED¦16¦B | EXTERNAL DEVELOPMENT WORK | 1753 | F/W (Steel Plate)-Upto Plinth (vertical) | 12-12-2019 | 17-03-2022 | M2 | 220 | 2020 | 8
172 | BLD-2248-D-ED¦16¦E | EXTERNAL DEVELOPMENT WORK | 1754 | F/W (Steel Plate)-above Plinth (Horizon) | 12-12-2019 | 17-03-2022 | M2 | 276 | 2020 | 8
173 | BLD-2248-D-ED¦17¦A | EXTERNAL DEVELOPMENT WORK | 1755 | P&F reinf steel incl tran/strght/cut/Bnd | 12-12-2019 | 17-03-2022 | MT | 273 | 2020 | 8
174 | BLD-2248-D-ED¦18 | EXTERNAL DEVELOPMENT WORK | 1756 | S&L Polythene Sheet (150gm/Sqm) over DPC | 12-12-2019 | 17-03-2022 | M2 | 2850 | 2020 | 8
175 | BLD-2248-D-ED¦19¦A | EXTERNAL DEVELOPMENT WORK | 1757 | Subgrade Preparation (300mm Depth) | 12-12-2019 | 17-03-2022 | M2 | 2850 | 2020 | 8
176 | BLD-2248-D-ED¦20 | EXTERNAL DEVELOPMENT WORK | 1758 | Rolling Subgrade by Roller (8-12T) | 12-12-2019 | 17-03-2022 | M2 | 2900 | 2020 | 8
177 | BLD-2248-D-ED¦21 | EXTERNAL DEVELOPMENT WORK | 1759 | Sprd&Scrn Road metal-brick bat (63-90mm) | 12-12-2019 | 17-03-2022 | M3 | 441 | 2020 | 8
178 | BLD-2248-D-ED¦22 | EXTERNAL DEVELOPMENT WORK | 1760 | P&F 25mm thk thermocol sheet in Exp Jnt | 12-12-2019 | 17-03-2022 | M2 | 184 | 2020 | 8
179 | BLD-2248-D-ED¦23¦A | EXTERNAL DEVELOPMENT WORK | 1761 | P&L bitumen sealing compound in Exp Jnt | 12-12-2019 | 17-03-2022 | M | 900 | 2020 | 8
180 | BLD-2248-D-ED¦24 | EXTERNAL DEVELOPMENT WORK | 1762 | P&L Conc. (M40) Grass paver block | 12-12-2019 | 17-03-2022 | M2 | 800 | 2020 | 8
181 | BLD-2248-D-ED¦25 | EXTERNAL DEVELOPMENT WORK | 1763 | P&L Conc. (M30) interlocking paver block | 12-12-2019 | 17-03-2022 | M2 | 160 | 2020 | 8
182 | BLD-2248-D-ED¦26 | EXTERNAL DEVELOPMENT WORK | 1764 | P&L Kerb Channel 50mm Thk (Mort: 1:3:6) | 12-12-2019 | 17-03-2022 | M2 | 190 | 2020 | 8
183 | BLD-2248-D-ED¦27 | EXTERNAL DEVELOPMENT WORK | 1765 | P&L Kerb Stone (M:25) with Mort: 1:3 | 12-12-2019 | 17-03-2022 | M3 | 68 | 2020 | 8
184 | BLD-2248-D-ED¦28¦A | EXTERNAL DEVELOPMENT WORK | 1766 | P&A synthetic enamel paint | 12-12-2019 | 17-03-2022 | M2 | 660 | 2020 | 8
185 | BLD-2248-D-ED¦29 | EXTERNAL DEVELOPMENT WORK | 1767 | P&L Pol Granite flooring (1:4)-18 mm Thk | 12-12-2019 | 17-03-2022 | M2 | 513 | 2020 | 8
186 | BLD-2248-D-ED¦30¦A | EXTERNAL DEVELOPMENT WORK | 1768 | P&L Flame finish Granite flooring (1:4) | 12-12-2019 | 17-03-2022 | M2 | 1540 | 2020 | 8
187 | BLD-2248-D-ED¦31¦A | EXTERNAL DEVELOPMENT WORK | 1769 | P&L Kota flooring (1:4)-25 mm Thk | 12-12-2019 | 17-03-2022 | M2 | 52 | 2020 | 8
188 | BLD-2248-D-ED¦32 | EXTERNAL DEVELOPMENT WORK | 1770 | P&L Kota Skirt,Dado,Stair(1:3)-20 mm Thk | 12-12-2019 | 17-03-2022 | M2 | 12 | 2020 | 8
189 | BLD-2248-D-ED¦33 | EXTERNAL DEVELOPMENT WORK | 1771 | P&L Anti skid exter grade Vitrified Tile | 12-12-2019 | 17-03-2022 | M2 | 86 | 2020 | 8
190 | BLD-2248-D-ED¦34 | EXTERNAL DEVELOPMENT WORK | 1772 | P&L Glass mosaic tiles on wall (1:4) | 12-12-2019 | 17-03-2022 | M2 | 130 | 2020 | 8
191 | BLD-2248-D-ED¦35¦A | EXTERNAL DEVELOPMENT WORK | 1773 | Conc. Floor (1:2:4)- 40mm Thk | 12-12-2019 | 17-03-2022 | M2 | 250 | 2020 | 8
192 | BLD-2248-D-ED¦36 | EXTERNAL DEVELOPMENT WORK | 1774 | P&L Turf paver on 150 mm thick sub grade | 12-12-2019 | 17-03-2022 | M2 | 150 | 2020 | 8
193 | BLD-2248-D-ED¦37¦A | EXTERNAL DEVELOPMENT WORK | 1775 | P&A water proofing cement paint | 12-12-2019 | 17-03-2022 | M2 | 210 | 2020 | 8
194 | BLD-2248-D-ED¦38¦A | EXTERNAL DEVELOPMENT WORK | 1776 | P&A primer with red oxide on steel/Iron | 12-12-2019 | 17-03-2022 | M2 | 583 | 2020 | 8
195 | BLD-2248-D-ED¦39¦A | EXTERNAL DEVELOPMENT WORK | 1777 | P&A Premium Acrylic exterior paint | 12-12-2019 | 17-03-2022 | M2 | 1221 | 2020 | 8
196 | BLD-2248-D-ED¦40¦A | EXTERNAL DEVELOPMENT WORK | 1778 | P&A synthetic enamel paint (2 Coats) | 12-12-2019 | 17-03-2022 | M2 | 583 | 2020 | 8
197 | BLD-2248-D-ED¦41 | EXTERNAL DEVELOPMENT WORK | 1779 | Making V-groove in plastered surface | 12-12-2019 | 17-03-2022 | M | 1200 | 2020 | 8
198 | BLD-2248-D-ED¦42¦A | EXTERNAL DEVELOPMENT WORK | 1780 | Sup,Fab & Erec of Structural Steel | 12-12-2019 | 17-03-2022 | KG | 35590 | 2020 | 8
199 | BLD-2248-D-ED¦43 | EXTERNAL DEVELOPMENT WORK | 1781 | P&L Precast RCC (M:30) Rect. Covers | 12-12-2019 | 17-03-2022 | M2 | 468 | 2020 | 8
200 | BLD-2248-D-ED¦44¦ITOIX | EXTERNAL DEVELOPMENT WORK | 1782 | SITC aerating column jet fountain | 12-12-2019 | 17-03-2022 | JOB | 1 | 2020 | 8
201 | BLD-2248-D-HC¦A¦1 | HORTICULTURE WORK | 1783 | Trenching in Ord. Soil upto depth 30cm | 12-12-2019 | 17-03-2022 | M3 | 728 | 2020 | 8
202 | BLD-2248-D-HC¦A¦2 | HORTICULTURE WORK | 1784 | Supp & Stack Good earth | 12-12-2019 | 17-03-2022 | M3 | 364 | 2020 | 8
203 | BLD-2248-D-HC¦A¦3 | HORTICULTURE WORK | 1785 | Supp & Stack sludge | 12-12-2019 | 17-03-2022 | M3 | 243 | 2020 | 8
204 | BLD-2248-D-HC¦A¦4¦A | HORTICULTURE WORK | 1786 | Supp & Stack dump manure-sieve 20mm | 12-12-2019 | 17-03-2022 | M3 | 80 | 2020 | 8
205 | BLD-2248-D-HC¦A¦4¦B | HORTICULTURE WORK | 1787 | Supp & Stack dump manure-sieve 16mm | 12-12-2019 | 17-03-2022 | M3 | 80 | 2020 | 8
206 | BLD-2248-D-HC¦A¦4¦C | HORTICULTURE WORK | 1788 | Supp & Stack dump manure-sieve 4.7mm | 12-12-2019 | 17-03-2022 | M3 | 80 | 2020 | 8
207 | BLD-2248-D-HC¦A¦5 | HORTICULTURE WORK | 1789 | Rough dressing the trenched ground | 12-12-2019 | 17-03-2022 | 101 | 24 | 2020 | 8
208 | BLD-2248-D-HC¦A¦6 | HORTICULTURE WORK | 1790 | Uprooting weeds from trenched area | 12-12-2019 | 17-03-2022 | 101 | 24 | 2020 | 8
209 | BLD-2248-D-HC¦A¦7 | HORTICULTURE WORK | 1791 | Spreading of sludge,manure,good earth | 12-12-2019 | 17-03-2022 | M3 | 845 | 2020 | 8
210 | BLD-2248-D-HC¦A¦8 | HORTICULTURE WORK | 1792 | P&F MS Flat tree guard with Name plate | 12-12-2019 | 17-03-2022 | EA | 50 | 2020 | 8
211 | BLD-2248-D-HC¦A¦9¦A | HORTICULTURE WORK | 1793 | Edging with brick incl Excv,refil,Consld | 12-12-2019 | 17-03-2022 | M | 150 | 2020 | 8
212 | BLD-2248-D-HC¦A¦10 | HORTICULTURE WORK | 1794 | Supp & Stack decayed cow dung manure | 12-12-2019 | 17-03-2022 | M3 | 30 | 2020 | 8
213 | BLD-2248-D-HC¦A¦11¦A | HORTICULTURE WORK | 1795 | P&F Circular Conc. Pots (1:2:4)- 35/25mm | 12-12-2019 | 17-03-2022 | EA | 50 | 2020 | 8
214 | BLD-2248-D-HC¦A¦11¦B | HORTICULTURE WORK | 1796 | P&F Circular Conc. Pots (1:2:4)- 30/20mm | 12-12-2019 | 17-03-2022 | EA | 50 | 2020 | 8
215 | BLD-2248-D-HC¦A¦12¦A | HORTICULTURE WORK | 1797 | P&L water filtration Pebble-Pure white | 12-12-2019 | 17-03-2022 | M3 | 5 | 2020 | 8
216 | BLD-2248-D-HC¦A¦12¦B | HORTICULTURE WORK | 1798 | P&L water filtration Pebble-Pure black | 12-12-2019 | 17-03-2022 | M3 | 3 | 2020 | 8
217 | BLD-2248-D-HC¦A¦12¦C | HORTICULTURE WORK | 1799 | P&L water filtration Pebble-Naturl Brown | 12-12-2019 | 17-03-2022 | M3 | 25 | 2020 | 8
218 | BLD-2248-D-HC¦A¦13'1 | HORTICULTURE WORK | 1800 | S&P Achras Sapota (Chiku Tree) | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
219 | BLD-2248-D-HC¦A¦13'2 | HORTICULTURE WORK | 1801 | S&P Achras Sapota (Chiku Tree) | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
220 | BLD-2248-D-HC¦A¦13'3 | HORTICULTURE WORK | 1802 | S&P Alstonia scholaris(Saptoprni/ Chatim | 12-12-2019 | 17-03-2022 | EA | 3 | 2020 | 8
221 | BLD-2248-D-HC¦A¦13'4 | HORTICULTURE WORK | 1803 | S&P Azadirachta Indica (Neem) | 12-12-2019 | 17-03-2022 | EA | 6 | 2020 | 8
222 | BLD-2248-D-HC¦A¦13'5 | HORTICULTURE WORK | 1804 | S&P Red Bottle Brush | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
223 | BLD-2248-D-HC¦A¦13'6 | HORTICULTURE WORK | 1805 | S&P Cassia fistula (Indian Laburnum) | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
224 | BLD-2248-D-HC¦A¦13'7 | HORTICULTURE WORK | 1806 | S&P Cassia Javanica (Apple Blossom) | 12-12-2019 | 17-03-2022 | EA | 6 | 2020 | 8
225 | BLD-2248-D-HC¦A¦13'8 | HORTICULTURE WORK | 1807 | S&P Cordia sebestena ( Raktarag) | 12-12-2019 | 17-03-2022 | EA | 6 | 2020 | 8
226 | BLD-2248-D-HC¦A¦13'9 | HORTICULTURE WORK | 1808 | S&P Coroupita Guinensis (Canon Ball) | 12-12-2019 | 17-03-2022 | EA | 6 | 2020 | 8
227 | BLD-2248-D-HC¦A¦13'10 | HORTICULTURE WORK | 1809 | S&P Cycas Revoluta ( Sago Palm)@1500 c/c | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
228 | BLD-2248-D-HC¦A¦13'11 | HORTICULTURE WORK | 1810 | S&P Caesalpinia Pulcherrima | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
229 | BLD-2248-D-HC¦A¦13'12 | HORTICULTURE WORK | 1811 | S&P Delonix Regia ( Gulmohor) | 12-12-2019 | 17-03-2022 | EA | 6 | 2020 | 8
230 | BLD-2248-D-HC¦A¦13'13 | HORTICULTURE WORK | 1812 | S&P Eugenia Jambolana (Jamun/Java Palm) | 12-12-2019 | 17-03-2022 | EA | 6 | 2020 | 8
231 | BLD-2248-D-HC¦A¦13'14 | HORTICULTURE WORK | 1813 | S&P Ficus Benjamina(Pernnial Buck wheat) | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
232 | BLD-2248-D-HC¦A¦13'15 | HORTICULTURE WORK | 1814 | S&P Ficus Ingens (Red Ficus) @1500 c/c | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
233 | BLD-2248-D-HC¦A¦13'16 | HORTICULTURE WORK | 1815 | S&P Ficus Microcarpa Chinese Banyan | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
234 | BLD-2248-D-HC¦A¦13'17 | HORTICULTURE WORK | 1816 | S&P Ficus Variegata ( Fig ) @1500 c/c | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
235 | BLD-2248-D-HC¦A¦13'18 | HORTICULTURE WORK | 1817 | S&P Filifera aurea ( Golden Cypruss) | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
236 | BLD-2248-D-HC¦A¦13'19 | HORTICULTURE WORK | 1818 | S&P Grevillea Robusta ( Silver Oak) | 12-12-2019 | 17-03-2022 | EA | 4 | 2020 | 8
237 | BLD-2248-D-HC¦A¦13'20 | HORTICULTURE WORK | 1819 | S&P Javanica Mimosifolia | 12-12-2019 | 17-03-2022 | EA | 3 | 2020 | 8
238 | BLD-2248-D-HC¦A¦13'21 | HORTICULTURE WORK | 1820 | S&P Lagerstroemia Flos-reginae ( Jarul) | 12-12-2019 | 17-03-2022 | EA | 3 | 2020 | 8
239 | BLD-2248-D-HC¦A¦13'22 | HORTICULTURE WORK | 1821 | S&P Lagerstroemia Indica | 12-12-2019 | 17-03-2022 | EA | 6 | 2020 | 8
240 | BLD-2248-D-HC¦A¦13'23 | HORTICULTURE WORK | 1822 | S&P Mangifera Indica ( Mango) | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
241 | BLD-2248-D-HC¦A¦13'24 | HORTICULTURE WORK | 1823 | S&P Golden Bottle Brush | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
242 | BLD-2248-D-HC¦A¦13'25 | HORTICULTURE WORK | 1824 | S&P Michelia Champaca ( Golden Champa) | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
243 | BLD-2248-D-HC¦A¦13'26 | HORTICULTURE WORK | 1825 | S&P Mimusops elengi Spanish Cherry | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
244 | BLD-2248-D-HC¦A¦13'27 | HORTICULTURE WORK | 1826 | S&P Night Flowering Jesmine | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
245 | BLD-2248-D-HC¦A¦13'28 | HORTICULTURE WORK | 1827 | S&P Nerium Oleander | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
246 | BLD-2248-D-HC¦A¦13'29 | HORTICULTURE WORK | 1828 | S&P Odallum Rubra ( Champa) @2500 c/c | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
247 | BLD-2248-D-HC¦A¦13'30 | HORTICULTURE WORK | 1829 | S&P Peltophorum feruginium(Yellow Flame) | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
248 | BLD-2248-D-HC¦A¦13'31 | HORTICULTURE WORK | 1830 | S&P Plumeria acutifolia (Red Frangipani) | 12-12-2019 | 17-03-2022 | EA | 4 | 2020 | 8
249 | BLD-2248-D-HC¦A¦13'32 | HORTICULTURE WORK | 1831 | S&P Plumeria Alba ( Gulancha) @3000 c/c | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
250 | BLD-2248-D-HC¦A¦13'33 | HORTICULTURE WORK | 1832 | S&P Plumeria Rubra( Ftrangipani) | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
251 | BLD-2248-D-HC¦A¦13'34 | HORTICULTURE WORK | 1833 | S&P Podocarpus macrophyllus(Yellow Pine) | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
252 | BLD-2248-D-HC¦A¦13'35 | HORTICULTURE WORK | 1834 | S&P Polyalthia longifolia (Mast Tree) | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
253 | BLD-2248-D-HC¦A¦13'36 | HORTICULTURE WORK | 1835 | S&P Poltoforum Pterocarpum | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
254 | BLD-2248-D-HC¦A¦13'37 | HORTICULTURE WORK | 1836 | S&P Plumbago Capensiss | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
255 | BLD-2248-D-HC¦A¦13'38 | HORTICULTURE WORK | 1837 | S&P Saraca Indica ( Ashoka) | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
256 | BLD-2248-D-HC¦A¦13'39 | HORTICULTURE WORK | 1838 | S&P Spathodea Companulata ( Tulip) | 12-12-2019 | 17-03-2022 | EA | 3 | 2020 | 8
257 | BLD-2248-D-HC¦A¦13'40 | HORTICULTURE WORK | 1839 | S&P Spiral Buxus | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
258 | BLD-2248-D-HC¦A¦13'41 | HORTICULTURE WORK | 1840 | S&P Tabebuia Argentea ( Silver Trumpet) | 12-12-2019 | 17-03-2022 | EA | 3 | 2020 | 8
259 | BLD-2248-D-HC¦A¦13'42 | HORTICULTURE WORK | 1841 | S&P Tabebuia Rosea ( Pink Trumpet) | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
260 | BLD-2248-D-HC¦A¦13'43 | HORTICULTURE WORK | 1842 | S&P Tecoma Gaudichaudi | 12-12-2019 | 17-03-2022 | EA | 6 | 2020 | 8
261 | BLD-2248-D-HC¦A¦13'44 | HORTICULTURE WORK | 1843 | S&P Terminalia Variegata ( Tagor) | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
262 | BLD-2248-D-HC¦A¦14'1 | HORTICULTURE WORK | 1844 | S&P Areca Palm | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
263 | BLD-2248-D-HC¦A¦14'2 | HORTICULTURE WORK | 1845 | S&P Cyrtostachys Renda | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
264 | BLD-2248-D-HC¦A¦14'3 | HORTICULTURE WORK | 1846 | S&P Date Palm | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
265 | BLD-2248-D-HC¦A¦14'4 | HORTICULTURE WORK | 1847 | S&P Golden Cane Palm | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
266 | BLD-2248-D-HC¦A¦14'5 | HORTICULTURE WORK | 1848 | S&P Livistona Decipiens | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
267 | BLD-2248-D-HC¦A¦14'6 | HORTICULTURE WORK | 1849 | S&P Livistona Rotundifolia | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
268 | BLD-2248-D-HC¦A¦14'7 | HORTICULTURE WORK | 1850 | S&P Phoenix Palm | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
269 | BLD-2248-D-HC¦A¦14'8 | HORTICULTURE WORK | 1851 | S&P Rhapis Excalsa | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
270 | BLD-2248-D-HC¦A¦14'9 | HORTICULTURE WORK | 1852 | S&P Royal Palm | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
271 | BLD-2248-D-HC¦A¦14'10 | HORTICULTURE WORK | 1853 | S&P Triangular Palm | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
272 | BLD-2248-D-HC¦A¦14'11 | HORTICULTURE WORK | 1854 | S&P Veitchia Merrilli | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
273 | BLD-2248-D-HC¦A¦14'12 | HORTICULTURE WORK | 1855 | S&P Wodyetia Bifurcata (Foxtail palm) | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
274 | BLD-2248-D-HC¦A¦15'1 | HORTICULTURE WORK | 1856 | S&P Acalypha wilkesiana compacta dwarf | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
275 | BLD-2248-D-HC¦A¦15'2 | HORTICULTURE WORK | 1857 | S&P Alpinia purpurea | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
276 | BLD-2248-D-HC¦A¦15'3 | HORTICULTURE WORK | 1858 | S&P Alpinia Z. Variegated Dwarf | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
277 | BLD-2248-D-HC¦A¦15'4 | HORTICULTURE WORK | 1859 | S&P Alternanthera bettzickiana | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
278 | BLD-2248-D-HC¦A¦15'5 | HORTICULTURE WORK | 1860 | S&P Anthurium spp. | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
279 | BLD-2248-D-HC¦A¦15'6 | HORTICULTURE WORK | 1861 | S&P Asparagus | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
280 | BLD-2248-D-HC¦A¦15'7 | HORTICULTURE WORK | 1862 | S&P Bambusa ventricosa | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
281 | BLD-2248-D-HC¦A¦15'8 | HORTICULTURE WORK | 1863 | S&P Bambusa Vulgaris | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
282 | BLD-2248-D-HC¦A¦15'9 | HORTICULTURE WORK | 1864 | S&P Canna Spp. Dwarf | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
283 | BLD-2248-D-HC¦A¦15'10 | HORTICULTURE WORK | 1865 | S&P Chrysopogon zizanioides (vetiver) | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
284 | BLD-2248-D-HC¦A¦15'11 | HORTICULTURE WORK | 1866 | S&P Cordyline Mahatma Red | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
285 | BLD-2248-D-HC¦A¦15'12 | HORTICULTURE WORK | 1867 | S&P Cortaderia Selloana | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
286 | BLD-2248-D-HC¦A¦15'13 | HORTICULTURE WORK | 1868 | S&P Cymbopogon Citratus | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
287 | BLD-2248-D-HC¦A¦15'14 | HORTICULTURE WORK | 1869 | S&P Cyperus Alternifolius Gracilis | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
288 | BLD-2248-D-HC¦A¦15'15 | HORTICULTURE WORK | 1870 | S&P Clerodendrum Inerme (Forest Jasmico) | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
289 | BLD-2248-D-HC¦A¦15'16 | HORTICULTURE WORK | 1871 | S&P Duranta goldeana | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
290 | BLD-2248-D-HC¦A¦15'17 | HORTICULTURE WORK | 1872 | S&P Euphorbia cotinifolia | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
291 | BLD-2248-D-HC¦A¦15'18 | HORTICULTURE WORK | 1873 | S&P Ficus Panda | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
292 | BLD-2248-D-HC¦A¦15'19 | HORTICULTURE WORK | 1874 | S&P Furcraea Gigantica | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
293 | BLD-2248-D-HC¦A¦15'20 | HORTICULTURE WORK | 1875 | S&P Green Lily | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
294 | BLD-2248-D-HC¦A¦15'21 | HORTICULTURE WORK | 1876 | S&P Gaillardia Pukhella | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
295 | BLD-2248-D-HC¦A¦15'22 | HORTICULTURE WORK | 1877 | S&P Geranium Psilostemon | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
296 | BLD-2248-D-HC¦A¦15'23 | HORTICULTURE WORK | 1878 | S&P Hamelia Patens Dwarf | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
297 | BLD-2248-D-HC¦A¦15'24 | HORTICULTURE WORK | 1879 | S&P Heliconia psittacarum | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
298 | BLD-2248-D-HC¦A¦15'25 | HORTICULTURE WORK | 1880 | S&P Hydrangia Macrophylla | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
299 | BLD-2248-D-HC¦A¦15'26 | HORTICULTURE WORK | 1881 | S&P Heliconia rostrata | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
300 | BLD-2248-D-HC¦A¦15'27 | HORTICULTURE WORK | 1882 | S&P Hemerocallis SPP | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
301 | BLD-2248-D-HC¦A¦15'28 | HORTICULTURE WORK | 1883 | S&P Hymenocallys littoralis | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
302 | BLD-2248-D-HC¦A¦15'29 | HORTICULTURE WORK | 1884 | S&P Impatiens SPP. | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
303 | BLD-2248-D-HC¦A¦15'30 | HORTICULTURE WORK | 1885 | S&P Lantana Sellowiana | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
304 | BLD-2248-D-HC¦A¦15'31 | HORTICULTURE WORK | 1886 | S&P Lemonia S variagata | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
305 | BLD-2248-D-HC¦A¦15'32 | HORTICULTURE WORK | 1887 | S&P Lantnna Camara (Pink) | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
306 | BLD-2248-D-HC¦A¦15'33 | HORTICULTURE WORK | 1888 | S&P Musa Ornata | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
307 | BLD-2248-D-HC¦A¦15'34 | HORTICULTURE WORK | 1889 | S&P Nerium Dwarf Variegata (Petite Pink) | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
308 | BLD-2248-D-HC¦A¦15'35 | HORTICULTURE WORK | 1890 | S&P Ophiopogon J.variegata | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
309 | BLD-2248-D-HC¦A¦15'36 | HORTICULTURE WORK | 1891 | S&P Osmoxylon lineare | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
310 | BLD-2248-D-HC¦A¦15'37 | HORTICULTURE WORK | 1892 | S&P Philodendron Xanadu | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
311 | BLD-2248-D-HC¦A¦15'38 | HORTICULTURE WORK | 1893 | S&P Phyllostachys nigra | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
312 | BLD-2248-D-HC¦A¦15'39 | HORTICULTURE WORK | 1894 | S&P Pleioblastus Variegata | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
313 | BLD-2248-D-HC¦A¦15'40 | HORTICULTURE WORK | 1895 | S&P Plumbago Capiensis | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
314 | BLD-2248-D-HC¦A¦15'41 | HORTICULTURE WORK | 1896 | S&P Plumeria Pudica | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
315 | BLD-2248-D-HC¦A¦15'42 | HORTICULTURE WORK | 1897 | S&P Pleatranthus Scutellarioides | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
316 | BLD-2248-D-HC¦A¦15'43 | HORTICULTURE WORK | 1898 | S&P Pandanus Sanderi | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
317 | BLD-2248-D-HC¦A¦16'1 | HORTICULTURE WORK | 1899 | S&P Antigonon leptopus | 12-12-2019 | 17-03-2022 | EA | 10 | 2020 | 8
318 | BLD-2248-D-HC¦A¦16'2 | HORTICULTURE WORK | 1900 | S&P Beaumontia grandiflora | 12-12-2019 | 17-03-2022 | EA | 10 | 2020 | 8
319 | BLD-2248-D-HC¦A¦16'3 | HORTICULTURE WORK | 1901 | S&P Bignonia Venusta | 12-12-2019 | 17-03-2022 | EA | 10 | 2020 | 8
320 | BLD-2248-D-HC¦A¦16'4 | HORTICULTURE WORK | 1902 | S&P Bougainvillea sp. | 12-12-2019 | 17-03-2022 | EA | 10 | 2020 | 8
321 | BLD-2248-D-HC¦A¦16'5 | HORTICULTURE WORK | 1903 | S&P Jacquimontia Violacea | 12-12-2019 | 17-03-2022 | EA | 10 | 2020 | 8
322 | BLD-2248-D-HC¦A¦16'6 | HORTICULTURE WORK | 1904 | S&P Passiflora Caerulea | 12-12-2019 | 17-03-2022 | EA | 10 | 2020 | 8
323 | BLD-2248-D-HC¦A¦16'7 | HORTICULTURE WORK | 1905 | S&P Thunbergia grandiflora | 12-12-2019 | 17-03-2022 | EA | 10 | 2020 | 8
324 | BLD-2248-D-HC¦A¦17'1 | HORTICULTURE WORK | 1906 | S&P Blade grass | 12-12-2019 | 17-03-2022 | M2 | 300 | 2020 | 8
325 | BLD-2248-D-HC¦A¦17'2 | HORTICULTURE WORK | 1907 | S&P Calcutta doob - selection 1 | 12-12-2019 | 17-03-2022 | M2 | 1850 | 2020 | 8
326 | BLD-2248-D-HC¦A¦17'3 | HORTICULTURE WORK | 1908 | S&P Korean grass | 12-12-2019 | 17-03-2022 | M2 | 300 | 2020 | 8
327 | BLD-2248-D-HC¦A¦18 | HORTICULTURE WORK | 1909 | Maint-tree,shrub,crepr,lawn,perenal,palm | 12-12-2019 | 17-03-2022 | JOB | 1 | 2020 | 8
328 | BLD-2248-D-HC¦A¦19 | HORTICULTURE WORK | 1910 | lift earth,manure-roof garden (upto 9FL) | 12-12-2019 | 17-03-2022 | M3 | 50 | 2020 | 8
329 | BLD-2248-D-LIC¦B¦1'1¦A | LANDSCAPING IRRIGATION WORK | 1911 | P&F HDPE pipe incl. fittings-110mm | 12-12-2019 | 17-03-2022 | M | 250 | 2020 | 8
330 | BLD-2248-D-LIC¦B¦1'1¦B | LANDSCAPING IRRIGATION WORK | 1912 | P&F HDPE pipe incl. fittings-90mm | 12-12-2019 | 17-03-2022 | M | 180 | 2020 | 8
331 | BLD-2248-D-LIC¦B¦1'1¦C | LANDSCAPING IRRIGATION WORK | 1913 | P&F HDPE pipe incl. fittings-75mm | 12-12-2019 | 17-03-2022 | M | 100 | 2020 | 8
332 | BLD-2248-D-LIC¦B¦1'1¦D | LANDSCAPING IRRIGATION WORK | 1914 | P&F HDPE pipe incl. fittings-63mm | 12-12-2019 | 17-03-2022 | M | 550 | 2020 | 8
333 | BLD-2248-D-LIC¦B¦1'1¦E | LANDSCAPING IRRIGATION WORK | 1915 | P&F HDPE pipe incl. fittings-50mm | 12-12-2019 | 17-03-2022 | M | 50 | 2020 | 8
334 | BLD-2248-D-LIC¦B¦1'2¦A | LANDSCAPING IRRIGATION WORK | 1916 | P&F LLDPE pipe-16mm incl pressre dripper | 12-12-2019 | 17-03-2022 | M | 50 | 2020 | 8
335 | BLD-2248-D-LIC¦B¦1'2¦B | LANDSCAPING IRRIGATION WORK | 1917 | P&F LLDPE pipe-16mm (Poly tube) | 12-12-2019 | 17-03-2022 | M | 50 | 2020 | 8
336 | BLD-2248-D-LIC¦ | LANDSCAPING IRRIGATION WORK | 1918 | S&F plastic mini valve for Dripline-16mm | 12-12-2019 | 17-03-2022 | EA | 50 | 2020 | 8
337 | BLD-2248-D-LIC¦B¦3¦A | LANDSCAPING IRRIGATION WORK | 1919 | S&F Pop-Up type rotos (Rad-12.3M) | 12-12-2019 | 17-03-2022 | EA | 50 | 2020 | 8
338 | BLD-2248-D-LIC¦B¦3¦B | LANDSCAPING IRRIGATION WORK | 1920 | S&F Pop-Up type sprayers (Rad-5.5M) | 12-12-2019 | 17-03-2022 | EA | 50 | 2020 | 8
339 | BLD-2248-D-LIC¦B¦3¦C | LANDSCAPING IRRIGATION WORK | 1921 | S&F Pop-Up type Sprauyers (Rad-3.7M) | 12-12-2019 | 17-03-2022 | EA | 50 | 2020 | 8
340 | BLD-2248-D-LIC¦B¦4¦A | LANDSCAPING IRRIGATION WORK | 1922 | S&F serice saddles-20mmx63mm | 12-12-2019 | 17-03-2022 | EA | 50 | 2020 | 8
341 | BLD-2248-D-LIC¦B¦4¦B | LANDSCAPING IRRIGATION WORK | 1923 | S&F serice saddles-15mmx75mm | 12-12-2019 | 17-03-2022 | EA | 50 | 2020 | 8
342 | BLD-2248-D-LIC¦B¦4¦C | LANDSCAPING IRRIGATION WORK | 1924 | S&F serice saddles-15mmx63mm | 12-12-2019 | 17-03-2022 | EA | 30 | 2020 | 8
343 | BLD-2248-D-LIC¦B¦4¦D | LANDSCAPING IRRIGATION WORK | 1925 | S&F serice saddles-15mmx63mm | 12-12-2019 | 17-03-2022 | EA | 30 | 2020 | 8
344 | BLD-2248-D-LIC¦B¦5¦A | LANDSCAPING IRRIGATION WORK | 1926 | S&F CI Flazed -100 mm dia gate Valve | 12-12-2019 | 17-03-2022 | EA | 4 | 2020 | 8
345 | BLD-2248-D-LIC¦B¦5¦B | LANDSCAPING IRRIGATION WORK | 1927 | S&F CI Flazed -100 mm dia foot valve | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
346 | BLD-2248-D-LIC¦B¦5¦C | LANDSCAPING IRRIGATION WORK | 1928 | S&F CI Flazed-D 100 mm Non return valve | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
347 | BLD-2248-D-LIC¦B¦5¦D | LANDSCAPING IRRIGATION WORK | 1929 | S&F CI Flazed -D 100 mm Butter fly valve | 12-12-2019 | 17-03-2022 | EA | 8 | 2020 | 8
348 | BLD-2248-D-LIC¦B¦5¦E | LANDSCAPING IRRIGATION WORK | 1930 | S&F CI Flazed -50 mm dia butter fly vale | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
349 | BLD-2248-D-LIC¦B¦5¦F | LANDSCAPING IRRIGATION WORK | 1931 | S&F Air/Vaccum release valve 50 mm | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
350 | BLD-2248-D-LIC¦B¦5¦G | LANDSCAPING IRRIGATION WORK | 1932 | S&F Autm. pressr releasing Hydrlic valve | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
351 | BLD-2248-D-LIC¦B¦5¦H | LANDSCAPING IRRIGATION WORK | 1933 | S&F Rugged reinf heavy duty PVC valve | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
352 | BLD-2248-D-LIC¦B¦6 | LANDSCAPING IRRIGATION WORK | 1934 | SITC single tank unit sand/media filter | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
353 | BLD-2248-D-LIC¦B¦7 | LANDSCAPING IRRIGATION WORK | 1935 | SITC Disc of capacity 50 cum/ Hours | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
354 | BLD-2248-D-LIC¦B¦8 | LANDSCAPING IRRIGATION WORK | 1936 | SITC control panel/ Starter | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
355 | BLD-2248-D-FCD¦WT01¦1'1 | FAÇADE WORK | 1937 | Facade work-SDPC coating | 12-12-2019 | 17-03-2022 | M2 | 6500 | 2020 | 8
356 | BLD-2248-D-FCD¦WT01¦1'2 | FAÇADE WORK | 1938 | Facade work-Glass 30mm DGU | 12-12-2019 | 17-03-2022 | M2 | 5035 | 2020 | 8
357 | BLD-2248-D-FCD¦WT01¦1'3 | FAÇADE WORK | 1939 | Facade work-8 mm Spandrel Glass | 12-12-2019 | 17-03-2022 | M2 | 1465 | 2020 | 8
358 | BLD-2248-D-FCD¦WT01¦1'4 | FAÇADE WORK | 1940 | Facade work-Spandrel Insulation | 12-12-2019 | 17-03-2022 | M2 | 1465 | 2020 | 8
359 | BLD-2248-D-FCD¦WT01¦1'5 | FAÇADE WORK | 1941 | Facade work-Rock wool Insulation | 12-12-2019 | 17-03-2022 | M | 1625 | 2020 | 8
360 | BLD-2248-D-FCD¦WT01¦1'6 | FAÇADE WORK | 1942 | Facade work-shutter Windows sys 1.8x1.2M | 12-12-2019 | 17-03-2022 | EA | 250 | 2020 | 8
361 | BLD-2248-D-FCD¦WT01¦1'7 | FAÇADE WORK | 1943 | Facade work-Vertical aluminium fins | 12-12-2019 | 17-03-2022 | M | 350 | 2020 | 8
362 | BLD-2248-D-FCD¦WT02¦2'1 | FAÇADE WORK | 1944 | Facade work-SDPC coating | 12-12-2019 | 17-03-2022 | M2 | 350 | 2020 | 8
363 | BLD-2248-D-FCD¦WT02¦2'2 | FAÇADE WORK | 1945 | Facade work-Glass 30mm DGU | 12-12-2019 | 17-03-2022 | M2 | 275 | 2020 | 8
364 | BLD-2248-D-FCD¦WT02¦2'3 | FAÇADE WORK | 1946 | Facade work-8 mm Spandrel Glass | 12-12-2019 | 17-03-2022 | M2 | 75 | 2020 | 8
365 | BLD-2248-D-FCD¦WT02¦2'4 | FAÇADE WORK | 1947 | Facade work-Spandrel Insulation | 12-12-2019 | 17-03-2022 | M2 | 75 | 2020 | 8
366 | BLD-2248-D-FCD¦WT02¦2'5 | FAÇADE WORK | 1948 | Facade work-SITDC of M.S. work | 12-12-2019 | 17-03-2022 | MT | 8 | 2020 | 8
367 | BLD-2248-D-FCD¦WT03¦3'1 | FAÇADE WORK | 1949 | Facade work-SDPC coating | 12-12-2019 | 17-03-2022 | M2 | 850 | 2020 | 8
368 | BLD-2248-D-FCD¦WT03¦3'2 | FAÇADE WORK | 1950 | Facade work-Glass 30mm DGU | 12-12-2019 | 17-03-2022 | M2 | 659 | 2020 | 8
369 | BLD-2248-D-FCD¦WT03¦3'3 | FAÇADE WORK | 1951 | Facade work-8 mm Spandrel Glass | 12-12-2019 | 17-03-2022 | M2 | 191 | 2020 | 8
370 | BLD-2248-D-FCD¦WT03¦3'4 | FAÇADE WORK | 1952 | Facade work-Spandrel Insulation | 12-12-2019 | 17-03-2022 | M2 | 191 | 2020 | 8
371 | BLD-2248-D-FCD¦WT03¦3'5 | FAÇADE WORK | 1953 | Facade work-Rock wool Insulation | 12-12-2019 | 17-03-2022 | M | 215 | 2020 | 8
372 | BLD-2248-D-FCD¦WT03¦3'6 | FAÇADE WORK | 1954 | Facade work-shutter Windows sys 1.8x1.2M | 12-12-2019 | 17-03-2022 | EA | 32 | 2020 | 8
373 | BLD-2248-D-FCD¦WT03¦3'7 | FAÇADE WORK | 1955 | Facade work-shutter Windows sys 2.4x1.2M | 12-12-2019 | 17-03-2022 | EA | 10 | 2020 | 8
374 | BLD-2248-D-FCD¦WT04¦4'1 | FAÇADE WORK | 1956 | Facade work-SDPC coating | 12-12-2019 | 17-03-2022 | M2 | 500 | 2020 | 8
375 | BLD-2248-D-FCD¦WT04¦4'2 | FAÇADE WORK | 1957 | Facade work-Glass 30mm DGU | 12-12-2019 | 17-03-2022 | M2 | 387 | 2020 | 8
376 | BLD-2248-D-FCD¦WT04¦4'3 | FAÇADE WORK | 1958 | Facade work-8 mm Spandrel Glass | 12-12-2019 | 17-03-2022 | M2 | 113 | 2020 | 8
377 | BLD-2248-D-FCD¦WT04¦4'4 | FAÇADE WORK | 1959 | Facade work-Spandrel Insulation | 12-12-2019 | 17-03-2022 | M2 | 113 | 2020 | 8
378 | BLD-2248-D-FCD¦WT04¦4'5 | FAÇADE WORK | 1960 | Facade work-Rock wool Insulation | 12-12-2019 | 17-03-2022 | M | 125 | 2020 | 8
379 | BLD-2248-D-FCD¦WT04¦4'6 | FAÇADE WORK | 1961 | Facade work-shutter Windows sys 1.8x1.2M | 12-12-2019 | 17-03-2022 | EA | 66 | 2020 | 8
380 | BLD-2248-D-FCD¦WT4A¦4'1A | FAÇADE WORK | 1962 | Facade work-SDPC coating | 12-12-2019 | 17-03-2022 | M2 | 550 | 2020 | 8
381 | BLD-2248-D-FCD¦WT4A¦4'2A | FAÇADE WORK | 1963 | Facade work-Glass 30mm DGU | 12-12-2019 | 17-03-2022 | M2 | 426 | 2020 | 8
382 | BLD-2248-D-FCD¦WT4A¦4'3A | FAÇADE WORK | 1964 | Facade work-8 mm Spandrel Glass | 12-12-2019 | 17-03-2022 | M2 | 124 | 2020 | 8
383 | BLD-2248-D-FCD¦WT4A¦4'4A | FAÇADE WORK | 1965 | Facade work-Spandrel Insulation | 12-12-2019 | 17-03-2022 | M2 | 124 | 2020 | 8
384 | BLD-2248-D-FCD¦WT4A¦4'5A | FAÇADE WORK | 1966 | Facade work-Rock wool Insulation | 12-12-2019 | 17-03-2022 | M | 138 | 2020 | 8
385 | BLD-2248-D-FCD¦WT4A¦4'6A | FAÇADE WORK | 1967 | Facade work-shutter Windows sys 1.8x1.2M | 12-12-2019 | 17-03-2022 | EA | 8 | 2020 | 8
386 | BLD-2248-D-FCD¦WT05¦5'1 | FAÇADE WORK | 1968 | Facade work-SDPC coating | 12-12-2019 | 17-03-2022 | M2 | 2000 | 2020 | 8
387 | BLD-2248-D-FCD¦WT05¦5'2 | FAÇADE WORK | 1969 | Facade work-Glass 30mm DGU | 12-12-2019 | 17-03-2022 | M2 | 2000 | 2020 | 8
388 | BLD-2248-D-FCD¦WT05¦5'3 | FAÇADE WORK | 1970 | Facade work-shutter Windows sys 1.8x1.2M | 12-12-2019 | 17-03-2022 | EA | 104 | 2020 | 8
389 | BLD-2248-D-FCD¦WT05¦5'4 | FAÇADE WORK | 1971 | Facade work-shutter Windows sys 2.4x1.2M | 12-12-2019 | 17-03-2022 | EA | 80 | 2020 | 8
390 | BLD-2248-D-FCD¦WT06¦6'1 | FAÇADE WORK | 1972 | Facade work-SDPC coating | 12-12-2019 | 17-03-2022 | M2 | 2800 | 2020 | 8
391 | BLD-2248-D-FCD¦WT06¦6'2 | FAÇADE WORK | 1973 | Facade work-Glass 32mm DGU | 12-12-2019 | 17-03-2022 | M2 | 2170 | 2020 | 8
392 | BLD-2248-D-FCD¦WT06¦6'3 | FAÇADE WORK | 1974 | Facade work-8 mm Spandrel Glass | 12-12-2019 | 17-03-2022 | M2 | 630 | 2020 | 8
393 | BLD-2248-D-FCD¦WT06¦6'4 | FAÇADE WORK | 1975 | Facade work-Spandrel Insulation | 12-12-2019 | 17-03-2022 | M2 | 630 | 2020 | 8
394 | BLD-2248-D-FCD¦WT06¦6'5 | FAÇADE WORK | 1976 | Facade work-Rock wool Insulation | 12-12-2019 | 17-03-2022 | M | 700 | 2020 | 8
395 | BLD-2248-D-FCD¦WT06¦6'6 | FAÇADE WORK | 1977 | Facade work-shutter Windows sys 2.4x1.2M | 12-12-2019 | 17-03-2022 | EA | 8 | 2020 | 8
396 | BLD-2248-D-FCD¦WT07¦7 | FAÇADE WORK | 1978 | Facade work-Standing railing | 12-12-2019 | 17-03-2022 | M | 750 | 2020 | 8
397 | BLD-2248-D-FCD¦WT08¦8'1 | FAÇADE WORK | 1979 | Facade work-System rate Wall cladding | 12-12-2019 | 17-03-2022 | M2 | 2500 | 2020 | 8
398 | BLD-2248-D-FCD¦WT08¦8'2 | FAÇADE WORK | 1980 | Facade work-Beam / Box cladding | 12-12-2019 | 17-03-2022 | M2 | 1800 | 2020 | 8
399 | BLD-2248-D-FCD¦WT08¦8'3 | FAÇADE WORK | 1981 | Facade work-Beam / Box cladding | 12-12-2019 | 17-03-2022 | M2 | 500 | 2020 | 8
400 | BLD-2248-D-FCD¦WT08¦8'4 | FAÇADE WORK | 1982 | Facade work-Shaft Cladding | 12-12-2019 | 17-03-2022 | M2 | 3000 | 2020 | 8
401 | BLD-2248-D-FCD¦WT08¦8'5 | FAÇADE WORK | 1983 | Facade work-Aluminium sheet PVDF | 12-12-2019 | 17-03-2022 | M2 | 7800 | 2020 | 8
402 | BLD-2248-D-FCD¦WT9¦10¦9 | FAÇADE WORK | 1984 | Facade work-System rate Wall cladding | 12-12-2019 | 17-03-2022 | M2 | 4127 | 2020 | 8
403 | BLD-2248-D-FCD¦W9¦10¦9'1 | FAÇADE WORK | 1985 | Facade work-Aluminium sheet PVDF | 12-12-2019 | 17-03-2022 | M2 | 2377 | 2020 | 8
404 | BLD-2248-D-FCD¦9¦10¦10'1 | FAÇADE WORK | 1986 | Facade work-Aluminium perforated sheet | 12-12-2019 | 17-03-2022 | M2 | 1750 | 2020 | 8
405 | BLD-2248-D-FCD¦WT11¦11'1 | FAÇADE WORK | 1987 | Facade work-Glass Façade | 12-12-2019 | 17-03-2022 | M2 | 350 | 2020 | 8
406 | BLD-2248-D-FCD¦WT11¦11'2 | FAÇADE WORK | 1988 | Facade work-Glass Façade | 12-12-2019 | 17-03-2022 | M2 | 350 | 2020 | 8
407 | BLD-2248-D-FCD¦WT11¦11'3 | FAÇADE WORK | 1989 | Facade work-Automatic Sliding Door | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
408 | BLD-2248-D-FCD¦WT11¦11'4 | FAÇADE WORK | 1990 | Facade work-Patch Door | 12-12-2019 | 17-03-2022 | EA | 6 | 2020 | 8
409 | BLD-2248-D-FCD¦WT12¦12 | FAÇADE WORK | 1991 | Facade work-3mm thick SS 316 sheet | 12-12-2019 | 17-03-2022 | M2 | 280 | 2020 | 8
410 | BLD-2248-D-FCD¦WT12¦12'1 | FAÇADE WORK | 1992 | Facade work-custom designed M.S. work | 12-12-2019 | 17-03-2022 | MT | 15 | 2020 | 8
411 | BLD-2248-D-FCD¦WT13¦13'1 | FAÇADE WORK | 1993 | Facade work-3mm thick SS 316 sheet | 12-12-2019 | 17-03-2022 | M2 | 300 | 2020 | 8
412 | BLD-2248-D-FCD¦WT13¦13'2 | FAÇADE WORK | 1994 | Facade work-custom designed M.S. work | 12-12-2019 | 17-03-2022 | MT | 12 | 2020 | 8
413 | BLD-2248-D-FCD¦WT14¦14'1 | FAÇADE WORK | 1995 | Facade work-stone cladding at skirting | 12-12-2019 | 17-03-2022 | M2 | 150 | 2020 | 8
414 | BLD-2248-D-FCD¦WT14¦14'2 | FAÇADE WORK | 1996 | Facade work-custom designed M.S. work | 12-12-2019 | 17-03-2022 | MT | 1 | 2020 | 8
415 | BLD-2248-D-FCD¦WT15¦15'1 | FAÇADE WORK | 1997 | Facade work-Signage with back light | 12-12-2019 | 17-03-2022 | M2 | 350 | 2020 | 8
416 | BLD-2248-D-FCD¦WT15¦15'2 | FAÇADE WORK | 1998 | Facade work-custom designed M.S. work | 12-12-2019 | 17-03-2022 | MT | 5 | 2020 | 8
417 | BLD-2248-D-FCD¦WT16¦16 | FAÇADE WORK | 1999 | Facade work-Fixed alumiium louvers | 12-12-2019 | 17-03-2022 | M2 | 856 | 2020 | 8
418 | BLD-2248-D-FCD¦BMU¦17'1 | FAÇADE WORK | 2000 | Facade work-BMU system (Tower) | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
419 | BLD-2248-D-FCD¦BMU¦17'2 | FAÇADE WORK | 2001 | Facade work-BMU system (Hostel Block) | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
420 | BLD-2248-D-FCD¦LED¦18'1 | FAÇADE WORK | 2002 | Facade work-LED strip light (Tower) | 12-12-2019 | 17-03-2022 | M | 750 | 2020 | 8
421 | BLD-2248-D-FCD¦LED¦18'2 | FAÇADE WORK | 2003 | Facade work-LED strip light(Wall washer) | 12-12-2019 | 17-03-2022 | M | 242 | 2020 | 8
422 | BLD-2248-D-SW¦A'1 | SANITARY WORK (PHE) | 2004 | ITC of Wall EWC | 12-12-2019 | 17-03-2022 | EA | 278 | 2020 | 8
423 | BLD-2248-D-SW¦A¦2¦A | SANITARY WORK (PHE) | 2005 | ITC Wash Basin Oval | 12-12-2019 | 17-03-2022 | EA | 168 | 2020 | 8
424 | BLD-2248-D-SW¦A¦2¦B | SANITARY WORK (PHE) | 2006 | ITC Wash Basin Rectangular | 12-12-2019 | 17-03-2022 | EA | 113 | 2020 | 8
425 | BLD-2248-D-SW¦A¦3 | SANITARY WORK (PHE) | 2007 | ITC of Flat Back Urinal | 12-12-2019 | 17-03-2022 | EA | 128 | 2020 | 8
426 | BLD-2248-D-SW¦A¦4 | SANITARY WORK (PHE) | 2008 | ITC of Single Bowl Sink With Drain Board | 12-12-2019 | 17-03-2022 | EA | 23 | 2020 | 8
427 | BLD-2248-D-SW¦A¦5 | SANITARY WORK (PHE) | 2009 | ITC of CP 3 In One Wall Mixture | 12-12-2019 | 17-03-2022 | EA | 81 | 2020 | 8
428 | BLD-2248-D-SW¦A¦6 | SANITARY WORK (PHE) | 2010 | ITC of Vertical Water Cooler | 12-12-2019 | 17-03-2022 | EA | 28 | 2020 | 8
429 | BLD-2248-D-SW¦A¦7 | SANITARY WORK (PHE) | 2011 | ITC of Janitor Sink With Bibcock | 12-12-2019 | 17-03-2022 | EA | 17 | 2020 | 8
430 | BLD-2248-D-SW¦A¦8 | SANITARY WORK (PHE) | 2012 | ITC of Conceal Flush Valve | 12-12-2019 | 17-03-2022 | EA | 295 | 2020 | 8
431 | BLD-2248-D-SW¦A¦9 | SANITARY WORK (PHE) | 2013 | ITC of Automatic Flushing For Urinal | 12-12-2019 | 17-03-2022 | EA | 128 | 2020 | 8
432 | BLD-2248-D-SW¦A¦10 | SANITARY WORK (PHE) | 2014 | ITC of EWC Pillartap & Wash Basin | 12-12-2019 | 17-03-2022 | EA | 17 | 2020 | 8
433 | BLD-2248-D-SW¦A¦11 | SANITARY WORK (PHE) | 2015 | ITC of Urinal Partition | 12-12-2019 | 17-03-2022 | EA | 130 | 2020 | 8
434 | BLD-2248-D-SW¦A¦12 | SANITARY WORK (PHE) | 2016 | ITC of IWC With PVC Cistern | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
435 | BLD-2248-D-SW¦A¦13 | SANITARY WORK (PHE) | 2017 | ITC PVC WC Connector | 12-12-2019 | 17-03-2022 | EA | 296 | 2020 | 8
436 | BLD-2248-D-SW¦A¦14 | SANITARY WORK (PHE) | 2018 | ITC of Bevel Edge Mirror 5.5Mm Thick | 12-12-2019 | 17-03-2022 | M2 | 310 | 2020 | 8
437 | BLD-2248-D-SW¦A¦15 | SANITARY WORK (PHE) | 2019 | ITC of CP Angle Valve | 12-12-2019 | 17-03-2022 | EA | 606 | 2020 | 8
438 | BLD-2248-D-SW¦A¦16 | SANITARY WORK (PHE) | 2020 | ITC of 32Mm CP Bottle Trap With All Accs | 12-12-2019 | 17-03-2022 | EA | 281 | 2020 | 8
439 | BLD-2248-D-SW¦A¦17 | SANITARY WORK (PHE) | 2021 | ITC of 40Mm CP Bottle Trap With All Accs | 12-12-2019 | 17-03-2022 | EA | 23 | 2020 | 8
440 | BLD-2248-D-SW¦A¦18 | SANITARY WORK (PHE) | 2022 | ITC of 32Mm Dia CP Brass Waste Coupling | 12-12-2019 | 17-03-2022 | EA | 281 | 2020 | 8
441 | BLD-2248-D-SW¦A¦19 | SANITARY WORK (PHE) | 2023 | ITC of 40Mm Dia CP Brass Waste Coupling | 12-12-2019 | 17-03-2022 | EA | 23 | 2020 | 8
442 | BLD-2248-D-SW¦A¦20 | SANITARY WORK (PHE) | 2024 | ITC of 600Mm Long Braided Flexible Pipe | 12-12-2019 | 17-03-2022 | EA | 606 | 2020 | 8
443 | BLD-2248-D-SW¦A¦21 | SANITARY WORK (PHE) | 2025 | ITC of Pillar Tap For Wash Basin | 12-12-2019 | 17-03-2022 | EA | 281 | 2020 | 8
444 | BLD-2248-D-SW¦A¦22 | SANITARY WORK (PHE) | 2026 | ITC of Pillar Tap For Sink | 12-12-2019 | 17-03-2022 | EA | 23 | 2020 | 8
445 | BLD-2248-D-SW¦A¦23 | SANITARY WORK (PHE) | 2027 | ITC of CP Brass Health Faucet | 12-12-2019 | 17-03-2022 | EA | 295 | 2020 | 8
446 | BLD-2248-D-SW¦A¦24 | SANITARY WORK (PHE) | 2028 | ITC of Toilet Paper Holder | 12-12-2019 | 17-03-2022 | EA | 295 | 2020 | 8
447 | BLD-2248-D-SW¦A¦25 | SANITARY WORK (PHE) | 2029 | ITC of Soap Dispencer | 12-12-2019 | 17-03-2022 | EA | 281 | 2020 | 8
448 | BLD-2248-D-SW¦A¦26 | SANITARY WORK (PHE) | 2030 | ITC of CP Brass Coat Hook | 12-12-2019 | 17-03-2022 | EA | 296 | 2020 | 8
449 | BLD-2248-D-SW¦A¦27 | SANITARY WORK (PHE) | 2031 | ITC of CP Towel Rack | 12-12-2019 | 17-03-2022 | EA | 81 | 2020 | 8
450 | BLD-2248-D-SW¦A¦28 | SANITARY WORK (PHE) | 2032 | ITC of Tissue Paper Holder | 12-12-2019 | 17-03-2022 | EA | 65 | 2020 | 8
451 | BLD-2248-D-SW¦A¦29 | SANITARY WORK (PHE) | 2033 | ITC of CP Towel Ring | 12-12-2019 | 17-03-2022 | EA | 113 | 2020 | 8
452 | BLD-2248-D-SW¦A¦30 | SANITARY WORK (PHE) | 2034 | ITC of Hand Drier | 12-12-2019 | 17-03-2022 | EA | 43 | 2020 | 8
453 | BLD-2248-D-SW¦A¦31 | SANITARY WORK (PHE) | 2035 | ITC of CP Long Body Bibcock | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
454 | BLD-2248-D-SWL¦B¦1¦A | SOIL,WASTE, VENT PIPE (PHE) | 2036 | SITC of RW CI Pipe 100Mm Dia Is 3989 | 12-12-2019 | 17-03-2022 | M | 100 | 2020 | 8
455 | BLD-2248-D-SWL¦B¦1¦B | SOIL,WASTE, VENT PIPE (PHE) | 2037 | SITC of RW CI Pipe 150Mm Dia Is 3989 | 12-12-2019 | 17-03-2022 | M | 1200 | 2020 | 8
456 | BLD-2248-D-SWL¦B¦1¦C | SOIL,WASTE, VENT PIPE (PHE) | 2038 | SITC of RW CI Pipe 200Mm Dia Is 3989 | 12-12-2019 | 17-03-2022 | M | 40 | 2020 | 8
457 | BLD-2248-D-SWL¦B¦2¦A | SOIL,WASTE, VENT PIPE (PHE) | 2039 | SITC of Soil CI Pipe 75Mm Dia Is 3989 | 12-12-2019 | 17-03-2022 | M | 430 | 2020 | 8
458 | BLD-2248-D-SWL¦B¦2¦B | SOIL,WASTE, VENT PIPE (PHE) | 2040 | SITC of Soil CI Pipe 100Mm Dia Is 3989 | 12-12-2019 | 17-03-2022 | M | 2750 | 2020 | 8
459 | BLD-2248-D-SWL¦B¦2¦C | SOIL,WASTE, VENT PIPE (PHE) | 2041 | SITC of Soil CI Pipe 150Mm Dia Is 3989 | 12-12-2019 | 17-03-2022 | M | 5 | 2020 | 8
460 | BLD-2248-D-SWL¦B¦3¦A | SOIL,WASTE, VENT PIPE (PHE) | 2042 | SITC of 32Mm Dia GI Pipe Is 1239 | 12-12-2019 | 17-03-2022 | M | 250 | 2020 | 8
461 | BLD-2248-D-SWL¦B¦3¦B | SOIL,WASTE, VENT PIPE (PHE) | 2043 | SITC of 40Mm Dia GI Pipe Is 1239 | 12-12-2019 | 17-03-2022 | M | 70 | 2020 | 8
462 | BLD-2248-D-SWL¦B¦3¦C | SOIL,WASTE, VENT PIPE (PHE) | 2044 | SITC of 50Mm Dia GI Pipe Is 1239 | 12-12-2019 | 17-03-2022 | M | 85 | 2020 | 8
463 | BLD-2248-D-SWL¦B¦4¦A | SOIL,WASTE, VENT PIPE (PHE) | 2045 | Painting For CI Pipe 75Mm Dia | 12-12-2019 | 17-03-2022 | M | 430 | 2020 | 8
464 | BLD-2248-D-SWL¦B¦4¦B | SOIL,WASTE, VENT PIPE (PHE) | 2046 | Painting For CI Pipe 100Mm Dia | 12-12-2019 | 17-03-2022 | M | 2750 | 2020 | 8
465 | BLD-2248-D-SWL¦B¦4¦C | SOIL,WASTE, VENT PIPE (PHE) | 2047 | Painting For CI Pipe 150Mm Dia | 12-12-2019 | 17-03-2022 | M | 5 | 2020 | 8
466 | BLD-2248-D-SWL¦B¦5¦A | SOIL,WASTE, VENT PIPE (PHE) | 2048 | Painting of GI Pipe With Tape 32Mm Dia | 12-12-2019 | 17-03-2022 | M | 250 | 2020 | 8
467 | BLD-2248-D-SWL¦B¦5¦B | SOIL,WASTE, VENT PIPE (PHE) | 2049 | Painting of GI Pipe With Tape 40Mm Dia | 12-12-2019 | 17-03-2022 | M | 70 | 2020 | 8
468 | BLD-2248-D-SWL¦B¦5¦C | SOIL,WASTE, VENT PIPE (PHE) | 2050 | Painting of GI Pipe With Tape 50Mm Dia | 12-12-2019 | 17-03-2022 | M | 85 | 2020 | 8
469 | BLD-2248-D-SWL¦B¦6¦A | SOIL,WASTE, VENT PIPE (PHE) | 2051 | SITC of CI P Or S Trap 100Mm In & Out | 12-12-2019 | 17-03-2022 | EA | 582 | 2020 | 8
470 | BLD-2248-D-SWL¦B¦7¦A | SOIL,WASTE, VENT PIPE (PHE) | 2052 | SITC of GI Fd 100 X 50 Mm Elbow | 12-12-2019 | 17-03-2022 | EA | 3 | 2020 | 8
471 | BLD-2248-D-SWL¦B¦8 | SOIL,WASTE, VENT PIPE (PHE) | 2053 | SITC of GI Inlet Fab From 100Mm GI Pipe | 12-12-2019 | 17-03-2022 | EA | 582 | 2020 | 8
472 | BLD-2248-D-SWL¦B¦9 | SOIL,WASTE, VENT PIPE (PHE) | 2054 | SITC of Brass Clean Out Plug 100Mm Dia | 12-12-2019 | 17-03-2022 | EA | 278 | 2020 | 8
473 | BLD-2248-D-SWL¦B¦10¦A | SOIL,WASTE, VENT PIPE (PHE) | 2055 | SITC of Ss Ring & Grating 125Mm Dia | 12-12-2019 | 17-03-2022 | EA | 582 | 2020 | 8
474 | BLD-2248-D-SWL¦B¦11 | SOIL,WASTE, VENT PIPE (PHE) | 2056 | SITC of Brass Clean Out Plug 100Mm Dia | 12-12-2019 | 17-03-2022 | EA | 6 | 2020 | 8
475 | BLD-2248-D-SWL¦B¦12¦A | SOIL,WASTE, VENT PIPE (PHE) | 2057 | SITC of CI Cowl 75Mm Dia | 12-12-2019 | 17-03-2022 | EA | 7 | 2020 | 8
476 | BLD-2248-D-SWL¦B¦12¦B | SOIL,WASTE, VENT PIPE (PHE) | 2058 | SITC of CI Cowl 100Mm Dia | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
477 | BLD-2248-D-SWL¦B¦13¦A | SOIL,WASTE, VENT PIPE (PHE) | 2059 | SITC of CI Grating 125 X 125Mm | 12-12-2019 | 17-03-2022 | EA | 4 | 2020 | 8
478 | BLD-2248-D-SWL¦B¦13¦B | SOIL,WASTE, VENT PIPE (PHE) | 2060 | SITC of CI Grating 175 X 175Mm | 12-12-2019 | 17-03-2022 | EA | 22 | 2020 | 8
479 | BLD-2248-D-WS¦C¦1¦1'1¦A | WATER SUPPLY SYSTEM (PHE) | 2061 | SITC of GI Pipe B Class Cws Fws 15Mm Dia | 12-12-2019 | 17-03-2022 | M | 5 | 2020 | 8
480 | BLD-2248-D-WS¦C¦1¦1'1¦B | WATER SUPPLY SYSTEM (PHE) | 2062 | SITC of GI Pipe B Class Cws Fws 20Mm Dia | 12-12-2019 | 17-03-2022 | M | 35 | 2020 | 8
481 | BLD-2248-D-WS¦C¦1¦1'1¦C | WATER SUPPLY SYSTEM (PHE) | 2063 | SITC of GI Pipe B Class Cws Fws 25Mm Dia | 12-12-2019 | 17-03-2022 | M | 65 | 2020 | 8
482 | BLD-2248-D-WS¦C¦1¦1'1¦D | WATER SUPPLY SYSTEM (PHE) | 2064 | SITC of GI Pipe B Class Cws Fws 32Mm Dia | 12-12-2019 | 17-03-2022 | M | 90 | 2020 | 8
483 | BLD-2248-D-WS¦C¦1¦1'1¦E | WATER SUPPLY SYSTEM (PHE) | 2065 | SITC of GI Pipe B Class Cws Fws 40Mm Dia | 12-12-2019 | 17-03-2022 | M | 95 | 2020 | 8
484 | BLD-2248-D-WS¦C¦1¦1'1¦F | WATER SUPPLY SYSTEM (PHE) | 2066 | SITC of GI Pipe B Class Cws Fws 50Mm Dia | 12-12-2019 | 17-03-2022 | M | 250 | 2020 | 8
485 | BLD-2248-D-WS¦C¦1¦1'1¦G | WATER SUPPLY SYSTEM (PHE) | 2067 | SITC of GI Pipe B Class Cws Fws 65Mm Dia | 12-12-2019 | 17-03-2022 | M | 195 | 2020 | 8
486 | BLD-2248-D-WS¦C¦1¦1'1¦H | WATER SUPPLY SYSTEM (PHE) | 2068 | SITC of GI Pipe B Class Cws Fws 80Mm Dia | 12-12-2019 | 17-03-2022 | M | 230 | 2020 | 8
487 | BLD-2248-D-WS¦C¦1¦1'1¦I | WATER SUPPLY SYSTEM (PHE) | 2069 | SITC of GI Pipe B Class Cwsfws 100Mm Dia | 12-12-2019 | 17-03-2022 | M | 365 | 2020 | 8
488 | BLD-2248-D-WS¦C¦1¦1'1¦J | WATER SUPPLY SYSTEM (PHE) | 2070 | SITC of GI Pipe B Class Cwsfws 150Mm Dia | 12-12-2019 | 17-03-2022 | M | 30 | 2020 | 8
489 | BLD-2248-D-WS¦C¦1¦1'2¦A | WATER SUPPLY SYSTEM (PHE) | 2071 | SITC of GI Pipe B Class Hws 15Mm Dia | 12-12-2019 | 17-03-2022 | M | 185 | 2020 | 8
490 | BLD-2248-D-WS¦C¦1¦1'2¦B | WATER SUPPLY SYSTEM (PHE) | 2072 | SITC of GI Pipe B Class Hws 20Mm Dia | 12-12-2019 | 17-03-2022 | M | 270 | 2020 | 8
491 | BLD-2248-D-WS¦C¦1¦1'2¦C | WATER SUPPLY SYSTEM (PHE) | 2073 | SITC of GI Pipe B Class Hws 25Mm Dia | 12-12-2019 | 17-03-2022 | M | 150 | 2020 | 8
492 | BLD-2248-D-WS¦C¦1¦1'2¦D | WATER SUPPLY SYSTEM (PHE) | 2074 | SITC of GI Pipe B Class Hws 32Mm Dia | 12-12-2019 | 17-03-2022 | M | 175 | 2020 | 8
493 | BLD-2248-D-WS¦C¦1¦1'2¦E | WATER SUPPLY SYSTEM (PHE) | 2075 | SITC of GI Pipe B Class Hws 40Mm Dia | 12-12-2019 | 17-03-2022 | M | 95 | 2020 | 8
494 | BLD-2248-D-WS¦C¦1¦1'2¦F | WATER SUPPLY SYSTEM (PHE) | 2076 | SITC of GI Pipe B Class Hws 50Mm Dia | 12-12-2019 | 17-03-2022 | M | 20 | 2020 | 8
495 | BLD-2248-D-WS¦C¦1¦1'2¦G | WATER SUPPLY SYSTEM (PHE) | 2077 | SITC of GI Pipe B Class Hws 65Mm Dia | 12-12-2019 | 17-03-2022 | M | 100 | 2020 | 8
496 | BLD-2248-D-WS¦C¦1¦1'2¦H | WATER SUPPLY SYSTEM (PHE) | 2078 | SITC of GI Pipe B Class Hws 80Mm Dia | 12-12-2019 | 17-03-2022 | M | 100 | 2020 | 8
497 | BLD-2248-D-WS¦C¦1¦1'3¦A | WATER SUPPLY SYSTEM (PHE) | 2079 | SITC of GI Pipe B Class Riser 32Mm Dia | 12-12-2019 | 17-03-2022 | M | 70 | 2020 | 8
498 | BLD-2248-D-WS¦C¦1¦1'3¦B | WATER SUPPLY SYSTEM (PHE) | 2080 | SITC of GI Pipe B Class Riser 40Mm Dia | 12-12-2019 | 17-03-2022 | M | 100 | 2020 | 8
499 | BLD-2248-D-WS¦C¦1¦1'3¦C | WATER SUPPLY SYSTEM (PHE) | 2081 | SITC of GI Pipe B Class Riser 50Mm Dia | 12-12-2019 | 17-03-2022 | M | 240 | 2020 | 8
500 | BLD-2248-D-WS¦C¦1¦1'3¦D | WATER SUPPLY SYSTEM (PHE) | 2082 | SITC of GI Pipe B Class Riser 65Mm Dia | 12-12-2019 | 17-03-2022 | M | 165 | 2020 | 8
501 | BLD-2248-D-WS¦C¦2¦A | WATER SUPPLY SYSTEM (PHE) | 2083 | SITC of Cpvc Pipe Cwsfws 15Mm Dia Pipe | 12-12-2019 | 17-03-2022 | M | 700 | 2020 | 8
502 | BLD-2248-D-WS¦C¦2¦B | WATER SUPPLY SYSTEM (PHE) | 2084 | SITC of Cpvc Pipe Cwsfws 20Mm Dia Pipe | 12-12-2019 | 17-03-2022 | M | 1015 | 2020 | 8
503 | BLD-2248-D-WS¦C¦2¦C | WATER SUPPLY SYSTEM (PHE) | 2085 | SITC of Cpvc Pipe Cwsfws 25Mm Dia Pipe | 12-12-2019 | 17-03-2022 | M | 525 | 2020 | 8
504 | BLD-2248-D-WS¦C¦2¦D | WATER SUPPLY SYSTEM (PHE) | 2086 | SITC of Cpvc Pipe Cwsfws 32Mm Dia Pipe | 12-12-2019 | 17-03-2022 | M | 670 | 2020 | 8
505 | BLD-2248-D-WS¦C¦2¦E | WATER SUPPLY SYSTEM (PHE) | 2087 | SITC of Cpvc Pipe Cwsfws 40Mm Dia Pipe | 12-12-2019 | 17-03-2022 | M | 389.5 | 2020 | 8
506 | BLD-2248-D-WS¦C¦2¦F | WATER SUPPLY SYSTEM (PHE) | 2088 | SITC of Cpvc Pipe Cwsfws 50Mm Dia Pipe | 12-12-2019 | 17-03-2022 | M | 180 | 2020 | 8
507 | BLD-2248-D-WS¦C¦2¦G | WATER SUPPLY SYSTEM (PHE) | 2089 | SITC of Cpvc Pipe Cwsfws 65Mm Dia Pipe | 12-12-2019 | 17-03-2022 | M | 45 | 2020 | 8
508 | BLD-2248-D-WS¦C¦3¦A | WATER SUPPLY SYSTEM (PHE) | 2090 | SITC of 6Mm Nitrile Ins On 15Mm Dia Pipe | 12-12-2019 | 17-03-2022 | M | 185 | 2020 | 8
509 | BLD-2248-D-WS¦C¦3¦B | WATER SUPPLY SYSTEM (PHE) | 2091 | SITC of 6Mm Nitrile Ins On 20Mm Dia Pipe | 12-12-2019 | 17-03-2022 | M | 270 | 2020 | 8
510 | BLD-2248-D-WS¦C¦3¦C | WATER SUPPLY SYSTEM (PHE) | 2092 | SITC of 6Mm Nitrile Ins On 25Mm Dia Pipe | 12-12-2019 | 17-03-2022 | M | 150 | 2020 | 8
511 | BLD-2248-D-WS¦C¦3¦D | WATER SUPPLY SYSTEM (PHE) | 2093 | SITC of 6Mm Nitrile Ins On 32Mm Dia Pipe | 12-12-2019 | 17-03-2022 | M | 175 | 2020 | 8
512 | BLD-2248-D-WS¦C¦3¦E | WATER SUPPLY SYSTEM (PHE) | 2094 | SITC of 6Mm Nitrile Ins On 40Mm Dia Pipe | 12-12-2019 | 17-03-2022 | M | 95 | 2020 | 8
513 | BLD-2248-D-WS¦C¦3¦F | WATER SUPPLY SYSTEM (PHE) | 2095 | SITC of 6Mm Nitrile Ins On 50Mm Dia Pipe | 12-12-2019 | 17-03-2022 | M | 20 | 2020 | 8
514 | BLD-2248-D-WS¦C¦3¦G | WATER SUPPLY SYSTEM (PHE) | 2096 | SITC of 6Mm Nitrile Ins On 65Mm Dia Pipe | 12-12-2019 | 17-03-2022 | M | 100 | 2020 | 8
515 | BLD-2248-D-WS¦C¦3¦H | WATER SUPPLY SYSTEM (PHE) | 2097 | SITC of 6Mm Nitrile Ins On 80Mm Dia Pipe | 12-12-2019 | 17-03-2022 | M | 100 | 2020 | 8
516 | BLD-2248-D-WS¦C¦4¦A | WATER SUPPLY SYSTEM (PHE) | 2098 | SITC of GI Cladding Over Insl 15Mm Dia | 12-12-2019 | 17-03-2022 | M | 185 | 2020 | 8
517 | BLD-2248-D-WS¦C¦4¦B | WATER SUPPLY SYSTEM (PHE) | 2099 | SITC of GI Cladding Over Insl 20Mm Dia | 12-12-2019 | 17-03-2022 | M | 270 | 2020 | 8
518 | BLD-2248-D-WS¦C¦4¦C | WATER SUPPLY SYSTEM (PHE) | 2100 | SITC of GI Cladding Over Insl 25Mm Dia | 12-12-2019 | 17-03-2022 | M | 150 | 2020 | 8
519 | BLD-2248-D-WS¦C¦4¦D | WATER SUPPLY SYSTEM (PHE) | 2101 | SITC of GI Cladding Over Insl 32Mm Dia | 12-12-2019 | 17-03-2022 | M | 175 | 2020 | 8
520 | BLD-2248-D-WS¦C¦4¦E | WATER SUPPLY SYSTEM (PHE) | 2102 | SITC of GI Cladding Over Insl 40Mm Dia | 12-12-2019 | 17-03-2022 | M | 95 | 2020 | 8
521 | BLD-2248-D-WS¦C¦4¦F | WATER SUPPLY SYSTEM (PHE) | 2103 | SITC of GI Cladding Over Insl 50Mm Dia | 12-12-2019 | 17-03-2022 | M | 20 | 2020 | 8
522 | BLD-2248-D-WS¦C¦4¦G | WATER SUPPLY SYSTEM (PHE) | 2104 | SITC of GI Cladding Over Insl 65Mm Dia | 12-12-2019 | 17-03-2022 | M | 100 | 2020 | 8
523 | BLD-2248-D-WS¦C¦4¦H | WATER SUPPLY SYSTEM (PHE) | 2105 | SITC of GI Cladding Over Insl 80Mm Dia | 12-12-2019 | 17-03-2022 | M | 100 | 2020 | 8
524 | BLD-2248-D-WS¦C¦5¦A | WATER SUPPLY SYSTEM (PHE) | 2106 | SITC of Gm Ball Valve 15Mm Dia | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
525 | BLD-2248-D-WS¦C¦5¦B | WATER SUPPLY SYSTEM (PHE) | 2107 | SITC of Gm Ball Valve 20Mm Dia | 12-12-2019 | 17-03-2022 | EA | 141 | 2020 | 8
526 | BLD-2248-D-WS¦C¦5¦C | WATER SUPPLY SYSTEM (PHE) | 2108 | SITC of Gm Ball Valve 25Mm Dia | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
527 | BLD-2248-D-WS¦C¦5¦D | WATER SUPPLY SYSTEM (PHE) | 2109 | SITC of Gm Ball Valve 32Mm Dia | 12-12-2019 | 17-03-2022 | EA | 112 | 2020 | 8
528 | BLD-2248-D-WS¦C¦5¦E | WATER SUPPLY SYSTEM (PHE) | 2110 | SITC of Gm Ball Valve 40Mm Dia | 12-12-2019 | 17-03-2022 | EA | 43 | 2020 | 8
529 | BLD-2248-D-WS¦C¦6¦A | WATER SUPPLY SYSTEM (PHE) | 2111 | SITC of Of CI Butterfly Valve 50Mm Dia | 12-12-2019 | 17-03-2022 | EA | 39 | 2020 | 8
530 | BLD-2248-D-WS¦C¦6¦B | WATER SUPPLY SYSTEM (PHE) | 2112 | SITC of Of CI Butterfly Valve 65Mm Dia | 12-12-2019 | 17-03-2022 | EA | 11 | 2020 | 8
531 | BLD-2248-D-WS¦C¦6¦C | WATER SUPPLY SYSTEM (PHE) | 2113 | SITC of Of CI Butterfly Valve 80Mm Dia | 12-12-2019 | 17-03-2022 | EA | 6 | 2020 | 8
532 | BLD-2248-D-WS¦C¦6¦D | WATER SUPPLY SYSTEM (PHE) | 2114 | SITC of Of CI Butterfly Valve 100Mm Dia | 12-12-2019 | 17-03-2022 | EA | 6 | 2020 | 8
533 | BLD-2248-D-WS¦C¦6¦E | WATER SUPPLY SYSTEM (PHE) | 2115 | SITC of Of CI Butterfly Valve 150Mm Dia | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
534 | BLD-2248-D-WS¦C¦7¦A | WATER SUPPLY SYSTEM (PHE) | 2116 | SITC of Ss Body Solenoid Valve 65Mm Dia | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
535 | BLD-2248-D-WS¦C¦7¦B | WATER SUPPLY SYSTEM (PHE) | 2117 | SITC of Ss Body Solenoid Valve 50Mm Dia | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
536 | BLD-2248-D-WS¦C¦7¦C | WATER SUPPLY SYSTEM (PHE) | 2118 | SITC of Ss Body Solenoid Valve 40Mm Dia | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
537 | BLD-2248-D-WS¦C¦8¦A | WATER SUPPLY SYSTEM (PHE) | 2119 | SITC of Pressure Reducing Station 20Mm | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
538 | BLD-2248-D-WS¦C¦8¦B | WATER SUPPLY SYSTEM (PHE) | 2120 | SITC of Pressure Reducing Station 25Mm | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
539 | BLD-2248-D-WS¦C¦8¦C | WATER SUPPLY SYSTEM (PHE) | 2121 | SITC of Pressure Reducing Station 32Mm | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
540 | BLD-2248-D-WS¦C¦8¦D | WATER SUPPLY SYSTEM (PHE) | 2122 | SITC of Pressure Reducing Station 40Mm | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
541 | BLD-2248-D-WS¦C¦8¦E | WATER SUPPLY SYSTEM (PHE) | 2123 | SITC of Pressure Reducing Station 50Mm | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
542 | BLD-2248-D-WS¦C¦8¦F | WATER SUPPLY SYSTEM (PHE) | 2124 | SITC of Pressure Reducing Station 65Mm | 12-12-2019 | 17-03-2022 | EA | 7 | 2020 | 8
543 | BLD-2248-D-WS¦C¦8¦G | WATER SUPPLY SYSTEM (PHE) | 2125 | SITC of Pressure Reducing Station 80Mm | 12-12-2019 | 17-03-2022 | EA | 8 | 2020 | 8
544 | BLD-2248-D-WS¦C¦8¦H | WATER SUPPLY SYSTEM (PHE) | 2126 | SITC of Pressure Reducing Station 100Mm | 12-12-2019 | 17-03-2022 | EA | 3 | 2020 | 8
545 | BLD-2248-D-WS¦C¦9 | WATER SUPPLY SYSTEM (PHE) | 2127 | SITC of Disinfection For Line & Oht | 12-12-2019 | 17-03-2022 | JOB | 1 | 2020 | 8
546 | BLD-2248-D-ES¦D¦1¦A | EXTERNAL SERVICES (PHE) | 2128 | SITC of Stoneware Pipe 150Mm Dia | 12-12-2019 | 17-03-2022 | M | 55 | 2020 | 8
547 | BLD-2248-D-ES¦D¦1¦B | EXTERNAL SERVICES (PHE) | 2129 | SITC of Stoneware Pipe 200Mm Dia | 12-12-2019 | 17-03-2022 | M | 210 | 2020 | 8
548 | BLD-2248-D-ES¦D¦2¦A | EXTERNAL SERVICES (PHE) | 2130 | SITC of Rcc Pipe Np3 150Mm Dia | 12-12-2019 | 17-03-2022 | M | 30 | 2020 | 8
549 | BLD-2248-D-ES¦D¦2¦B | EXTERNAL SERVICES (PHE) | 2131 | SITC of Rcc Pipe Np3 250Mm Dia | 12-12-2019 | 17-03-2022 | M | 370 | 2020 | 8
550 | BLD-2248-D-ES¦D¦2¦C | EXTERNAL SERVICES (PHE) | 2132 | SITC of Rcc Pipe Np3 300Mm Dia | 12-12-2019 | 17-03-2022 | M | 215 | 2020 | 8
551 | BLD-2248-D-ES¦D¦2¦D | EXTERNAL SERVICES (PHE) | 2133 | SITC of Rcc Pipe Np3 450Mm Dia | 12-12-2019 | 17-03-2022 | M | 5 | 2020 | 8
552 | BLD-2248-D-ES¦D¦2¦E | EXTERNAL SERVICES (PHE) | 2134 | SITC of Rcc Pipe Np3 600Mm Dia | 12-12-2019 | 17-03-2022 | M | 20 | 2020 | 8
553 | BLD-2248-D-ES¦D¦3¦A | EXTERNAL SERVICES (PHE) | 2135 | SITC of Concrete Bed 15Cm For 150Mm Dia | 12-12-2019 | 17-03-2022 | M | 85 | 2020 | 8
554 | BLD-2248-D-ES¦D¦3¦B | EXTERNAL SERVICES (PHE) | 2136 | SITC of Concrete Bed 15Cm For 200Mm Dia | 12-12-2019 | 17-03-2022 | M | 210 | 2020 | 8
555 | BLD-2248-D-ES¦D¦3¦C | EXTERNAL SERVICES (PHE) | 2137 | SITC of Concrete Bed 15Cm For 250Mm Dia | 12-12-2019 | 17-03-2022 | M | 370 | 2020 | 8
556 | BLD-2248-D-ES¦D¦3¦D | EXTERNAL SERVICES (PHE) | 2138 | SITC of Concrete Bed 15Cm For 300Mm Dia | 12-12-2019 | 17-03-2022 | M | 215 | 2020 | 8
557 | BLD-2248-D-ES¦D¦3¦E | EXTERNAL SERVICES (PHE) | 2139 | SITC of Concrete Bed 15Cm For 450Mm Dia | 12-12-2019 | 17-03-2022 | M | 5 | 2020 | 8
558 | BLD-2248-D-ES¦D¦3¦F | EXTERNAL SERVICES (PHE) | 2140 | SITC of Concrete Bed 15Cm For 600Mm Dia | 12-12-2019 | 17-03-2022 | M | 20 | 2020 | 8
559 | BLD-2248-D-ES¦D¦4 | EXTERNAL SERVICES (PHE) | 2141 | SITC of S.W Gully Trap 150X 100Mm | 12-12-2019 | 17-03-2022 | EA | 12 | 2020 | 8
560 | BLD-2248-D-ES¦D¦5¦A | EXTERNAL SERVICES (PHE) | 2142 | SITC of Manhole 45X 45Cm Depth 60Cm | 12-12-2019 | 17-03-2022 | EA | 8 | 2020 | 8
561 | BLD-2248-D-ES¦D¦5¦B | EXTERNAL SERVICES (PHE) | 2143 | SITC of Manhole 60X 60Cm Depth 75Cm | 12-12-2019 | 17-03-2022 | EA | 4 | 2020 | 8
562 | BLD-2248-D-ES¦D¦5¦C | EXTERNAL SERVICES (PHE) | 2144 | SITC of Manhole 75X 75Cm Depth 100Cm | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
563 | BLD-2248-D-ES¦D¦5¦D | EXTERNAL SERVICES (PHE) | 2145 | SITC of Manhole 100X 100Cm Depth 150Cm | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
564 | BLD-2248-D-ES¦D¦5¦E | EXTERNAL SERVICES (PHE) | 2146 | SITC of Manhole 120X 120Cm Depth 150Cm | 12-12-2019 | 17-03-2022 | EA | 18 | 2020 | 8
565 | BLD-2248-D-ES¦D¦6¦A | EXTERNAL SERVICES (PHE) | 2147 | SITC of Manhole 75X 75Cm Depth 100Cm | 12-12-2019 | 17-03-2022 | EA | 12 | 2020 | 8
566 | BLD-2248-D-ES¦D¦6¦B | EXTERNAL SERVICES (PHE) | 2148 | SITC of Manhole 75X 75Cm Depth 100Cm | 12-12-2019 | 17-03-2022 | EA | 4 | 2020 | 8
567 | BLD-2248-D-ES¦D¦6¦C | EXTERNAL SERVICES (PHE) | 2149 | SITC of Manhole 75X 75Cm Depth 100Cm | 12-12-2019 | 17-03-2022 | EA | 8 | 2020 | 8
568 | BLD-2248-D-ES¦D¦6¦D | EXTERNAL SERVICES (PHE) | 2150 | SITC of Manhole 75X 75Cm Depth 100Cm | 12-12-2019 | 17-03-2022 | EA | 4 | 2020 | 8
569 | BLD-2248-D-ES¦D¦7 | EXTERNAL SERVICES (PHE) | 2151 | SITC of Rcpc Grating & Frame 600X 600Mm | 12-12-2019 | 17-03-2022 | EA | 28 | 2020 | 8
570 | BLD-2248-D-ES¦D¦8 | EXTERNAL SERVICES (PHE) | 2152 | SITC of CI Manhole Cover 600Mm Dia | 12-12-2019 | 17-03-2022 | EA | 36 | 2020 | 8
571 | BLD-2248-D-ES¦D¦9 | EXTERNAL SERVICES (PHE) | 2153 | SITC Orange Color Safety Foot Rest | 12-12-2019 | 17-03-2022 | EA | 200 | 2020 | 8
572 | BLD-2248-D-ES¦D¦10 | EXTERNAL SERVICES (PHE) | 2154 | SITC of Water Meter | 12-12-2019 | 17-03-2022 | JOB | 1 | 2020 | 8
573 | BLD-2248-D-ES¦D¦11 | EXTERNAL SERVICES (PHE) | 2155 | SITC Tapping From Municipal Line | 12-12-2019 | 17-03-2022 | JOB | 1 | 2020 | 8
574 | BLD-2248-D-ES¦D¦12¦A | EXTERNAL SERVICES (PHE) | 2156 | SITC Underground GI Pipe 50Mm Dia | 12-12-2019 | 17-03-2022 | M | 10 | 2020 | 8
575 | BLD-2248-D-ES¦D¦12¦B | EXTERNAL SERVICES (PHE) | 2157 | SITC Underground GI Pipe 65Mm Dia | 12-12-2019 | 17-03-2022 | M | 100 | 2020 | 8
576 | BLD-2248-D-ES¦D¦12¦C | EXTERNAL SERVICES (PHE) | 2158 | SITC Underground GI Pipe 80Mm Dia | 12-12-2019 | 17-03-2022 | M | 15 | 2020 | 8
577 | BLD-2248-D-ES¦D¦12¦D | EXTERNAL SERVICES (PHE) | 2159 | SITC Underground GI Pipe 100Mm Dia | 12-12-2019 | 17-03-2022 | M | 50 | 2020 | 8
578 | BLD-2248-D-ES¦D¦13¦A | EXTERNAL SERVICES (PHE) | 2160 | SITC Underground Upvc Pipe 50Mm Dia | 12-12-2019 | 17-03-2022 | M | 400 | 2020 | 8
579 | BLD-2248-D-ES¦D¦13¦B | EXTERNAL SERVICES (PHE) | 2161 | SITC Underground Upvc Pipe 40Mm Dia | 12-12-2019 | 17-03-2022 | M | 5 | 2020 | 8
580 | BLD-2248-D-ES¦D¦13¦C | EXTERNAL SERVICES (PHE) | 2162 | SITC Underground Upvc Pipe 32Mm Dia | 12-12-2019 | 17-03-2022 | M | 5 | 2020 | 8
581 | BLD-2248-D-ES¦D¦13¦D | EXTERNAL SERVICES (PHE) | 2163 | SITC Underground Upvc Pipe 25Mm Dia | 12-12-2019 | 17-03-2022 | M | 110 | 2020 | 8
582 | BLD-2248-D-ES¦D¦13¦E | EXTERNAL SERVICES (PHE) | 2164 | SITC Underground Upvc Pipe 20Mm Dia | 12-12-2019 | 17-03-2022 | M | 35 | 2020 | 8
583 | BLD-2248-D-ES¦D¦14¦A | EXTERNAL SERVICES (PHE) | 2165 | SITC of CI Butterfly Valve 50Mm Dia | 12-12-2019 | 17-03-2022 | EA | 3 | 2020 | 8
584 | BLD-2248-D-ES¦D¦14¦B | EXTERNAL SERVICES (PHE) | 2166 | SITC of CI Butterfly Valve 65Mm Dia | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
585 | BLD-2248-D-ES¦D¦14¦C | EXTERNAL SERVICES (PHE) | 2167 | SITC of CI Butterfly Valve 80Mm Dia | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
586 | BLD-2248-D-ES¦D¦14¦D | EXTERNAL SERVICES (PHE) | 2168 | SITC of CI Butterfly Valve 100Mm Dia | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
587 | BLD-2248-D-ES¦D¦15 | EXTERNAL SERVICES (PHE) | 2169 | SITC of 20Mm Dia Garden Hydrant Valve | 12-12-2019 | 17-03-2022 | EA | 26 | 2020 | 8
588 | BLD-2248-D-ES¦D¦16¦A | EXTERNAL SERVICES (PHE) | 2170 | SITC of Gm Ball Valve 20Mm Dia | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
589 | BLD-2248-D-ES¦D¦16¦B | EXTERNAL SERVICES (PHE) | 2171 | SITC of Gm Ball Valve 25Mm Dia | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
590 | BLD-2248-D-ES¦D¦16¦C | EXTERNAL SERVICES (PHE) | 2172 | SITC of Gm Ball Valve 32Mm Dia | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
591 | BLD-2248-D-ES¦D¦16¦D | EXTERNAL SERVICES (PHE) | 2173 | SITC of Gm Ball Valve 40Mm Dia | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
592 | BLD-2248-D-ES¦D¦17 | EXTERNAL SERVICES (PHE) | 2174 | SITC of Manhole 30X30X50 Cm Sfrc Cover | 12-12-2019 | 17-03-2022 | EA | 26 | 2020 | 8
593 | BLD-2248-D-ES¦D¦18 | EXTERNAL SERVICES (PHE) | 2175 | SITC of Manhole 60X60X75 Cm Rcc Cover | 12-12-2019 | 17-03-2022 | EA | 7 | 2020 | 8
594 | BLD-2248-D-PH¦E¦1¦1'1 | PUMP HOUSE (PHE) | 2176 | SITC of Filter Feed Pumps | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
595 | BLD-2248-D-PH¦E¦1¦1'2 | PUMP HOUSE (PHE) | 2177 | SITC of Make Up Pumps | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
596 | BLD-2248-D-PH¦E¦2¦2'1 | PUMP HOUSE (PHE) | 2178 | SITC of Domestic Pump To Office Block | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
597 | BLD-2248-D-PH¦E¦2¦2'2 | PUMP HOUSE (PHE) | 2179 | SITC of Domestic Pump To Hostel Block | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
598 | BLD-2248-D-PH¦E¦3 | PUMP HOUSE (PHE) | 2180 | SITC of Submersible Drainage Pump | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
599 | BLD-2248-D-PH¦E¦4 | PUMP HOUSE (PHE) | 2181 | SITC of Terrace Booster Pumps | 12-12-2019 | 17-03-2022 | SET | 2 | 2020 | 8
600 | BLD-2248-D-PH¦E¦5 | PUMP HOUSE (PHE) | 2182 | SITC of Rain Water Transfer Pump | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
601 | BLD-2248-D-PH¦E¦6¦A | PUMP HOUSE (PHE) | 2183 | SITC of Turbine Type Flow Meter 50Mm Dia | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
602 | BLD-2248-D-PH¦E¦6¦B | PUMP HOUSE (PHE) | 2184 | SITC of Turbine Type Flow Meter 65Mm Dia | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
603 | BLD-2248-D-PH¦E¦7¦A | PUMP HOUSE (PHE) | 2185 | SITC of C Class GI Pipe Is1239 150Mm Dia | 12-12-2019 | 17-03-2022 | M | 10 | 2020 | 8
604 | BLD-2248-D-PH¦E¦7¦B | PUMP HOUSE (PHE) | 2186 | SITC of C Class GI Pipe Is1239 100Mm Dia | 12-12-2019 | 17-03-2022 | M | 10 | 2020 | 8
605 | BLD-2248-D-PH¦E¦7¦C | PUMP HOUSE (PHE) | 2187 | SITC of C Class GI Pipe Is1239 80Mm Dia | 12-12-2019 | 17-03-2022 | M | 5 | 2020 | 8
606 | BLD-2248-D-PH¦E¦7¦D | PUMP HOUSE (PHE) | 2188 | SITC of C Class GI Pipe Is1239 65Mm Dia | 12-12-2019 | 17-03-2022 | M | 25 | 2020 | 8
607 | BLD-2248-D-PH¦E¦7¦E | PUMP HOUSE (PHE) | 2189 | SITC of C Class GI Pipe Is1239 50Mm Dia | 12-12-2019 | 17-03-2022 | M | 30 | 2020 | 8
608 | BLD-2248-D-PH¦E¦7¦F | PUMP HOUSE (PHE) | 2190 | SITC of C Class GI Pipe Is1239 40Mm Dia | 12-12-2019 | 17-03-2022 | M | 10 | 2020 | 8
609 | BLD-2248-D-PH¦E¦7¦G | PUMP HOUSE (PHE) | 2191 | SITC of C Class GI Pipe Is1239 25Mm Dia | 12-12-2019 | 17-03-2022 | M | 5 | 2020 | 8
610 | BLD-2248-D-PH¦E¦8¦A | PUMP HOUSE (PHE) | 2192 | SITC of Gm Ball Valve Is318 25Mm Dia | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
611 | BLD-2248-D-PH¦E¦8¦B | PUMP HOUSE (PHE) | 2193 | SITC of Gm Ball Valve Is318 40Mm Dia | 12-12-2019 | 17-03-2022 | EA | 4 | 2020 | 8
612 | BLD-2248-D-PH¦E¦9¦A | PUMP HOUSE (PHE) | 2194 | SITC of CI Butterfly Valve Pn2.0 80Mmdia | 12-12-2019 | 17-03-2022 | EA | 6 | 2020 | 8
613 | BLD-2248-D-PH¦E¦9¦B | PUMP HOUSE (PHE) | 2195 | SITC of CI Butterfly Valve Pn2.0 65Mmdia | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
614 | BLD-2248-D-PH¦E¦9¦C | PUMP HOUSE (PHE) | 2196 | SITC of CI Butterfly Valve Pn2.0 50Mmdia | 12-12-2019 | 17-03-2022 | EA | 10 | 2020 | 8
615 | BLD-2248-D-PH¦E¦10¦A | PUMP HOUSE (PHE) | 2197 | SITC of Nrv Pn2.0 50Mm Dia | 12-12-2019 | 17-03-2022 | EA | 4 | 2020 | 8
616 | BLD-2248-D-PH¦E¦10¦B | PUMP HOUSE (PHE) | 2198 | SITC of Nrv Pn2.0 65Mm Dia | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
617 | BLD-2248-D-PH¦E¦11¦A | PUMP HOUSE (PHE) | 2199 | SITC of CI Y Strainer 150Mm Dia | 12-12-2019 | 17-03-2022 | EA | 4 | 2020 | 8
618 | BLD-2248-D-PH¦E¦12 | PUMP HOUSE (PHE) | 2200 | SITC of Pressure Gauge 150Mm Dia | 12-12-2019 | 17-03-2022 | EA | 8 | 2020 | 8
619 | BLD-2248-D-PH¦E¦13¦A | PUMP HOUSE (PHE) | 2201 | SITC of Hd CI Manhole Cover For Ugr | 12-12-2019 | 17-03-2022 | EA | 12 | 2020 | 8
620 | BLD-2248-D-PH¦E¦13¦B | PUMP HOUSE (PHE) | 2202 | SITC of Ld CI Manhole Cover For Ohr | 12-12-2019 | 17-03-2022 | EA | 12 | 2020 | 8
621 | BLD-2248-D-PH¦E¦14 | PUMP HOUSE (PHE) | 2203 | SITC of 100 Mm Dia GI Vent Pipe | 12-12-2019 | 17-03-2022 | EA | 14 | 2020 | 8
622 | BLD-2248-D-PH¦E¦15 | PUMP HOUSE (PHE) | 2204 | SITC of PVC Foot Rest For Ugr & Oht | 12-12-2019 | 17-03-2022 | EA | 120 | 2020 | 8
623 | BLD-2248-D-PH¦E¦16¦A | PUMP HOUSE (PHE) | 2205 | SITC of 600Mm Galv Puddle Flange 25Mm | 12-12-2019 | 17-03-2022 | EA | 19 | 2020 | 8
624 | BLD-2248-D-PH¦E¦16¦B | PUMP HOUSE (PHE) | 2206 | SITC of 600Mm Galv Puddle Flange 32Mm | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
625 | BLD-2248-D-PH¦E¦16¦C | PUMP HOUSE (PHE) | 2207 | SITC of 600Mm Galv Puddle Flange 40Mm | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
626 | BLD-2248-D-PH¦E¦16¦D | PUMP HOUSE (PHE) | 2208 | SITC of 600Mm Galv Puddle Flange 50Mm | 12-12-2019 | 17-03-2022 | EA | 12 | 2020 | 8
627 | BLD-2248-D-PH¦E¦16¦E | PUMP HOUSE (PHE) | 2209 | SITC of 600Mm Galv Puddle Flange 65Mm | 12-12-2019 | 17-03-2022 | EA | 13 | 2020 | 8
628 | BLD-2248-D-PH¦E¦16¦F | PUMP HOUSE (PHE) | 2210 | SITC of 600Mm Galv Puddle Flange 80Mm | 12-12-2019 | 17-03-2022 | EA | 14 | 2020 | 8
629 | BLD-2248-D-PH¦E¦16¦G | PUMP HOUSE (PHE) | 2211 | SITC of 600Mm Galv Puddle Flange 100Mm | 12-12-2019 | 17-03-2022 | EA | 35 | 2020 | 8
630 | BLD-2248-D-PH¦E¦16¦H | PUMP HOUSE (PHE) | 2212 | SITC of 600Mm Galv Puddle Flange 150Mm | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
631 | BLD-2248-D-PH¦E¦16¦I | PUMP HOUSE (PHE) | 2213 | SITC of 600Mm Galv Puddle Flange 200Mm | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
632 | BLD-2248-D-WTP¦F¦1¦A | WATER TREATMENT PLANT (PHE) | 2214 | SITC of Multi Grated Filter | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
633 | BLD-2248-D-WTP¦F¦1¦B | WATER TREATMENT PLANT (PHE) | 2215 | SITC of Activated Carbon Filter | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
634 | BLD-2248-D-WTP¦F¦2 | WATER TREATMENT PLANT (PHE) | 2216 | SITC of Hdpe Tank of 500Ltrs | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
635 | BLD-2248-D-MCCPHE¦G¦1 | ELECTRICAL INSTALATION MCC (PHE) | 2217 | SITC of Phe & Wtp Mcc | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
636 | BLD-2248-D-HWS¦H¦1¦1'1 | HOT WATER SYSTEM (PHE) | 2218 | SITC of Air To Water Scroll Heat Pump | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
637 | BLD-2248-D-HWS¦H¦2¦2'3 | HOT WATER SYSTEM (PHE) | 2219 | SITC of 2500 Ltrs Ms Hot Water Tank | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
638 | BLD-2248-D-HWS¦H¦2¦2'4 | HOT WATER SYSTEM (PHE) | 2220 | SITC of Ball Valve 32Mm Dia | 12-12-2019 | 17-03-2022 | EA | 4 | 2020 | 8
639 | BLD-2248-D-HWS¦H¦2¦2'5 | HOT WATER SYSTEM (PHE) | 2221 | SITC of Y Strainer | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
640 | BLD-2248-D-HWS¦H¦2¦2'6 | HOT WATER SYSTEM (PHE) | 2222 | SITC of Pressure Gauge | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
641 | BLD-2248-D-HWS¦H¦2¦2'7 | HOT WATER SYSTEM (PHE) | 2223 | SITC of 32Mm Dia Piping With Insl & Clad | 12-12-2019 | 17-03-2022 | M | 15 | 2020 | 8
642 | BLD-2248-D-HWS¦H¦2¦2'8 | HOT WATER SYSTEM (PHE) | 2224 | SITC of Ball Valve For Drain | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
643 | BLD-2248-D-HWS¦H¦2¦2'9 | HOT WATER SYSTEM (PHE) | 2225 | SITC of Ball Valve For Ret Line | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
644 | BLD-2248-D-HTP¦A¦1'1¦A | HT SYSTEM WORK | 2226 | Supply of 33Kv Rmu 2 Ic 1 Og | 12-12-2019 | 17-03-2022 | SET | 0 | 2020 | 8
645 | BLD-2248-D-HTP¦A¦1'1¦B | HT SYSTEM WORK | 2227 | ITC of 33Kv Rmu | 12-12-2019 | 17-03-2022 | SET | 0 | 2020 | 8
646 | BLD-2248-D-HTP¦A¦1'2¦A | HT SYSTEM WORK | 2228 | Supply of 33Kv 1000Mva Ht Panel 1Ic 3Og | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
647 | BLD-2248-D-HTP¦A¦1'2¦B | HT SYSTEM WORK | 2229 | ITC of 33Kv 1000Mva Ht Panel 1Ic 3Og | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
648 | BLD-2248-D-HTP¦A¦1'3¦A | HT SYSTEM WORK | 2230 | Supply of 33Kv Ht Metering Panel | 12-12-2019 | 17-03-2022 | SET | 0 | 2020 | 8
649 | BLD-2248-D-HTP¦A¦1'3¦B | HT SYSTEM WORK | 2231 | ITC of 33Kv Ht Metering Panel | 12-12-2019 | 17-03-2022 | SET | 0 | 2020 | 8
650 | BLD-2248-D-TRF¦B¦1'1¦A | TRANSFORMER | 2232 | Supply of 1200Kva 3Ph Transformer | 12-12-2019 | 17-03-2022 | SET | 3 | 2020 | 8
651 | BLD-2248-D-TRF¦B¦1'1¦B | TRANSFORMER | 2233 | ITC of 1200Kva 3Ph Transformer | 12-12-2019 | 17-03-2022 | SET | 3 | 2020 | 8
652 | BLD-2248-D-HTCBL¦C¦1'1¦A | HT ANCILLARY SYSTEM WORK | 2234 | S&L of 3C X 300Sqmm 33Kv Xlpe Cable | 12-12-2019 | 17-03-2022 | M | 290 | 2020 | 8
653 | BLD-2248-D-HTCBL¦C¦1'2¦A | HT ANCILLARY SYSTEM WORK | 2235 | S&M End Termination of 33Kv 300Sqmmcable | 12-12-2019 | 17-03-2022 | EA | 10 | 2020 | 8
654 | BLD-2248-D-HTCBL¦C¦1'3¦A | HT ANCILLARY SYSTEM WORK | 2236 | S&L of GI Sleeves 150Mm Dia | 12-12-2019 | 17-03-2022 | M | 20 | 2020 | 8
655 | BLD-2248-D-HTCBL¦C¦1'3¦B | HT ANCILLARY SYSTEM WORK | 2237 | S&L of GI Sleeves 200Mm Dia | 12-12-2019 | 17-03-2022 | M | 5 | 2020 | 8
656 | BLD-2248-D-HTCBL¦C¦1'3¦C | HT ANCILLARY SYSTEM WORK | 2238 | S&L of GI Sleeves 300Mm Dia | 12-12-2019 | 17-03-2022 | M | 5 | 2020 | 8
657 | BLD-2248-D-HTCBL¦C¦1'4¦A | HT ANCILLARY SYSTEM WORK | 2239 | S&L 7C X 2.5Sqmm Cu Ar Control Cable | 12-12-2019 | 17-03-2022 | M | 240 | 2020 | 8
658 | BLD-2248-D-HTCBL¦C¦1'5¦A | HT ANCILLARY SYSTEM WORK | 2240 | End Termination7C X 2.5Sqmm Ctrl Cable | 12-12-2019 | 17-03-2022 | EA | 16 | 2020 | 8
659 | BLD-2248-D-E¦C¦2'1¦2'1'1 | HT ANCILLARY SYSTEM WORK | 2241 | SITC of Bare 50 X 6Mm Cu Tape | 12-12-2019 | 17-03-2022 | M | 280 | 2020 | 8
660 | BLD-2248-D-E¦C¦2'1¦2'1'2 | HT ANCILLARY SYSTEM WORK | 2242 | SITC of Bare 32 X 6Mm Cu Tape | 12-12-2019 | 17-03-2022 | M | 0 | 2020 | 8
661 | BLD-2248-D-E¦C¦2'1¦2'1'3 | HT ANCILLARY SYSTEM WORK | 2243 | SITC of Bare 50 X 6Mm Cu Tape | 12-12-2019 | 17-03-2022 | M | 160 | 2020 | 8
662 | BLD-2248-D-E¦C¦2'2 | HT ANCILLARY SYSTEM WORK | 2244 | SITC of 600 X600X 3.15 Mm Cu Plate Earth | 12-12-2019 | 17-03-2022 | EA | 6 | 2020 | 8
663 | BLD-2248-D-ETH¦C¦2'3 | HT ANCILLARY SYSTEM WORK | 2245 | SITC of 600 X600X 6.3 Mm GI Plate Earth | 12-12-2019 | 17-03-2022 | EA | 10 | 2020 | 8
664 | BLD-2248-D-E¦C¦2'4¦2'4'1 | HT ANCILLARY SYSTEM WORK | 2246 | SITC GI Pipe Road Crossing 150Mm Dia | 12-12-2019 | 17-03-2022 | M | 30 | 2020 | 8
665 | BLD-2248-D-M¦C¦3'1¦3'1'1 | HT ANCILLARY SYSTEM WORK | 2247 | SITC GI Pipe Road Crossing 50Mm Dia | 12-12-2019 | 17-03-2022 | M | 0 | 2020 | 8
666 | BLD-2248-D-M¦C¦3'1¦3'1'2 | HT ANCILLARY SYSTEM WORK | 2248 | SITC GI Pipe Road Crossing 100Mm Dia | 12-12-2019 | 17-03-2022 | M | 0 | 2020 | 8
667 | BLD-2248-D-MISC¦C¦3'2 | HT ANCILLARY SYSTEM WORK | 2249 | S&F of Shock Treatment Chart | 12-12-2019 | 17-03-2022 | SET | 6 | 2020 | 8
668 | BLD-2248-D-MISC¦C¦3'3 | HT ANCILLARY SYSTEM WORK | 2250 | S&F of Fire Buckets | 12-12-2019 | 17-03-2022 | SET | 6 | 2020 | 8
669 | BLD-2248-D-MISC¦C¦3'4 | HT ANCILLARY SYSTEM WORK | 2251 | S&F of Danger Boards | 12-12-2019 | 17-03-2022 | SET | 6 | 2020 | 8
670 | BLD-2248-D-MISC¦C¦3'5 | HT ANCILLARY SYSTEM WORK | 2252 | S&F of 1.8M X .9M Rubber Mats | 12-12-2019 | 17-03-2022 | SET | 10 | 2020 | 8
671 | BLD-2248-D-MISC¦C¦3'6 | HT ANCILLARY SYSTEM WORK | 2253 | S&F of Co2 Fire Extg 5 Ltrs | 12-12-2019 | 17-03-2022 | SET | 6 | 2020 | 8
672 | BLD-2248-D-MISC¦C¦3'7 | HT ANCILLARY SYSTEM WORK | 2254 | S&F of Sld Framed In 1000X800Mm Frame | 12-12-2019 | 17-03-2022 | SET | 6 | 2020 | 8
673 | BLD-2248-D-MISC¦C¦3'8 | HT ANCILLARY SYSTEM WORK | 2255 | Supply of Tool Kit With 33Kv Gloves | 12-12-2019 | 17-03-2022 | SET | 2 | 2020 | 8
674 | BLD-2248-D-MISC¦C¦3'9 | HT ANCILLARY SYSTEM WORK | 2256 | SITC of 150 X 40Mm Raceway With Jb | 12-12-2019 | 17-03-2022 | M | 30 | 2020 | 8
675 | BLD-2248-D-MISC¦C¦3'10¦G | HT ANCILLARY SYSTEM WORK | 2257 | Liasoning Charges For Substation | 12-12-2019 | 17-03-2022 | LS | 1 | 2020 | 8
676 | BLD-2248-D-PNTW¦A¦1'1 | LOW SIDE ELECTRICAL WORK | 2258 | Primary Point Cntrld By 6 Amp Switch | 12-12-2019 | 17-03-2022 | P | 720 | 2020 | 8
677 | BLD-2248-D-PNTW¦A¦1'2 | LOW SIDE ELECTRICAL WORK | 2259 | Secondary Point Incl Switch | 12-12-2019 | 17-03-2022 | P | 90 | 2020 | 8
678 | BLD-2248-D-PNTW¦A¦1'3 | LOW SIDE ELECTRICAL WORK | 2260 | Looping Between 1St Swtch Brd To 2Nd | 12-12-2019 | 17-03-2022 | P | 500 | 2020 | 8
679 | BLD-2248-D-PNTW¦A¦2'1 | LOW SIDE ELECTRICAL WORK | 2261 | Primary Point Cntrld By Mcb | 12-12-2019 | 17-03-2022 | P | 600 | 2020 | 8
680 | BLD-2248-D-PNTW¦A¦2'2 | LOW SIDE ELECTRICAL WORK | 2262 | Secondary Point Cntrld By Mcb | 12-12-2019 | 17-03-2022 | P | 2880 | 2020 | 8
681 | BLD-2248-D-PNTW¦A¦3 | LOW SIDE ELECTRICAL WORK | 2263 | Wiring For 250V Single Phase 16 Amps | 12-12-2019 | 17-03-2022 | P | 40 | 2020 | 8
682 | BLD-2248-D-PNTW¦A¦4 | LOW SIDE ELECTRICAL WORK | 2264 | Wiring For 250V Single Phase 32 Amps | 12-12-2019 | 17-03-2022 | P | 0 | 2020 | 8
683 | BLD-2248-D-PNTW¦A¦5 | LOW SIDE ELECTRICAL WORK | 2265 | Wiring For 250V Single Phase 6/16 Amps | 12-12-2019 | 17-03-2022 | P | 10 | 2020 | 8
684 | BLD-2248-D-PNTW¦A¦6'1 | LOW SIDE ELECTRICAL WORK | 2266 | Wiring Primary Point (250V S.Ph 6/16 A) | 12-12-2019 | 17-03-2022 | P | 420 | 2020 | 8
685 | BLD-2248-D-PNTW¦A¦6'2 | LOW SIDE ELECTRICAL WORK | 2267 | Wiring Secondary Point (250V S.Ph 16 A) | 12-12-2019 | 17-03-2022 | P | 512 | 2020 | 8
686 | BLD-2248-D-PNTW¦A¦7'1 | LOW SIDE ELECTRICAL WORK | 2268 | Wiring Primary Point (6A Switch Socket) | 12-12-2019 | 17-03-2022 | P | 60 | 2020 | 8
687 | BLD-2248-D-PNTW¦A¦7'2 | LOW SIDE ELECTRICAL WORK | 2269 | Wiring Secondary Point (> 6.1A) | 12-12-2019 | 17-03-2022 | P | 80 | 2020 | 8
688 | BLD-2248-D-PNTW¦A¦8 | LOW SIDE ELECTRICAL WORK | 2270 | Wiring For Exhaust Fan | 12-12-2019 | 17-03-2022 | P | 0 | 2020 | 8
689 | BLD-2248-D-PNTW¦A¦9'1 | LOW SIDE ELECTRICAL WORK | 2271 | P&F 4M2 PVC Insulated Cupper Conductor | 12-12-2019 | 17-03-2022 | M | 1100 | 2020 | 8
690 | BLD-2248-D-PNTW¦B¦1'1 | LOW SIDE ELECTRICAL WORK | 2272 | S&L Al Cable-3.5 Core 400 Sq. Mm | 12-12-2019 | 17-03-2022 | M | 2700 | 2020 | 8
691 | BLD-2248-D-PNTW¦B¦1'2 | LOW SIDE ELECTRICAL WORK | 2273 | S&L Al Cable-3.5 Core 300 Sq. Mm | 12-12-2019 | 17-03-2022 | M | 1500 | 2020 | 8
692 | BLD-2248-D-PNTW¦B¦1'3 | LOW SIDE ELECTRICAL WORK | 2274 | S&L Al Cable-3.5 Core 240 Sq. Mm | 12-12-2019 | 17-03-2022 | M | 700 | 2020 | 8
693 | BLD-2248-D-PNTW¦B¦1'4 | LOW SIDE ELECTRICAL WORK | 2275 | S&L Al Cable-3.5 Core 185 Sq. Mm | 12-12-2019 | 17-03-2022 | M | 450 | 2020 | 8
694 | BLD-2248-D-PNTW¦B¦1'5 | LOW SIDE ELECTRICAL WORK | 2276 | S&L Al Cable-3.5 Core 150 Sq. Mm | 12-12-2019 | 17-03-2022 | M | 400 | 2020 | 8
695 | BLD-2248-D-PNTW¦B¦1'6 | LOW SIDE ELECTRICAL WORK | 2277 | S&L Al Cable-3.5 Core 120 Sq. Mm | 12-12-2019 | 17-03-2022 | M | 200 | 2020 | 8
696 | BLD-2248-D-PNTW¦B¦1'7 | LOW SIDE ELECTRICAL WORK | 2278 | S&L Al Cable-3.5 Core 95 Sq. Mm | 12-12-2019 | 17-03-2022 | M | 200 | 2020 | 8
697 | BLD-2248-D-PNTW¦B¦1'8 | LOW SIDE ELECTRICAL WORK | 2279 | S&L Al Cable-3.5 Core 70 Sq. Mm | 12-12-2019 | 17-03-2022 | M | 1200 | 2020 | 8
698 | BLD-2248-D-PNTW¦B¦1'9 | LOW SIDE ELECTRICAL WORK | 2280 | S&L Al Cable-3.5 Core 50 Sq. Mm | 12-12-2019 | 17-03-2022 | M | 750 | 2020 | 8
699 | BLD-2248-D-PNTW¦B¦1'10 | LOW SIDE ELECTRICAL WORK | 2281 | S&L Al Cable-3.5 Core 35 Sq. Mm | 12-12-2019 | 17-03-2022 | M | 500 | 2020 | 8
700 | BLD-2248-D-PNTW¦B¦1'11 | LOW SIDE ELECTRICAL WORK | 2282 | S&L Al Cable-3.5 Core 25 Sq. Mm | 12-12-2019 | 17-03-2022 | M | 2200 | 2020 | 8
701 | BLD-2248-D-PNTW¦B¦1'12 | LOW SIDE ELECTRICAL WORK | 2283 | S&L Al Cable-4 Core 16 Sq.Mm | 12-12-2019 | 17-03-2022 | M | 2400 | 2020 | 8
702 | BLD-2248-D-PNTW¦B¦2'1 | LOW SIDE ELECTRICAL WORK | 2284 | S&L Cu Cable-4 Core 10 Sq. Mm. | 12-12-2019 | 17-03-2022 | M | 7200 | 2020 | 8
703 | BLD-2248-D-PNTW¦B¦2'2 | LOW SIDE ELECTRICAL WORK | 2285 | S&L Cu Cable-4 Core 6 Sq.Mm | 12-12-2019 | 17-03-2022 | M | 2500 | 2020 | 8
704 | BLD-2248-D-PNTW¦B¦2'3 | LOW SIDE ELECTRICAL WORK | 2286 | S&L Cu Cable-4 Core 4 Sq.Mm | 12-12-2019 | 17-03-2022 | M | 0 | 2020 | 8
705 | BLD-2248-D-PNTW¦B¦2'4 | LOW SIDE ELECTRICAL WORK | 2287 | S&L Cu Cable-3 Core 10 Sq.Mm | 12-12-2019 | 17-03-2022 | M | 0 | 2020 | 8
706 | BLD-2248-D-PNTW¦B¦2'5 | LOW SIDE ELECTRICAL WORK | 2288 | S&L Cu Cable-3 Core 6 Sq. Mm. | 12-12-2019 | 17-03-2022 | M | 4800 | 2020 | 8
707 | BLD-2248-D-PNTW¦B¦2'6 | LOW SIDE ELECTRICAL WORK | 2289 | S&L Cu Cable-3 Core 4 Sq. Mm. | 12-12-2019 | 17-03-2022 | M | 0 | 2020 | 8
708 | BLD-2248-D-PNTW¦B¦3 | LOW SIDE ELECTRICAL WORK | 2290 | S&L 2.5 Mm2 Control Cable | 12-12-2019 | 17-03-2022 | M | 0 | 2020 | 8
709 | BLD-2248-D-PNTW¦B¦4'1 | LOW SIDE ELECTRICAL WORK | 2291 | S&L Al Cable-3.5 Core 400 Sq. Mm | 12-12-2019 | 17-03-2022 | EA | 260 | 2020 | 8
710 | BLD-2248-D-PNTW¦B¦4'2 | LOW SIDE ELECTRICAL WORK | 2292 | S&L Al Cable-3.5 Core 300 Sq. Mm | 12-12-2019 | 17-03-2022 | EA | 40 | 2020 | 8
711 | BLD-2248-D-PNTW¦B¦4'3 | LOW SIDE ELECTRICAL WORK | 2293 | S&L Al Cable-3.5 Core 240 Sq. Mm | 12-12-2019 | 17-03-2022 | EA | 40 | 2020 | 8
712 | BLD-2248-D-PNTW¦B¦4'4 | LOW SIDE ELECTRICAL WORK | 2294 | S&L Al Cable-3.5 Core 185 Sq. Mm | 12-12-2019 | 17-03-2022 | EA | 10 | 2020 | 8
713 | BLD-2248-D-PNTW¦B¦4'5 | LOW SIDE ELECTRICAL WORK | 2295 | S&L Al Cable-3.5 Core 150 Sq. Mm | 12-12-2019 | 17-03-2022 | EA | 10 | 2020 | 8
714 | BLD-2248-D-PNTW¦B¦4'6 | LOW SIDE ELECTRICAL WORK | 2296 | S&L Al Cable-3.5 Core 120 Sq. Mm | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
715 | BLD-2248-D-PNTW¦B¦4'7 | LOW SIDE ELECTRICAL WORK | 2297 | S&L Al Cable-3.5 Core 95 Sq. Mm | 12-12-2019 | 17-03-2022 | EA | 8 | 2020 | 8
716 | BLD-2248-D-PNTW¦B¦4'8 | LOW SIDE ELECTRICAL WORK | 2298 | S&L Al Cable-3.5 Core 70 Sq. Mm | 12-12-2019 | 17-03-2022 | EA | 44 | 2020 | 8
717 | BLD-2248-D-PNTW¦B¦4'9 | LOW SIDE ELECTRICAL WORK | 2299 | S&L Al Cable-3.5 Core 50 Sq. Mm | 12-12-2019 | 17-03-2022 | EA | 56 | 2020 | 8
718 | BLD-2248-D-PNTW¦B¦4'10 | LOW SIDE ELECTRICAL WORK | 2300 | S&L Al Cable-3.5 Core 35 Sq. Mm | 12-12-2019 | 17-03-2022 | EA | 38 | 2020 | 8
719 | BLD-2248-D-PNTW¦B¦4'11 | LOW SIDE ELECTRICAL WORK | 2301 | S&L Al Cable-3.5 Core 25 Sq. Mm | 12-12-2019 | 17-03-2022 | EA | 56 | 2020 | 8
720 | BLD-2248-D-PNTW¦B¦4'12 | LOW SIDE ELECTRICAL WORK | 2302 | S&L Al Cable-4 Core 16 Sq.Mm | 12-12-2019 | 17-03-2022 | EA | 210 | 2020 | 8
721 | BLD-2248-D-PNTW¦B¦4'13 | LOW SIDE ELECTRICAL WORK | 2303 | S&L 4 Core 10 Sq. Mm Copper Cable | 12-12-2019 | 17-03-2022 | EA | 190 | 2020 | 8
722 | BLD-2248-D-PNTW¦B¦4'14 | LOW SIDE ELECTRICAL WORK | 2304 | S&L 4 Core 6 Sq.Mm Copper Cable | 12-12-2019 | 17-03-2022 | EA | 90 | 2020 | 8
723 | BLD-2248-D-PNTW¦B¦4'15 | LOW SIDE ELECTRICAL WORK | 2305 | S&L 4 Core 4 Sq.Mm Copper Cable | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
724 | BLD-2248-D-PNTW¦B¦4'16 | LOW SIDE ELECTRICAL WORK | 2306 | S&L 3 Core 10 Sq.Mm Copper Cable | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
725 | BLD-2248-D-PNTW¦B¦4'17 | LOW SIDE ELECTRICAL WORK | 2307 | S&L 3 Core 6 Sq. Mm Copper Cable | 12-12-2019 | 17-03-2022 | EA | 220 | 2020 | 8
726 | BLD-2248-D-PNTW¦B¦4'18 | LOW SIDE ELECTRICAL WORK | 2308 | S&L 3 Core 4 Sq. Mm Copper Cable | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
727 | BLD-2248-D-PNTW¦B¦5'1 | LOW SIDE ELECTRICAL WORK | 2309 | P&F M Class GI Pipe Sleeves-100 Mm. Dia. | 12-12-2019 | 17-03-2022 | M | 15 | 2020 | 8
728 | BLD-2248-D-PNTW¦B¦5'2 | LOW SIDE ELECTRICAL WORK | 2310 | P&F M Class GI Pipe Sleeves-50 Mm. Dia. | 12-12-2019 | 17-03-2022 | M | 15 | 2020 | 8
729 | BLD-2248-D-PNTW¦C¦1'1 | LOW SIDE ELECTRICAL WORK | 2311 | S&F Fabricated GI Ladder-1500 Mm Wide | 12-12-2019 | 17-03-2022 | M | 300 | 2020 | 8
730 | BLD-2248-D-PNTW¦C¦1'2 | LOW SIDE ELECTRICAL WORK | 2312 | S&F Fabricated GI Ladder-1200 Mm Wide | 12-12-2019 | 17-03-2022 | M | 200 | 2020 | 8
731 | BLD-2248-D-PNTW¦C¦1'3 | LOW SIDE ELECTRICAL WORK | 2313 | S&F Fabricated GI Ladder-1000 Mm Wide | 12-12-2019 | 17-03-2022 | M | 150 | 2020 | 8
732 | BLD-2248-D-PNTW¦C¦1'4 | LOW SIDE ELECTRICAL WORK | 2314 | S&F Fabricated GI Ladder-750 Mm Wide | 12-12-2019 | 17-03-2022 | M | 400 | 2020 | 8
733 | BLD-2248-D-PNTW¦C¦1'5 | LOW SIDE ELECTRICAL WORK | 2315 | S&F Fabricated GI Ladder-600 Mm Wide | 12-12-2019 | 17-03-2022 | M | 750 | 2020 | 8
734 | BLD-2248-D-PNTW¦C¦1'6 | LOW SIDE ELECTRICAL WORK | 2316 | S&F Fabricated GI Ladder-450 Mm Wide | 12-12-2019 | 17-03-2022 | M | 1000 | 2020 | 8
735 | BLD-2248-D-PNTW¦C¦2'1 | LOW SIDE ELECTRICAL WORK | 2317 | S&F GI Cable Tray-450 Mm (40X40X2Mm) | 12-12-2019 | 17-03-2022 | M | 900 | 2020 | 8
736 | BLD-2248-D-PNTW¦C¦2'2 | LOW SIDE ELECTRICAL WORK | 2318 | S&F GI Cable Tray-300 Mm (40X40X2Mm) | 12-12-2019 | 17-03-2022 | M | 400 | 2020 | 8
737 | BLD-2248-D-PNTW¦C¦2'3 | LOW SIDE ELECTRICAL WORK | 2319 | S&F GI Cable Tray-150 Mm (40X40X2Mm) | 12-12-2019 | 17-03-2022 | M | 100 | 2020 | 8
738 | BLD-2248-D-HUME¦C¦3'1 | LOW SIDE ELECTRICAL WORK | 2320 | S&F Rcc (Np-2) Hume Pipe-300 Mm (Id) | 12-12-2019 | 17-03-2022 | M | 30 | 2020 | 8
739 | BLD-2248-D-HUME¦C¦3'2 | LOW SIDE ELECTRICAL WORK | 2321 | S&F Rcc (Np-2) Hume Pipe-200 Mm (Id) | 12-12-2019 | 17-03-2022 | M | 5 | 2020 | 8
740 | BLD-2248-D-HUME¦C¦3'3 | LOW SIDE ELECTRICAL WORK | 2322 | S&F Rcc (Np-2) Hume Pipe-150 Mm (Id) | 12-12-2019 | 17-03-2022 | M | 10 | 2020 | 8
741 | BLD-2248-D-PNL¦D¦1 | LOW SIDE ELECTRICAL WORK | 2323 | SITC of Dg Sync & Load Managing Panel | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
742 | BLD-2248-D-PNL¦D¦2 | LOW SIDE ELECTRICAL WORK | 2324 | SITC of Main Lt Cum Change Over Panel | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
743 | BLD-2248-D-PNL¦D¦3 | LOW SIDE ELECTRICAL WORK | 2325 | SITC of Common Utility/Emergency Panel | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
744 | BLD-2248-D-PNL¦D¦4 | LOW SIDE ELECTRICAL WORK | 2326 | SITC of Hvac Odu Panel Hostel | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
745 | BLD-2248-D-PNL¦D¦5 | LOW SIDE ELECTRICAL WORK | 2327 | SITC of Parkingventillation Panel Office | 12-12-2019 | 17-03-2022 | SET | 0 | 2020 | 8
746 | BLD-2248-D-PNL¦D¦6 | LOW SIDE ELECTRICAL WORK | 2328 | SITC of Common Area Lighting Panel Off | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
747 | BLD-2248-D-PNL¦D¦7 | LOW SIDE ELECTRICAL WORK | 2329 | SITC of External Lighting Panel | 12-12-2019 | 17-03-2022 | SET | 2 | 2020 | 8
748 | BLD-2248-D-PNL¦D¦8 | LOW SIDE ELECTRICAL WORK | 2330 | SITC of Comm Area Power Dist Panel | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
749 | BLD-2248-D-PNL¦D¦9 | LOW SIDE ELECTRICAL WORK | 2331 | SITC of Comm Utility/Emgy Panel Hostel | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
750 | BLD-2248-D-PNL¦D¦10 | LOW SIDE ELECTRICAL WORK | 2332 | SITC of Lift Dist Panel 1 Office | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
751 | BLD-2248-D-PNL¦D¦11 | LOW SIDE ELECTRICAL WORK | 2333 | SITC of Lift Dist Panel 2 Office | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
752 | BLD-2248-D-PNL¦D¦12 | LOW SIDE ELECTRICAL WORK | 2334 | SITC of Lift Dist Panel Hostel | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
753 | BLD-2248-D-PNL¦D¦13 | LOW SIDE ELECTRICAL WORK | 2335 | SITC of Terrace Ventilation Panel Off | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
754 | BLD-2248-D-PNL¦D¦14 | LOW SIDE ELECTRICAL WORK | 2336 | SITC of Terrace Ventilation Panel Hstl | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
755 | BLD-2248-D-PNL¦D¦15 | LOW SIDE ELECTRICAL WORK | 2337 | SITC of Ups Panel Common Area | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
756 | BLD-2248-D-PNL¦D¦16¦16'1 | LOW SIDE ELECTRICAL WORK | 2338 | SITC of Floor Dist Panel Fdb3 -Fdb17 Off | 12-12-2019 | 17-03-2022 | SET | 16 | 2020 | 8
757 | BLD-2248-D-PNL¦D¦16¦16'2 | LOW SIDE ELECTRICAL WORK | 2339 | SITC of Floor Dist Panel Fdb1 Off | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
758 | BLD-2248-D-PNL¦D¦16¦16'3 | LOW SIDE ELECTRICAL WORK | 2340 | SITC of Floor Dist Panel Fdb2 Off | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
759 | BLD-2248-D-PNL¦D¦16¦16'4 | LOW SIDE ELECTRICAL WORK | 2341 | SITC of Floor Dist Panel Fdb3-Fdb12 Hstl | 12-12-2019 | 17-03-2022 | SET | 10 | 2020 | 8
760 | BLD-2248-D-PNL¦D¦16¦16'5 | LOW SIDE ELECTRICAL WORK | 2342 | SITC of Floor Dist Panel Fdb1 Hstl | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
761 | BLD-2248-D-PNL¦D¦16¦16'6 | LOW SIDE ELECTRICAL WORK | 2343 | SITC of Floor Dist Panel Fdb2 Hstl | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
762 | BLD-2248-D-PNL¦D¦17¦17'1 | LOW SIDE ELECTRICAL WORK | 2344 | SITC of 2500Amps Busduct From Trafo | 12-12-2019 | 17-03-2022 | M | 60 | 2020 | 8
763 | BLD-2248-D-PNL¦D¦17¦17'2 | LOW SIDE ELECTRICAL WORK | 2345 | SITC of 2500Amps Busduct From Dg Sync | 12-12-2019 | 17-03-2022 | M | 50 | 2020 | 8
764 | BLD-2248-D-PNL¦D¦17¦17'3 | LOW SIDE ELECTRICAL WORK | 2346 | SITC of 3000Amp Tinned Cu Connection | 12-12-2019 | 17-03-2022 | EA | 12 | 2020 | 8
765 | BLD-2248-D-PNL¦D¦18¦18'1 | LOW SIDE ELECTRICAL WORK | 2347 | SITC of 1600Amp Rising Main 1 | 12-12-2019 | 17-03-2022 | M | 120 | 2020 | 8
766 | BLD-2248-D-PNL¦D¦18¦18'2 | LOW SIDE ELECTRICAL WORK | 2348 | SITC of 1600Amp Rising Main 2 | 12-12-2019 | 17-03-2022 | M | 120 | 2020 | 8
767 | BLD-2248-D-PNL¦D¦18¦18'3 | LOW SIDE ELECTRICAL WORK | 2349 | SITC of 800Amp Rising Main 3 | 12-12-2019 | 17-03-2022 | M | 120 | 2020 | 8
768 | BLD-2248-D-PNL¦D¦19 | LOW SIDE ELECTRICAL WORK | 2350 | SITC 1600Amp 4P Acb For Rising Main | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
769 | BLD-2248-D-PNL¦D¦20 | LOW SIDE ELECTRICAL WORK | 2351 | SITC 800Amp 4P Acb For Rising Main | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
770 | BLD-2248-D-PNL¦D¦21¦21'1 | LOW SIDE ELECTRICAL WORK | 2352 | SITC of 500Amp Tpn Mccb Tapoff Box | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
771 | BLD-2248-D-PNL¦D¦21¦21'2 | LOW SIDE ELECTRICAL WORK | 2353 | SITC of 400Amp Tpn Mccb Tapoff Box | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
772 | BLD-2248-D-PNL¦D¦21¦21'3 | LOW SIDE ELECTRICAL WORK | 2354 | SITC of 200Amp Tpn Mccb Tapoff Box | 12-12-2019 | 17-03-2022 | EA | 32 | 2020 | 8
773 | BLD-2248-D-PNL¦D¦21¦21'4 | LOW SIDE ELECTRICAL WORK | 2355 | SITC of 160Amp Tpn Mccb Tapoff Box | 12-12-2019 | 17-03-2022 | EA | 3 | 2020 | 8
774 | BLD-2248-D-PNL¦D¦21¦21'5 | LOW SIDE ELECTRICAL WORK | 2356 | SITC of 125Amp Tpn Mccb Tapoff Box | 12-12-2019 | 17-03-2022 | EA | 20 | 2020 | 8
775 | BLD-2248-D-PNL¦D¦21¦21'6 | LOW SIDE ELECTRICAL WORK | 2357 | SITC of 100Amp Tpn Mccb Tapoff Box | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
776 | BLD-2248-D-PNL¦D¦22¦22'1 | LOW SIDE ELECTRICAL WORK | 2358 | SITC of 36Way Tpndb Typ A Ldb | 12-12-2019 | 17-03-2022 | EA | 9 | 2020 | 8
777 | BLD-2248-D-PNL¦D¦22¦22'2 | LOW SIDE ELECTRICAL WORK | 2359 | SITC of 36Way Tpndb Typ B Pdb | 12-12-2019 | 17-03-2022 | EA | 9 | 2020 | 8
778 | BLD-2248-D-PNL¦D¦22¦22'3 | LOW SIDE ELECTRICAL WORK | 2360 | SITC of 24Way Tpndb Typ C Ldb | 12-12-2019 | 17-03-2022 | EA | 9 | 2020 | 8
779 | BLD-2248-D-PNL¦D¦22¦22'4 | LOW SIDE ELECTRICAL WORK | 2361 | SITC of 24Way Tpndb Typ D Ldb | 12-12-2019 | 17-03-2022 | EA | 3 | 2020 | 8
780 | BLD-2248-D-PNL¦D¦22¦22'5 | LOW SIDE ELECTRICAL WORK | 2362 | SITC of 18Way Tpndb Typ E Pdb | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
781 | BLD-2248-D-PNL¦D¦22¦22'6 | LOW SIDE ELECTRICAL WORK | 2363 | SITC of 12Way Tpndb Typ F Pdb | 12-12-2019 | 17-03-2022 | EA | 10 | 2020 | 8
782 | BLD-2248-D-PNL¦D¦22¦22'7 | LOW SIDE ELECTRICAL WORK | 2364 | SITC of 12Way Tpndb Typ C Edb | 12-12-2019 | 17-03-2022 | EA | 4 | 2020 | 8
783 | BLD-2248-D-PNL¦D¦22¦22'8 | LOW SIDE ELECTRICAL WORK | 2365 | SITC of 18Way Tpndb Typ C Edb | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
784 | BLD-2248-D-PNL¦D¦22¦22'9 | LOW SIDE ELECTRICAL WORK | 2366 | SITC of 2+16Way Spndb Typ G Eldb | 12-12-2019 | 17-03-2022 | EA | 8 | 2020 | 8
785 | BLD-2248-D-PN¦D¦22¦22'10 | LOW SIDE ELECTRICAL WORK | 2367 | SITC of 2+12Way Spndb Typ H Eldb | 12-12-2019 | 17-03-2022 | EA | 9 | 2020 | 8
786 | BLD-2248-D-PN¦D¦22¦22'11 | LOW SIDE ELECTRICAL WORK | 2368 | SITC of 2+8Way Spndb Typ H Eldb | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
787 | BLD-2248-D-PN¦D¦22¦22'12 | LOW SIDE ELECTRICAL WORK | 2369 | SITC of 2+8Way Spndb Typ I Ldb | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
788 | BLD-2248-D-PN¦D¦22¦22'13 | LOW SIDE ELECTRICAL WORK | 2370 | SITC of 2+8Way Spndb Typ I Pdb | 12-12-2019 | 17-03-2022 | EA | 4 | 2020 | 8
789 | BLD-2248-D-PNL¦D¦23 | LOW SIDE ELECTRICAL WORK | 2371 | SITC of 63Amp 4P Mcb Isso With Enclosure | 12-12-2019 | 17-03-2022 | EA | 4 | 2020 | 8
790 | BLD-2248-D-PNL¦D¦24 | LOW SIDE ELECTRICAL WORK | 2372 | SITC of 16Amp 4P Metal Clad Socket & Mcb | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
791 | BLD-2248-D-PNL¦D¦25 | LOW SIDE ELECTRICAL WORK | 2373 | S&F 1000Mm Wide 1.1Kv Grade Rubber Mat | 12-12-2019 | 17-03-2022 | M | 40 | 2020 | 8
792 | BLD-2248-D-APFC¦E¦1 | LOW SIDE ELECTRICAL WORK | 2374 | SITC of 600Kvar Apfc Panel | 12-12-2019 | 17-03-2022 | SET | 3 | 2020 | 8
793 | BLD-2248-D-ERTH¦F1¦1 | LOW SIDE ELECTRICAL WORK | 2375 | SITC of 600X600X3.15Mm Cu Plate Earth | 12-12-2019 | 17-03-2022 | EA | 20 | 2020 | 8
794 | BLD-2248-D-ERTH¦F1¦2 | LOW SIDE ELECTRICAL WORK | 2376 | SITC of 600X600X6.3Mm GI Plate Earth | 12-12-2019 | 17-03-2022 | EA | 110 | 2020 | 8
795 | BLD-2248-D-ERTH¦F1¦3 | LOW SIDE ELECTRICAL WORK | 2377 | SITC of 14.35Mm Dia3M Long Cu Earth Rod | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
796 | BLD-2248-D-ERTH¦F1¦4¦4'1 | LOW SIDE ELECTRICAL WORK | 2378 | SITC of 50X6Mm Bare Cu Tape | 12-12-2019 | 17-03-2022 | M | 300 | 2020 | 8
797 | BLD-2248-D-ERTH¦F1¦4¦4'2 | LOW SIDE ELECTRICAL WORK | 2379 | SITC of 25X6Mm Bare Cu Tape | 12-12-2019 | 17-03-2022 | M | 200 | 2020 | 8
798 | BLD-2248-D-ERTH¦F1¦4¦4'3 | LOW SIDE ELECTRICAL WORK | 2380 | SITC of 25X3Mm Bare Cu Tape | 12-12-2019 | 17-03-2022 | M | 0 | 2020 | 8
799 | BLD-2248-D-ERTH¦F1¦4¦4'4 | LOW SIDE ELECTRICAL WORK | 2381 | SITC of 50X10Mm Bare GI Tape | 12-12-2019 | 17-03-2022 | M | 200 | 2020 | 8
800 | BLD-2248-D-ERTH¦F1¦4¦4'5 | LOW SIDE ELECTRICAL WORK | 2382 | SITC of 50X6Mm Bare GI Tape | 12-12-2019 | 17-03-2022 | M | 2000 | 2020 | 8
801 | BLD-2248-D-ERTH¦F1¦4¦4'6 | LOW SIDE ELECTRICAL WORK | 2383 | SITC of 25X6Mm Bare GI Tape | 12-12-2019 | 17-03-2022 | M | 4000 | 2020 | 8
802 | BLD-2248-D-ERTH¦F1¦4¦4'7 | LOW SIDE ELECTRICAL WORK | 2384 | SITC of 8Swg GI Wire | 12-12-2019 | 17-03-2022 | M | 12000 | 2020 | 8
803 | BLD-2248-D-ERTH¦F1¦5¦5'1 | LOW SIDE ELECTRICAL WORK | 2385 | SITC of 1C 25Sqmm Green Cu Cable | 12-12-2019 | 17-03-2022 | M | 1500 | 2020 | 8
804 | BLD-2248-D-ERTH¦F1¦6 | LOW SIDE ELECTRICAL WORK | 2386 | S&I of 50X 6Mm Cubusbar With 6 Holes | 12-12-2019 | 17-03-2022 | EA | 42 | 2020 | 8
805 | BLD-2248-D-ERTH¦F1¦7 | LOW SIDE ELECTRICAL WORK | 2387 | SITC of Lockable Earth Terminal Box | 12-12-2019 | 17-03-2022 | EA | 42 | 2020 | 8
806 | BLD-2248-D-ERTH¦F1¦8¦8'1 | LOW SIDE ELECTRICAL WORK | 2388 | SITC of 50Mm Dia GI Hd Road Crossing | 12-12-2019 | 17-03-2022 | M | 20 | 2020 | 8
807 | BLD-2248-D-ERTH¦F1¦8¦8'2 | LOW SIDE ELECTRICAL WORK | 2389 | SITC of 100Mm Dia GI Hd Road Crossing | 12-12-2019 | 17-03-2022 | M | 160 | 2020 | 8
808 | BLD-2248-D-ERTH¦F2¦1 | LOW SIDE ELECTRICAL WORK | 2390 | SITC of 8Mm Dia Cu Bonded Steelconductor | 12-12-2019 | 17-03-2022 | M | 2250 | 2020 | 8
809 | BLD-2248-D-ERTH¦F2¦2 | LOW SIDE ELECTRICAL WORK | 2391 | Interconection of Cbsc Joints | 12-12-2019 | 17-03-2022 | EA | 100 | 2020 | 8
810 | BLD-2248-D-ERTH¦F2¦3 | LOW SIDE ELECTRICAL WORK | 2392 | Interconnections Between Cbsc & Steelbar | 12-12-2019 | 17-03-2022 | EA | 350 | 2020 | 8
811 | BLD-2248-D-ERTH¦F2¦4 | LOW SIDE ELECTRICAL WORK | 2393 | SITC of Earth Pad In Concrete Floor/Wall | 12-12-2019 | 17-03-2022 | EA | 150 | 2020 | 8
812 | BLD-2248-D-ERTH¦F2¦5 | LOW SIDE ELECTRICAL WORK | 2394 | SITC of Earthpad In Conc Floor Lift Loby | 12-12-2019 | 17-03-2022 | EA | 20 | 2020 | 8
813 | BLD-2248-D-ERTH¦F2¦6 | LOW SIDE ELECTRICAL WORK | 2395 | Joints Bw Cbsc & Earth Pad | 12-12-2019 | 17-03-2022 | EA | 170 | 2020 | 8
814 | BLD-2248-D-LPS¦G1¦1 | LOW SIDE ELECTRICAL WORK | 2396 | P&F Lightning Cond 25X300Mm GI Tube | 12-12-2019 | 17-03-2022 | EA | 40 | 2020 | 8
815 | BLD-2248-D-LPS¦G1¦2 | LOW SIDE ELECTRICAL WORK | 2397 | F of Lightning Cond With Base Plate | 12-12-2019 | 17-03-2022 | EA | 40 | 2020 | 8
816 | BLD-2248-D-LPS¦G1¦3 | LOW SIDE ELECTRICAL WORK | 2398 | Jointing of Cu/Gi Tape | 12-12-2019 | 17-03-2022 | EA | 400 | 2020 | 8
817 | BLD-2248-D-LPS¦G1¦4 | LOW SIDE ELECTRICAL WORK | 2399 | P&F GI Tape 20X3Mm On Parapet Horz. Run | 12-12-2019 | 17-03-2022 | M | 900 | 2020 | 8
818 | BLD-2248-D-LPS¦G1¦5 | LOW SIDE ELECTRICAL WORK | 2400 | P&F GI Tape 20X3Mm On Wall Vert. Run | 12-12-2019 | 17-03-2022 | M | 2800 | 2020 | 8
819 | BLD-2248-D-LPS¦G1¦6 | LOW SIDE ELECTRICAL WORK | 2401 | SITC of 8Mm Dia Cbsc For Lightning Protc | 12-12-2019 | 17-03-2022 | M | 0 | 2020 | 8
820 | BLD-2248-D-LPS¦G1¦7 | LOW SIDE ELECTRICAL WORK | 2402 | P&F of Testing Joint 20X3Mm GI Strip | 12-12-2019 | 17-03-2022 | M | 60 | 2020 | 8
821 | BLD-2248-D-LPS¦G1¦8 | LOW SIDE ELECTRICAL WORK | 2403 | P&L GI Tape 32X6Mm In Ground | 12-12-2019 | 17-03-2022 | M | 450 | 2020 | 8
822 | BLD-2248-D-LPS¦G2¦1¦1'1 | LOW SIDE ELECTRICAL WORK | 2404 | SITC of 32X6Mm GI Tape For Looping | 12-12-2019 | 17-03-2022 | M | 40 | 2020 | 8
823 | BLD-2248-D-LPS¦G2¦2 | LOW SIDE ELECTRICAL WORK | 2405 | P&L 14.35Mm Dia 3M Lng | 12-12-2019 | 17-03-2022 | EA | 4 | 2020 | 8
824 | BLD-2248-D-LPS¦G2¦3¦3'1 | LOW SIDE ELECTRICAL WORK | 2406 | SITC of Stormaster 60-79M Adv Lightprot | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
825 | BLD-2248-D-LPS¦G2¦3¦3'2 | LOW SIDE ELECTRICAL WORK | 2407 | SITC of Uper & Lower Term Kit | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
826 | BLD-2248-D-LPS¦G2¦3¦3'3 | LOW SIDE ELECTRICAL WORK | 2408 | SITC of Frp Mast 2M | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
827 | BLD-2248-D-LPS¦G2¦3¦3'4 | LOW SIDE ELECTRICAL WORK | 2409 | SITC of Inline Coupling | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
828 | BLD-2248-D-LPS¦G2¦3¦3'5 | LOW SIDE ELECTRICAL WORK | 2410 | SITC of Guy Wire Kit | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
829 | BLD-2248-D-LPS¦G2¦3¦3'6 | LOW SIDE ELECTRICAL WORK | 2411 | SITC of GI Mast 3M | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
830 | BLD-2248-D-LPS¦G2¦4 | LOW SIDE ELECTRICAL WORK | 2412 | SITC of Hvsc Cu Core Cable 70Sqmm | 12-12-2019 | 17-03-2022 | M | 250 | 2020 | 8
831 | BLD-2248-D-LPS¦G2¦5¦5'1 | LOW SIDE ELECTRICAL WORK | 2413 | SITC of GI Pipe 75Mm Dia Road Crossing | 12-12-2019 | 17-03-2022 | M | 20 | 2020 | 8
832 | BLD-2248-D-LPS¦G2¦6 | LOW SIDE ELECTRICAL WORK | 2414 | P&F of Test Link In 1.6Mm Thck Ms Box | 12-12-2019 | 17-03-2022 | EA | 4 | 2020 | 8
833 | BLD-2248-D-LFT¦H¦1 | LOW SIDE ELECTRICAL WORK | 2415 | SITC of Com Type 1X18Watt Led Tubelight | 12-12-2019 | 17-03-2022 | EA | 160 | 2020 | 8
834 | BLD-2248-D-LFT¦H¦2 | LOW SIDE ELECTRICAL WORK | 2416 | SITC of Com Type 2X18Watt Led Tubelight | 12-12-2019 | 17-03-2022 | EA | 2000 | 2020 | 8
835 | BLD-2248-D-LFT¦H¦3 | LOW SIDE ELECTRICAL WORK | 2417 | SITC of Com Type 1X28Watt Tl-5 Fitting | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
836 | BLD-2248-D-LFT¦H¦4 | LOW SIDE ELECTRICAL WORK | 2418 | SITC of Com Type 2X28Watt Tl-5 Fitting | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
837 | BLD-2248-D-LFT¦H¦5 | LOW SIDE ELECTRICAL WORK | 2419 | SITC of Recessed 1X24Watt Led Downlight | 12-12-2019 | 17-03-2022 | EA | 880 | 2020 | 8
838 | BLD-2248-D-LFT¦H¦6 | LOW SIDE ELECTRICAL WORK | 2420 | SITC of Surface 1X24Watt Led Downlight | 12-12-2019 | 17-03-2022 | EA | 280 | 2020 | 8
839 | BLD-2248-D-LFT¦H¦7 | LOW SIDE ELECTRICAL WORK | 2421 | SITC of Recessed 1X12Watt Led Downlight | 12-12-2019 | 17-03-2022 | EA | 680 | 2020 | 8
840 | BLD-2248-D-LFT¦H¦8 | LOW SIDE ELECTRICAL WORK | 2422 | SITC of 10W Led Bulkhead Light | 12-12-2019 | 17-03-2022 | EA | 90 | 2020 | 8
841 | BLD-2248-D-LFT¦H¦9 | LOW SIDE ELECTRICAL WORK | 2423 | SITC of 48" Sweep Ceiling Fan 5 Star | 12-12-2019 | 17-03-2022 | EA | 1280 | 2020 | 8
842 | BLD-2248-D-LFT¦H¦10 | LOW SIDE ELECTRICAL WORK | 2424 | SITC of 225Mm Sweep Hd Exhaust Fan | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
843 | BLD-2248-D-LFT¦H¦11 | LOW SIDE ELECTRICAL WORK | 2425 | SITC of Led Aviation Light Cluster | 12-12-2019 | 17-03-2022 | EA | 3 | 2020 | 8
844 | BLD-2248-D-LFT¦H¦12 | LOW SIDE ELECTRICAL WORK | 2426 | SITC of Occupancy Sensor | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
845 | BLD-2248-D-LFT¦H¦13 | LOW SIDE ELECTRICAL WORK | 2427 | SITC of Motion Control Sensor | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
846 | BLD-2248-D-UPS¦I¦1 | LOW SIDE ELECTRICAL WORK | 2428 | SITC of 75Kva Ups 3Ph 30Min Backup | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
847 | BLD-2248-D-UPS¦I¦2 | LOW SIDE ELECTRICAL WORK | 2429 | SITC of 2.5Kva Ups 3Ph 15Min Backup | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
848 | BLD-2248-D-UPS¦I¦3 | LOW SIDE ELECTRICAL WORK | 2430 | Sat At Full Load Com With Load Bank | 12-12-2019 | 17-03-2022 | LS | 1 | 2020 | 8
849 | BLD-2248-D-UPS¦I¦4 | LOW SIDE ELECTRICAL WORK | 2431 | S&F of 1000Mm Wide Ruber Mat 1100Volt | 12-12-2019 | 17-03-2022 | M | 15 | 2020 | 8
850 | BLD-2248-D-SRTLT¦J¦1¦1'1 | LOW SIDE ELECTRICAL WORK | 2432 | SITC of Street Light On 8M Pole | 12-12-2019 | 17-03-2022 | EA | 8 | 2020 | 8
851 | BLD-2248-D-SRTLT¦J¦1¦1'2 | LOW SIDE ELECTRICAL WORK | 2433 | SITC of Wall Braket Light | 12-12-2019 | 17-03-2022 | EA | 20 | 2020 | 8
852 | BLD-2248-D-SRTLT¦J¦1¦1'3 | LOW SIDE ELECTRICAL WORK | 2434 | SITC of 12M High Mast | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
853 | BLD-2248-D-SRTLT¦J¦1¦1'4 | LOW SIDE ELECTRICAL WORK | 2435 | SITC of Column Light | 12-12-2019 | 17-03-2022 | EA | 32 | 2020 | 8
854 | BLD-2248-D-SRTLT¦J¦1¦1'5 | LOW SIDE ELECTRICAL WORK | 2436 | SITC of 11W Bollard | 12-12-2019 | 17-03-2022 | EA | 55 | 2020 | 8
855 | BLD-2248-D-SRTLT¦J¦1¦1'6 | LOW SIDE ELECTRICAL WORK | 2437 | SITC of Post Top Luminaire For Gate | 12-12-2019 | 17-03-2022 | EA | 12 | 2020 | 8
856 | BLD-2248-D-SRTLT¦J¦1¦1'7 | LOW SIDE ELECTRICAL WORK | 2438 | SITC of Step Light | 12-12-2019 | 17-03-2022 | EA | 35 | 2020 | 8
857 | BLD-2248-D-SRTLT¦J¦1¦1'8 | LOW SIDE ELECTRICAL WORK | 2439 | SITC of In Ground Luminaires | 12-12-2019 | 17-03-2022 | EA | 10 | 2020 | 8
858 | BLD-2248-D-SRTLT¦J¦1¦1'9 | LOW SIDE ELECTRICAL WORK | 2440 | SITC of Bushlight | 12-12-2019 | 17-03-2022 | EA | 55 | 2020 | 8
859 | BLD-2248-D-SL¦J¦1¦1'10 | LOW SIDE ELECTRICAL WORK | 2441 | SITC of Underwater Lights With Driver | 12-12-2019 | 17-03-2022 | EA | 16 | 2020 | 8
860 | BLD-2248-D-SRTLT¦J¦1A | LOW SIDE ELECTRICAL WORK | 2442 | Sep & Earthing of 8M Long Steel Pole | 12-12-2019 | 17-03-2022 | EA | 8 | 2020 | 8
861 | BLD-2248-D-SRTLT¦J¦2¦2'1 | LOW SIDE ELECTRICAL WORK | 2443 | SITC of 3X2.5Sqmm Cu Ar Cable | 12-12-2019 | 17-03-2022 | M | 550 | 2020 | 8
862 | BLD-2248-D-SRTLT¦J¦2¦2'2 | LOW SIDE ELECTRICAL WORK | 2444 | SITC of 3X4Sqmm Cu Ar Cable | 12-12-2019 | 17-03-2022 | M | 400 | 2020 | 8
863 | BLD-2248-D-SRTLT¦J¦2¦2'3 | LOW SIDE ELECTRICAL WORK | 2445 | SITC of 3X6Sqmm Cu Ar Cable | 12-12-2019 | 17-03-2022 | M | 90 | 2020 | 8
864 | BLD-2248-D-SRTLT¦J¦2¦2'4 | LOW SIDE ELECTRICAL WORK | 2446 | SITC of 2X16Sqmm Cu Ar Cable | 12-12-2019 | 17-03-2022 | M | 400 | 2020 | 8
865 | BLD-2248-D-SRTLT¦J¦2¦2'5 | LOW SIDE ELECTRICAL WORK | 2447 | SITC of 2X10Sqmm Cu Ar Cable | 12-12-2019 | 17-03-2022 | M | 600 | 2020 | 8
866 | BLD-2248-D-SRTLT¦J¦2¦2'6 | LOW SIDE ELECTRICAL WORK | 2448 | SITC of 2X6Sqmm Cu Ar Cable | 12-12-2019 | 17-03-2022 | M | 500 | 2020 | 8
867 | BLD-2248-D-SRTLT¦J¦3¦3'1 | LOW SIDE ELECTRICAL WORK | 2449 | SITC of 3X4Sqmm Wire In 25Mm GI Conduit | 12-12-2019 | 17-03-2022 | M | 300 | 2020 | 8
868 | BLD-2248-D-SRTLT¦J¦3¦3'2 | LOW SIDE ELECTRICAL WORK | 2450 | SITC of 3X2.5Sqmm Wire In 25Mm GI Condui | 12-12-2019 | 17-03-2022 | M | 500 | 2020 | 8
869 | BLD-2248-D-SRTLT¦J¦4 | LOW SIDE ELECTRICAL WORK | 2451 | SITC of 200X150X125Mm Weathr Proof Jb | 12-12-2019 | 17-03-2022 | EA | 150 | 2020 | 8
870 | BLD-2248-D-SRTLT¦J¦5¦5'1 | LOW SIDE ELECTRICAL WORK | 2452 | SITC of Weathr Proof Jb One Way | 12-12-2019 | 17-03-2022 | EA | 40 | 2020 | 8
871 | BLD-2248-D-SRTLT¦J¦5¦5'2 | LOW SIDE ELECTRICAL WORK | 2453 | SITC of Weathr Proof Jb Two Way | 12-12-2019 | 17-03-2022 | EA | 60 | 2020 | 8
872 | BLD-2248-D-SRTLT¦J¦5¦5'3 | LOW SIDE ELECTRICAL WORK | 2454 | SITC of Weathr Proof Jb Three Way | 12-12-2019 | 17-03-2022 | EA | 60 | 2020 | 8
873 | BLD-2248-D-K¦1¦1'1¦1'1'1 | DG SET & ALLIED WORK | 2455 | Supply of 1750Kva Dg Set | 12-12-2019 | 17-03-2022 | SET | 2 | 2020 | 8
874 | BLD-2248-D-K¦1¦1'1¦1'1'2 | DG SET & ALLIED WORK | 2456 | ITC of 1750Kva Dg Set | 12-12-2019 | 17-03-2022 | SET | 2 | 2020 | 8
875 | BLD-2248-D-K¦1¦1'2¦1'2'1 | DG SET & ALLIED WORK | 2457 | Supply of 1010Kva Dg Set | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
876 | BLD-2248-D-K¦1¦1'2¦1'2'2 | DG SET & ALLIED WORK | 2458 | ITC of 1010Kva Dg Set | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
877 | BLD-2248-D-K¦2¦2'1¦2'1'1 | DG SET & ALLIED WORK | 2459 | Supply of B Cls Ms Pipe With Insulation | 12-12-2019 | 17-03-2022 | M | 378 | 2020 | 8
878 | BLD-2248-D-K¦2¦2'1¦2'1'2 | DG SET & ALLIED WORK | 2460 | ITC of Exhaust Piping | 12-12-2019 | 17-03-2022 | M | 378 | 2020 | 8
879 | BLD-2248-D-DG¦K¦3¦3'1 | DG SET & ALLIED WORK | 2461 | SITC of 600X600X6.3Mm GI Plate Earth | 12-12-2019 | 17-03-2022 | SET | 6 | 2020 | 8
880 | BLD-2248-D-DG¦K¦3¦3'2 | DG SET & ALLIED WORK | 2462 | SITC of 600X600X3.15Mm Cu Plate Earth | 12-12-2019 | 17-03-2022 | SET | 6 | 2020 | 8
881 | BLD-2248-D-K¦3¦3'3¦3'3'1 | DG SET & ALLIED WORK | 2463 | P&L of 50 X 6 Mm GI Strip | 12-12-2019 | 17-03-2022 | M | 300 | 2020 | 8
882 | BLD-2248-D-K¦3¦3'3¦3'3'2 | DG SET & ALLIED WORK | 2464 | P&L 8 Swg GI Wire | 12-12-2019 | 17-03-2022 | M | 190 | 2020 | 8
883 | BLD-2248-D-K¦3¦3'4¦3'4'1 | DG SET & ALLIED WORK | 2465 | P&L 50X6 Mm Cu Strip | 12-12-2019 | 17-03-2022 | M | 300 | 2020 | 8
884 | BLD-2248-D-K¦3¦3'4¦3'4'2 | DG SET & ALLIED WORK | 2466 | P&L 25X6 Mm Cu Strip | 12-12-2019 | 17-03-2022 | M | 0 | 2020 | 8
885 | BLD-2248-D-K¦4¦4'1¦4'1'1 | DG SET & ALLIED WORK | 2467 | SITC of 50Mm Dia GI Road Crossing | 12-12-2019 | 17-03-2022 | M | 50 | 2020 | 8
886 | BLD-2248-D-K¦4¦4'1¦4'1'2 | DG SET & ALLIED WORK | 2468 | SITC of 100Mm Dia GI Road Crossing | 12-12-2019 | 17-03-2022 | M | 0 | 2020 | 8
887 | BLD-2248-D-DG¦K¦4¦4'2 | DG SET & ALLIED WORK | 2469 | S&F of Shock Treatment Chart | 12-12-2019 | 17-03-2022 | SET | 2 | 2020 | 8
888 | BLD-2248-D-DG¦K¦4¦4'3 | DG SET & ALLIED WORK | 2470 | S&F of Fire Buckets | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
889 | BLD-2248-D-DG¦K¦4¦4'4 | DG SET & ALLIED WORK | 2471 | P&F of Danger Board | 12-12-2019 | 17-03-2022 | SET | 3 | 2020 | 8
890 | BLD-2248-D-DG¦K¦4¦4'5 | DG SET & ALLIED WORK | 2472 | S&F of 1.8M Len 0.9M Wide Rubber Mat | 12-12-2019 | 17-03-2022 | SET | 0 | 2020 | 8
891 | BLD-2248-D-DG¦K¦4¦4'6 | DG SET & ALLIED WORK | 2473 | P&F Fire Extng Co2 5Lts Capacity | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
892 | BLD-2248-D-DG¦K¦4¦4'7 | DG SET & ALLIED WORK | 2474 | S&I of Hand Pump For Diesel Transfer | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
893 | BLD-2248-D-DG¦K¦4¦4'8 | DG SET & ALLIED WORK | 2475 | P&W of Control Wires Bw Gen & Panel | 12-12-2019 | 17-03-2022 | SET | 3 | 2020 | 8
894 | BLD-2248-D-DG¦K¦4¦4'9 | DG SET & ALLIED WORK | 2476 | P&F Twin Dome Aviation Lamp | 12-12-2019 | 17-03-2022 | SET | 3 | 2020 | 8
895 | BLD-2248-D-DG¦K¦4¦4'10 | DG SET & ALLIED WORK | 2477 | Obtaining Cpcb & Wbspcb Clearance | 12-12-2019 | 17-03-2022 | LS | 1 | 2020 | 8
896 | BLD-2248-D-DG¦K¦5¦5'1 | DG SET & ALLIED WORK | 2478 | SITC of Temporary Load Bank 10% Overload | 12-12-2019 | 17-03-2022 | LOT | 1 | 2020 | 8
897 | BLD-2248-D-L¦1¦1'1¦1'1'1 | ELEVATOR | 2479 | SITC of 24 Pax Elevator | 12-12-2019 | 17-03-2022 | EA | 8 | 2020 | 8
898 | BLD-2248-D-L¦1¦1'1¦1'1'2 | ELEVATOR | 2480 | SITC of 13 Pax Elevator | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
899 | BLD-2248-D-L¦1¦1'1¦1'1'3 | ELEVATOR | 2481 | SITC of 20 Pax Elevator | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
900 | BLD-2248-D-LIFT¦L¦1¦1'2 | ELEVATOR | 2482 | Port Charges & Customs Duty Elevator | 12-12-2019 | 17-03-2022 | EA | 11 | 2020 | 8
901 | BLD-2248-D-LIFT¦L¦1¦1'3 | ELEVATOR | 2483 | Unloading & Shifting Charges | 12-12-2019 | 17-03-2022 | EA | 11 | 2020 | 8
902 | BLD-2248-D-CHLR¦1¦1'1 | CHILLERS | 2484 | SITC of 350Tr Water Cooled Chillers | 12-12-2019 | 17-03-2022 | EA | 3 | 2020 | 8
903 | BLD-2248-D-CHLR¦1¦1'2 | CHILLERS | 2485 | Port & Handling Charges For Chillers | 12-12-2019 | 17-03-2022 | EA | 3 | 2020 | 8
904 | BLD-2248-D-CHLR¦1¦1'3 | CHILLERS | 2486 | T&C of Above Machines | 12-12-2019 | 17-03-2022 | EA | 3 | 2020 | 8
905 | BLD-2248-D-A¦1¦1'1¦1'1'1 | HVAC SYSTEM OF OFFICE BLOCK | 2487 | SITC of Vav 200-500Cfm | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
906 | BLD-2248-D-A¦1¦1'1¦1'1'2 | HVAC SYSTEM OF OFFICE BLOCK | 2488 | SITC of Vav 501-600Cfm | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
907 | BLD-2248-D-A¦1¦1'1¦1'1'3 | HVAC SYSTEM OF OFFICE BLOCK | 2489 | SITC of Vav 1000-1500Cfm | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
908 | BLD-2248-D-A¦1¦1'1¦1'1'4 | HVAC SYSTEM OF OFFICE BLOCK | 2490 | SITC of Vav 2001-2500Cfm | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
909 | BLD-2248-D-A¦1¦1'1¦1'1'5 | HVAC SYSTEM OF OFFICE BLOCK | 2491 | SITC of Vav 2501-3000Cfm | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
910 | BLD-2248-D-A¦1¦1'1¦1'1'6 | HVAC SYSTEM OF OFFICE BLOCK | 2492 | SITC of Vav 30001-4000Cfm | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
911 | BLD-2248-D-A¦1¦1'1¦1'1'7 | HVAC SYSTEM OF OFFICE BLOCK | 2493 | SITC of Vav 4001-5000Cfm | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
912 | BLD-2248-D-A¦1¦1'1¦1'1'8 | HVAC SYSTEM OF OFFICE BLOCK | 2494 | SITC of Vav 5001-6000Cfm | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
913 | BLD-2248-D-A¦1¦1'1¦1'1'9 | HVAC SYSTEM OF OFFICE BLOCK | 2495 | SITC of Vav 6001-7000Cfm | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
914 | BLD-2248-D-A¦1¦1'2 | HVAC SYSTEM OF OFFICE BLOCK | 2496 | Port & Handling Charges For Vav | 12-12-2019 | 17-03-2022 | EA | 19 | 2020 | 8
915 | BLD-2248-D-IMEQP¦A¦1¦1'3 | HVAC SYSTEM OF OFFICE BLOCK | 2497 | Customs Duty & Countervailing For Vav | 12-12-2019 | 17-03-2022 | EA | 19 | 2020 | 8
916 | BLD-2248-D-IMEQP¦A¦1¦1'4 | HVAC SYSTEM OF OFFICE BLOCK | 2498 | Unloading & Shifting Charges For Vav | 12-12-2019 | 17-03-2022 | EA | 19 | 2020 | 8
917 | BLD-2248-D-A¦2¦2'1¦2'1'1 | HVAC SYSTEM OF OFFICE BLOCK | 2499 | SITC of Electrnc Pr Indepndt Vlv 3.6Gpm | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
918 | BLD-2248-D-A¦2¦2'1¦2'1'2 | HVAC SYSTEM OF OFFICE BLOCK | 2500 | SITC of Electrnc Pr Indepndt Vlv 19.2Gpm | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
919 | BLD-2248-D-A¦2¦2'1¦2'1'3 | HVAC SYSTEM OF OFFICE BLOCK | 2501 | SITC of Electrnc Pr Indepndt Vlv 48Gpm | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
920 | BLD-2248-D-A¦2¦2'1¦2'1'4 | HVAC SYSTEM OF OFFICE BLOCK | 2502 | SITC of Electrnc Pr Indepndt Vlv 52.8Gpm | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
921 | BLD-2248-D-A¦2¦2'1¦2'1'5 | HVAC SYSTEM OF OFFICE BLOCK | 2503 | SITC of Electrnc Pr Indepndt Vlv 55.3Gpm | 12-12-2019 | 17-03-2022 | EA | 3 | 2020 | 8
922 | BLD-2248-D-A¦2¦2'1¦2'1'6 | HVAC SYSTEM OF OFFICE BLOCK | 2504 | SITC of Electrnc Pr Indepndt Vlv 144Gpm | 12-12-2019 | 17-03-2022 | EA | 14 | 2020 | 8
923 | BLD-2248-D-A¦2¦2'1¦2'1'7 | HVAC SYSTEM OF OFFICE BLOCK | 2505 | SITC of Electrnc Pr Indepndt Vlv163.2Gpm | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
924 | BLD-2248-D-A¦2¦2'2 | HVAC SYSTEM OF OFFICE BLOCK | 2506 | Port Charges For Valve | 12-12-2019 | 17-03-2022 | EA | 24 | 2020 | 8
925 | BLD-2248-D-A¦2¦2'3 | HVAC SYSTEM OF OFFICE BLOCK | 2507 | Customs Duty & Countervailing For Valve | 12-12-2019 | 17-03-2022 | EA | 24 | 2020 | 8
926 | BLD-2248-D-A¦2¦2'4 | HVAC SYSTEM OF OFFICE BLOCK | 2508 | ITC of Electrnc Pr Indepndt Vlv | 12-12-2019 | 17-03-2022 | EA | 24 | 2020 | 8
927 | BLD-2248-D-A¦3¦3'1 | HVAC SYSTEM OF OFFICE BLOCK | 2509 | Supply of Thermostats Cif | 12-12-2019 | 17-03-2022 | EA | 24 | 2020 | 8
928 | BLD-2248-D-A¦3¦3'2 | HVAC SYSTEM OF OFFICE BLOCK | 2510 | Port Charges For Thermostats | 12-12-2019 | 17-03-2022 | EA | 24 | 2020 | 8
929 | BLD-2248-D-A¦3¦3'3 | HVAC SYSTEM OF OFFICE BLOCK | 2511 | Customs Duty For Thermostat | 12-12-2019 | 17-03-2022 | EA | 24 | 2020 | 8
930 | BLD-2248-D-A¦3¦3'4 | HVAC SYSTEM OF OFFICE BLOCK | 2512 | Unloading & Shifting Charges For Ts | 12-12-2019 | 17-03-2022 | EA | 24 | 2020 | 8
931 | BLD-2248-D-A¦4¦4'1¦4'1'1 | HVAC SYSTEM OF OFFICE BLOCK | 2513 | Supply of Vfd For Ahu 2.2Kw | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
932 | BLD-2248-D-A¦4¦4'1¦4'1'2 | HVAC SYSTEM OF OFFICE BLOCK | 2514 | Supply of Vfd For Ahu 3.7Kw | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
933 | BLD-2248-D-A¦4¦4'1¦4'1'3 | HVAC SYSTEM OF OFFICE BLOCK | 2515 | Supply of Vfd For Ahu 5.5Kw | 12-12-2019 | 17-03-2022 | EA | 4 | 2020 | 8
934 | BLD-2248-D-A¦4¦4'1¦4'1'4 | HVAC SYSTEM OF OFFICE BLOCK | 2516 | Supply of Vfd For Ahu 15Kw | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
935 | BLD-2248-D-A¦4¦4'1¦4'1'5 | HVAC SYSTEM OF OFFICE BLOCK | 2517 | Supply of Vfd For Ahu 22Kw | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
936 | BLD-2248-D-A¦4¦4'1¦4'1'6 | HVAC SYSTEM OF OFFICE BLOCK | 2518 | Supply of Vfd For Ahu 18.5Kw | 12-12-2019 | 17-03-2022 | EA | 3 | 2020 | 8
937 | BLD-2248-D-IMEQP¦A¦4¦4'2 | HVAC SYSTEM OF OFFICE BLOCK | 2519 | Port Handling Charges For Vfd | 12-12-2019 | 17-03-2022 | EA | 28 | 2020 | 8
938 | BLD-2248-D-IMEQP¦A¦4¦4'3 | HVAC SYSTEM OF OFFICE BLOCK | 2520 | Customs Duty & Contervailing For Vfd | 12-12-2019 | 17-03-2022 | EA | 28 | 2020 | 8
939 | BLD-2248-D-IMEQP¦A¦4¦4'4 | HVAC SYSTEM OF OFFICE BLOCK | 2521 | Unloading Shifting Handling Charges Vfd | 12-12-2019 | 17-03-2022 | EA | 28 | 2020 | 8
940 | BLD-2248-D-IMEQUIP¦A¦5 | HVAC SYSTEM OF OFFICE BLOCK | 2522 | SITC of Cooling Tower For 350 Tr Chiller | 12-12-2019 | 17-03-2022 | EA | 3 | 2020 | 8
941 | BLD-2248-D-INEQP¦B¦1¦1'1 | HVAC SYSTEM OF OFFICE BLOCK | 2523 | SITC of Primary Chw Pump 15Hp | 12-12-2019 | 17-03-2022 | EA | 4 | 2020 | 8
942 | BLD-2248-D-INEQP¦B¦2¦2'1 | HVAC SYSTEM OF OFFICE BLOCK | 2524 | SITC of Condensor Pump 25 Hp | 12-12-2019 | 17-03-2022 | EA | 4 | 2020 | 8
943 | BLD-2248-D-INEQP¦B¦3¦3'1 | HVAC SYSTEM OF OFFICE BLOCK | 2525 | SITC of Pr Chw Expansion Tank With Pump | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
944 | BLD-2248-D-INEQP¦B¦4¦4'1 | HVAC SYSTEM OF OFFICE BLOCK | 2526 | SITC of Chw Secondary Pump 50Hp | 12-12-2019 | 17-03-2022 | EA | 3 | 2020 | 8
945 | BLD-2248-D-INEQP¦B¦5¦5'1 | HVAC SYSTEM OF OFFICE BLOCK | 2527 | SITC of Sec Pump Controller & Sensor | 12-12-2019 | 17-03-2022 | EA | 3 | 2020 | 8
946 | BLD-2248-D-INEQP¦B¦5¦5'2 | HVAC SYSTEM OF OFFICE BLOCK | 2528 | SITC of 50Hp Variable Speed Drive | 12-12-2019 | 17-03-2022 | EA | 3 | 2020 | 8
947 | BLD-2248-D-INEQP¦B¦6¦A | HVAC SYSTEM OF OFFICE BLOCK | 2529 | SITC of 3200 Cfm 8Tr Ahu Brch Off Gf | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
948 | BLD-2248-D-INEQP¦B¦6¦B | HVAC SYSTEM OF OFFICE BLOCK | 2530 | SITC of 700 Cfm 1.5Tr Ahu Cour Rm Gf | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
949 | BLD-2248-D-INEQP¦B¦6¦C | HVAC SYSTEM OF OFFICE BLOCK | 2531 | SITC of 10250 Cfm 22Tr Ahuentr Lby Gf | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
950 | BLD-2248-D-INEQP¦B¦6¦D | HVAC SYSTEM OF OFFICE BLOCK | 2532 | SITC of 3200 Cfm 8Tr Ahu Cust Care Mf | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
951 | BLD-2248-D-INEQP¦B¦6¦E | HVAC SYSTEM OF OFFICE BLOCK | 2533 | SITC of 7000 Cfm 20Tr Ahu Hstl Dng L7F | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
952 | BLD-2248-D-INEQP¦B¦6¦F | HVAC SYSTEM OF OFFICE BLOCK | 2534 | SITC of 8200 Cfm 23Tr Ahu Hstl Dng R7F | 12-12-2019 | 17-03-2022 | EA | 3 | 2020 | 8
953 | BLD-2248-D-INEQP¦B¦6¦G | HVAC SYSTEM OF OFFICE BLOCK | 2535 | SITC of 28450 Cfm 60Tr Ahu Off Ar 9-22Fl | 12-12-2019 | 17-03-2022 | EA | 14 | 2020 | 8
954 | BLD-2248-D-INEQP¦B¦6¦H | HVAC SYSTEM OF OFFICE BLOCK | 2536 | SITC of 28950 Cfm 68Tr Ahu Off Ar 23Fl | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
955 | BLD-2248-D-INEQP¦B¦7¦7'1 | HVAC SYSTEM OF OFFICE BLOCK | 2537 | SITC of Hru 55Tr 26650Cfm At Terrace | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
956 | BLD-2248-D-INEQP¦B¦8¦8'1 | HVAC SYSTEM OF OFFICE BLOCK | 2538 | SITC of 7.5Tr Pac Unit | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
957 | BLD-2248-D-INEQP¦B¦8¦8'2 | HVAC SYSTEM OF OFFICE BLOCK | 2539 | SITC of 10Tr Pac Unit | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
958 | BLD-2248-D-INEQP¦B¦8¦8'3 | HVAC SYSTEM OF OFFICE BLOCK | 2540 | SITC of 15Tr Pac Unit | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
959 | BLD-2248-D-INEQP¦B¦9¦9'1 | HVAC SYSTEM OF OFFICE BLOCK | 2541 | SITC of 1Tr Split Ac | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
960 | BLD-2248-D-INEQP¦B¦9¦9'2 | HVAC SYSTEM OF OFFICE BLOCK | 2542 | SITC of 1.5Tr Split Ac | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
961 | BLD-2248-D-INEQP¦B¦9¦9'3 | HVAC SYSTEM OF OFFICE BLOCK | 2543 | SITC of 2Tr Split Ac | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
962 | BLD-2248-D-INEQP¦B¦10¦A | HVAC SYSTEM OF OFFICE BLOCK | 2544 | SITC of Lift Pr Fan 32000Cfm | 12-12-2019 | 17-03-2022 | EA | 4 | 2020 | 8
963 | BLD-2248-D-INEQP¦B¦10¦B | HVAC SYSTEM OF OFFICE BLOCK | 2545 | SITC of Lift & Lobby Pr Fan 38300Cfm | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
964 | BLD-2248-D-INEQP¦B¦10¦C | HVAC SYSTEM OF OFFICE BLOCK | 2546 | SITC of Lift & Makeup Air Prfan 58300Cfm | 12-12-2019 | 17-03-2022 | EA | 3 | 2020 | 8
965 | BLD-2248-D-INEQP¦B¦10¦D | HVAC SYSTEM OF OFFICE BLOCK | 2547 | SITC of Lift & Lobby Pr Fan 35800Cfm | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
966 | BLD-2248-D-INEQP¦B¦10¦E | HVAC SYSTEM OF OFFICE BLOCK | 2548 | SITC of Staircase Pr Fan 12000Cfm | 12-12-2019 | 17-03-2022 | EA | 4 | 2020 | 8
967 | BLD-2248-D-INEQP¦B¦10¦F | HVAC SYSTEM OF OFFICE BLOCK | 2549 | SITC of Off Smoke Extrctn Fan 23750Cfm | 12-12-2019 | 17-03-2022 | EA | 4 | 2020 | 8
968 | BLD-2248-D-INEQP¦B¦10¦G | HVAC SYSTEM OF OFFICE BLOCK | 2550 | SITC of Prkng Smoke Extrctn Fan 30500Cfm | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
969 | BLD-2248-D-INEQP¦B¦10¦H | HVAC SYSTEM OF OFFICE BLOCK | 2551 | SITC of Kitchn Frsh Air Fan 8000Cfm | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
970 | BLD-2248-D-INEB¦11¦11'1 | HVAC SYSTEM OF OFFICE BLOCK | 2552 | SITC of Proplr Fan 550Mm Dia 2900Cfm | 12-12-2019 | 17-03-2022 | EA | 12 | 2020 | 8
971 | BLD-2248-D-INE¦B¦12¦12'1 | HVAC SYSTEM OF OFFICE BLOCK | 2553 | SITC of Inline Fan 200Cfm For Toilet | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
972 | BLD-2248-D-INE¦B¦12¦12'2 | HVAC SYSTEM OF OFFICE BLOCK | 2554 | SITC of Inline Fan 300Cfm For Toilet | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
973 | BLD-2248-D-INE¦B¦12¦12'3 | HVAC SYSTEM OF OFFICE BLOCK | 2555 | SITC of Inline Fan 600Cfm For Toilet | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
974 | BLD-2248-D-INE¦B¦13¦13'1 | HVAC SYSTEM OF OFFICE BLOCK | 2556 | SITC of Kitchn Air Scrubber 7500Cfm | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
975 | BLD-2248-D-INE¦B¦14¦14'1 | HVAC SYSTEM OF OFFICE BLOCK | 2557 | SITC of Hvac Plant Mcc1 | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
976 | BLD-2248-D-INE¦B¦15¦15'1 | HVAC SYSTEM OF OFFICE BLOCK | 2558 | SITC of Hvac Plant Mcc2 | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
977 | BLD-2248-D-INE¦B¦16¦16'1 | HVAC SYSTEM OF OFFICE BLOCK | 2559 | SITC of Ahu Vfd Starter Panel 15Kw | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
978 | BLD-2248-D-INE¦B¦16¦16'2 | HVAC SYSTEM OF OFFICE BLOCK | 2560 | SITC of Ahu Vfd Starter Panel 5.5Kw | 12-12-2019 | 17-03-2022 | EA | 4 | 2020 | 8
979 | BLD-2248-D-INE¦B¦16¦16'3 | HVAC SYSTEM OF OFFICE BLOCK | 2561 | SITC of Ahu Vfd Starter Panel 3.7Kw | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
980 | BLD-2248-D-INE¦B¦16¦16'4 | HVAC SYSTEM OF OFFICE BLOCK | 2562 | SITC of Ahu Vfd Starter Panel 2.2Kw | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
981 | BLD-2248-D-INE¦B¦17¦17'1 | HVAC SYSTEM OF OFFICE BLOCK | 2563 | SITC of 0.2 Kw Dol Starter For Exhust | 12-12-2019 | 17-03-2022 | EA | 4 | 2020 | 8
982 | BLD-2248-D-INE¦B¦17¦17'2 | HVAC SYSTEM OF OFFICE BLOCK | 2564 | SITC of 0.5 Kw Dol Starter For Ventltn | 12-12-2019 | 17-03-2022 | EA | 12 | 2020 | 8
983 | BLD-2248-D-INE¦B¦17¦17'3 | HVAC SYSTEM OF OFFICE BLOCK | 2565 | SITC of 7.5 Kw Star Delta Starter | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
984 | BLD-2248-D-INE¦B¦17¦17'4 | HVAC SYSTEM OF OFFICE BLOCK | 2566 | SITC of 11Kw Star Delta Starter | 12-12-2019 | 17-03-2022 | EA | 4 | 2020 | 8
985 | BLD-2248-D-INE¦B¦17¦17'5 | HVAC SYSTEM OF OFFICE BLOCK | 2567 | SITC of 18.5Kw Star Delta Starter | 12-12-2019 | 17-03-2022 | EA | 4 | 2020 | 8
986 | BLD-2248-D-INE¦B¦17¦17'6 | HVAC SYSTEM OF OFFICE BLOCK | 2568 | SITC of 18.5Kw Star Delta Starter | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
987 | BLD-2248-D-INE¦B¦17¦17'7 | HVAC SYSTEM OF OFFICE BLOCK | 2569 | SITC of 18.5Kw Star Delta Starter | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
988 | BLD-2248-D-INE¦B¦17¦17'8 | HVAC SYSTEM OF OFFICE BLOCK | 2570 | SITC of 45Kw Star Delta Starter | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
989 | BLD-2248-D-INE¦B¦17¦17'9 | HVAC SYSTEM OF OFFICE BLOCK | 2571 | SITC of 18.5Kw Star Delta Starter | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
990 | BLD-2248-D-IE¦B¦17¦17'10 | HVAC SYSTEM OF OFFICE BLOCK | 2572 | SITC of 2.2Kw Star Delta Starter | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
991 | BLD-2248-D-INE¦B¦18¦18'1 | HVAC SYSTEM OF OFFICE BLOCK | 2573 | SITC For Mcc of Fresh Air (Doas)Unit | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
992 | BLD-2248-D-PIPE¦C¦1¦1'1 | HVAC SYSTEM OF OFFICE BLOCK | 2574 | SITC of 600Mm Dia Ms Pipes For Chw Line | 12-12-2019 | 17-03-2022 | M | 0 | 2020 | 8
993 | BLD-2248-D-PIPE¦C¦1¦1'2 | HVAC SYSTEM OF OFFICE BLOCK | 2575 | SITC of 500Mm Dia Ms Pipes For Chw Line | 12-12-2019 | 17-03-2022 | M | 0 | 2020 | 8
994 | BLD-2248-D-PIPE¦C¦1¦1'3 | HVAC SYSTEM OF OFFICE BLOCK | 2576 | SITC of 450Mm Dia Ms Pipes For Chw Line | 12-12-2019 | 17-03-2022 | M | 0 | 2020 | 8
995 | BLD-2248-D-PIPE¦C¦1¦1'4 | HVAC SYSTEM OF OFFICE BLOCK | 2577 | SITC of 400Mm Dia Ms Pipes For Chw Line | 12-12-2019 | 17-03-2022 | M | 0 | 2020 | 8
996 | BLD-2248-D-PIPE¦C¦1¦1'5 | HVAC SYSTEM OF OFFICE BLOCK | 2578 | SITC of 350Mm Dia Ms Pipes For Chw Line | 12-12-2019 | 17-03-2022 | M | 175 | 2020 | 8
997 | BLD-2248-D-PIPE¦C¦1¦1'6 | HVAC SYSTEM OF OFFICE BLOCK | 2579 | SITC of 300Mm Dia Ms Pipes For Chw Line | 12-12-2019 | 17-03-2022 | M | 395 | 2020 | 8
998 | BLD-2248-D-PIPE¦C¦1¦1'7 | HVAC SYSTEM OF OFFICE BLOCK | 2580 | SITC of 250Mm Dia Ms Pipes For Chw Line | 12-12-2019 | 17-03-2022 | M | 112 | 2020 | 8
999 | BLD-2248-D-PIPE¦C¦2¦2'1 | HVAC SYSTEM OF OFFICE BLOCK | 2581 | SITC of C Cls Ms Pipe 200Mm Dia For Chw | 12-12-2019 | 17-03-2022 | M | 120 | 2020 | 8
1000 | BLD-2248-D-PIPE¦C¦2¦2'2 | HVAC SYSTEM OF OFFICE BLOCK | 2582 | SITC of C Cls Ms Pipe 150Mm Dia For Chw | 12-12-2019 | 17-03-2022 | M | 28 | 2020 | 8
1001 | BLD-2248-D-PIPE¦C¦2¦2'3 | HVAC SYSTEM OF OFFICE BLOCK | 2583 | SITC of C Cls Ms Pipe 125Mm Dia For Chw | 12-12-2019 | 17-03-2022 | M | 15 | 2020 | 8
1002 | BLD-2248-D-PIPE¦C¦2¦2'4 | HVAC SYSTEM OF OFFICE BLOCK | 2584 | SITC of C Cls Ms Pipe 100Mm Dia For Chw | 12-12-2019 | 17-03-2022 | M | 370 | 2020 | 8
1003 | BLD-2248-D-PIPE¦C¦2¦2'5 | HVAC SYSTEM OF OFFICE BLOCK | 2585 | SITC of C Cls Ms Pipe 80Mm Dia For Chw | 12-12-2019 | 17-03-2022 | M | 280 | 2020 | 8
1004 | BLD-2248-D-PIPE¦C¦2¦2'6 | HVAC SYSTEM OF OFFICE BLOCK | 2586 | SITC of C Cls Ms Pipe 65Mm Dia For Chw | 12-12-2019 | 17-03-2022 | M | 210 | 2020 | 8
1005 | BLD-2248-D-PIPE¦C¦2¦2'7 | HVAC SYSTEM OF OFFICE BLOCK | 2587 | SITC of C Cls Ms Pipe 50Mm Dia For Chw | 12-12-2019 | 17-03-2022 | M | 250 | 2020 | 8
1006 | BLD-2248-D-PIPE¦C¦2¦2'8 | HVAC SYSTEM OF OFFICE BLOCK | 2588 | SITC of C Cls Ms Pipe 40Mm Dia For Chw | 12-12-2019 | 17-03-2022 | M | 75 | 2020 | 8
1007 | BLD-2248-D-PIPE¦C¦2¦2'9 | HVAC SYSTEM OF OFFICE BLOCK | 2589 | SITC of C Cls Ms Pipe 32Mm Dia For Chw | 12-12-2019 | 17-03-2022 | M | 10 | 2020 | 8
1008 | BLD-2248-D-PIPE¦C¦2¦2'10 | HVAC SYSTEM OF OFFICE BLOCK | 2590 | SITC of C Cls Ms Pipe 25Mm Dia For Chw | 12-12-2019 | 17-03-2022 | M | 0 | 2020 | 8
1009 | BLD-2248-D-PIPE¦C¦2¦2'11 | HVAC SYSTEM OF OFFICE BLOCK | 2591 | SITC of C Cls Ms Pipe 20Mm Dia For Chw | 12-12-2019 | 17-03-2022 | M | 0 | 2020 | 8
1010 | BLD-2248-D-PIPE¦C¦3¦3'1 | HVAC SYSTEM OF OFFICE BLOCK | 2592 | SITC of Preinslt Butterfly Vlv 400Mm Dia | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
1011 | BLD-2248-D-PIPE¦C¦3¦3'2 | HVAC SYSTEM OF OFFICE BLOCK | 2593 | SITC of Noninslt Butterfly Vlv 350Mm Dia | 12-12-2019 | 17-03-2022 | EA | 3 | 2020 | 8
1012 | BLD-2248-D-PIPE¦C¦3¦3'3 | HVAC SYSTEM OF OFFICE BLOCK | 2594 | SITC of Preinslt Butterfly Vlv 300Mm Dia | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
1013 | BLD-2248-D-PIPE¦C¦3¦3'4 | HVAC SYSTEM OF OFFICE BLOCK | 2595 | SITC of Noninslt Butterfly Vlv 250Mm Dia | 12-12-2019 | 17-03-2022 | EA | 8 | 2020 | 8
1014 | BLD-2248-D-PIPE¦C¦3¦3'5 | HVAC SYSTEM OF OFFICE BLOCK | 2596 | SITC of Preinslt Butterfly Vlv 200Mm Dia | 12-12-2019 | 17-03-2022 | EA | 14 | 2020 | 8
1015 | BLD-2248-D-PIPE¦C¦3¦3'6 | HVAC SYSTEM OF OFFICE BLOCK | 2597 | SITC of Preinslt Butterfly Vlv 200Mm Dia | 12-12-2019 | 17-03-2022 | EA | 4 | 2020 | 8
1016 | BLD-2248-D-PIPE¦C¦3¦3'7 | HVAC SYSTEM OF OFFICE BLOCK | 2598 | SITC of Preinslt Butterfly Vlv 150Mm Dia | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
1017 | BLD-2248-D-PIPE¦C¦3¦3'8 | HVAC SYSTEM OF OFFICE BLOCK | 2599 | SITC of Preinslt Butterfly Vlv 125Mm Dia | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
1018 | BLD-2248-D-PIPE¦C¦3¦3'9 | HVAC SYSTEM OF OFFICE BLOCK | 2600 | SITC of Preinslt Butterfly Vlv 100Mm Dia | 12-12-2019 | 17-03-2022 | EA | 32 | 2020 | 8
1019 | BLD-2248-D-PIPE¦C¦3¦3'10 | HVAC SYSTEM OF OFFICE BLOCK | 2601 | SITC of Preinslt Butterfly Vlv 80Mm Dia | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
1020 | BLD-2248-D-PIPE¦C¦3¦3'11 | HVAC SYSTEM OF OFFICE BLOCK | 2602 | SITC of Preinslt Butterfly Vlv 65Mm Dia | 12-12-2019 | 17-03-2022 | EA | 8 | 2020 | 8
1021 | BLD-2248-D-PIPE¦C¦3¦3'12 | HVAC SYSTEM OF OFFICE BLOCK | 2603 | SITC of Preinslt Butterfly Vlv 50Mm Dia | 12-12-2019 | 17-03-2022 | EA | 6 | 2020 | 8
1022 | BLD-2248-D-PIPE¦C¦3¦3'13 | HVAC SYSTEM OF OFFICE BLOCK | 2604 | SITC of Preinslt Butterfly Vlv 40Mm Dia | 12-12-2019 | 17-03-2022 | EA | 6 | 2020 | 8
1023 | BLD-2248-D-PIPE¦C¦4¦4'1 | HVAC SYSTEM OF OFFICE BLOCK | 2605 | SITC of Preinslt Balancing Vlv 300Mm Dia | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
1024 | BLD-2248-D-PIPE¦C¦4¦4'2 | HVAC SYSTEM OF OFFICE BLOCK | 2606 | SITC of Noninslt Balancing Vlv 250Mm Dia | 12-12-2019 | 17-03-2022 | EA | 7 | 2020 | 8
1025 | BLD-2248-D-PIPE¦C¦4¦4'3 | HVAC SYSTEM OF OFFICE BLOCK | 2607 | SITC of Preinslt Balancing Vlv 200Mm Dia | 12-12-2019 | 17-03-2022 | EA | 4 | 2020 | 8
1026 | BLD-2248-D-PIPE¦C¦5¦5'1 | HVAC SYSTEM OF OFFICE BLOCK | 2608 | SITC of Preinsltmtr Btrfly Vlv 300Mm Dia | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
1027 | BLD-2248-D-PIPE¦C¦5¦5'2 | HVAC SYSTEM OF OFFICE BLOCK | 2609 | SITC of Preinsltmtr Btrfly Vlv 250Mm Dia | 12-12-2019 | 17-03-2022 | EA | 7 | 2020 | 8
1028 | BLD-2248-D-PIPE¦C¦5¦5'3 | HVAC SYSTEM OF OFFICE BLOCK | 2610 | SITC of Preinsltmtr Btrfly Vlv 200Mm Dia | 12-12-2019 | 17-03-2022 | EA | 4 | 2020 | 8
1029 | BLD-2248-D-PIPE¦C¦5¦5'4 | HVAC SYSTEM OF OFFICE BLOCK | 2611 | SITC of Preinsltmtr Btrfly Vlv 150Mm Dia | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
1030 | BLD-2248-D-PIPE¦C¦6¦6'1 | HVAC SYSTEM OF OFFICE BLOCK | 2612 | SITC of Ball Valve With Insl 40Mm Dia | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
1031 | BLD-2248-D-PIPE¦C¦6¦6'2 | HVAC SYSTEM OF OFFICE BLOCK | 2613 | SITC of Ball Valve With Insl 32Mm Dia | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
1032 | BLD-2248-D-PIPE¦C¦6¦6'3 | HVAC SYSTEM OF OFFICE BLOCK | 2614 | SITC of Ball Valve With Insl 25Mm Dia | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
1033 | BLD-2248-D-PIPE¦C¦7¦7'1 | HVAC SYSTEM OF OFFICE BLOCK | 2615 | SITC of Ball Valve With Ystrn 25Mm Dia | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
1034 | BLD-2248-D-PIPE¦C¦7¦7'2 | HVAC SYSTEM OF OFFICE BLOCK | 2616 | SITC of Ball Valve With Ystrn 32Mm Dia | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
1035 | BLD-2248-D-PIPE¦C¦8¦8'1 | HVAC SYSTEM OF OFFICE BLOCK | 2617 | SITC of Preinslt Check Vlv 300Mm Dia | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
1036 | BLD-2248-D-PIPE¦C¦8¦8'2 | HVAC SYSTEM OF OFFICE BLOCK | 2618 | SITC of Preinslt Check Vlv 250Mm Dia | 12-12-2019 | 17-03-2022 | EA | 4 | 2020 | 8
1037 | BLD-2248-D-PIPE¦C¦8¦8'3 | HVAC SYSTEM OF OFFICE BLOCK | 2619 | SITC of Preinslt Check Vlv 200Mm Dia | 12-12-2019 | 17-03-2022 | EA | 7 | 2020 | 8
1038 | BLD-2248-D-PIPE¦C¦8¦8'4 | HVAC SYSTEM OF OFFICE BLOCK | 2620 | SITC of Preinslt Check Vlv 150Mm Dia | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
1039 | BLD-2248-D-PIPE¦C¦9¦9'1 | HVAC SYSTEM OF OFFICE BLOCK | 2621 | SITC of Preinslt Y Strainer 250Mm Dia | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
1040 | BLD-2248-D-PIPE¦C¦9¦9'2 | HVAC SYSTEM OF OFFICE BLOCK | 2622 | SITC of Preinslt Y Strainer 200Mm Dia | 12-12-2019 | 17-03-2022 | EA | 7 | 2020 | 8
1041 | BLD-2248-D-PIPE¦C¦9¦9'3 | HVAC SYSTEM OF OFFICE BLOCK | 2623 | SITC of Preinslt Y Strainer 150Mm Dia | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
1042 | BLD-2248-D-PIPE¦C¦9¦9'4 | HVAC SYSTEM OF OFFICE BLOCK | 2624 | SITC of Preinslt Y Strainer 125Mm Dia | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
1043 | BLD-2248-D-PIPE¦C¦9¦9'5 | HVAC SYSTEM OF OFFICE BLOCK | 2625 | SITC of Preinslt Y Strainer 100Mm Dia | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
1044 | BLD-2248-D-PIPE¦C¦9¦9'6 | HVAC SYSTEM OF OFFICE BLOCK | 2626 | SITC of Preinslt Y Strainer 80Mm Dia | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
1045 | BLD-2248-D-PIPE¦C¦9¦9'7 | HVAC SYSTEM OF OFFICE BLOCK | 2627 | SITC of Preinslt Y Strainer 65Mm Dia | 12-12-2019 | 17-03-2022 | EA | 4 | 2020 | 8
1046 | BLD-2248-D-PIPE¦C¦9¦9'8 | HVAC SYSTEM OF OFFICE BLOCK | 2628 | SITC of Preinslt Y Strainer 50Mm Dia | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
1047 | BLD-2248-D-PIPE¦C¦9¦9'9 | HVAC SYSTEM OF OFFICE BLOCK | 2629 | SITC of Preinslt Y Strainer 40Mm Dia | 12-12-2019 | 17-03-2022 | EA | 3 | 2020 | 8
1048 | BLD-2248-D-PIPE¦C¦9¦9'10 | HVAC SYSTEM OF OFFICE BLOCK | 2630 | SITC of Preinslt Y Strainer 30Mm Dia | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
1049 | BLD-2248-D-PI¦C¦10¦10'1 | HVAC SYSTEM OF OFFICE BLOCK | 2631 | SITC of Pot Strainer 350Mm Dia Pipe | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
1050 | BLD-2248-D-PIC¦10¦10'2 | HVAC SYSTEM OF OFFICE BLOCK | 2632 | SITC of Pot Strainer 250Mm Dia Pipe | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
1051 | BLD-2248-D-PI¦C¦10¦10'3 | HVAC SYSTEM OF OFFICE BLOCK | 2633 | SITC of Pot Strainer 200Mm Dia Pipe | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
1052 | BLD-2248-D-PI¦C¦11¦11'1 | HVAC SYSTEM OF OFFICE BLOCK | 2634 | SITC of Flexible Connection 300Mm Dia | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
1053 | BLD-2248-D-PI¦C¦11¦11'2 | HVAC SYSTEM OF OFFICE BLOCK | 2635 | SITC of Flexible Connection 250Mm Dia | 12-12-2019 | 17-03-2022 | EA | 16 | 2020 | 8
1054 | BLD-2248-D-PI¦C¦11¦11'3 | HVAC SYSTEM OF OFFICE BLOCK | 2636 | SITC of Flexible Connection 200Mm Dia | 12-12-2019 | 17-03-2022 | EA | 22 | 2020 | 8
1055 | BLD-2248-D-PI¦C¦11¦11'4 | HVAC SYSTEM OF OFFICE BLOCK | 2637 | SITC of Flexible Connection 150Mm Dia | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
1056 | BLD-2248-D-PIPE¦C¦12 | HVAC SYSTEM OF OFFICE BLOCK | 2638 | SITC of Auto Air Vents | 12-12-2019 | 17-03-2022 | EA | 10 | 2020 | 8
1057 | BLD-2248-D-PIPE¦C¦13 | HVAC SYSTEM OF OFFICE BLOCK | 2639 | P&F Probe Type Flow Meter | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
1058 | BLD-2248-D-PIPE¦C¦14 | HVAC SYSTEM OF OFFICE BLOCK | 2640 | P&F Ss304 Dial Type Pr Gauge Wth Gm Vlv | 12-12-2019 | 17-03-2022 | EA | 92 | 2020 | 8
1059 | BLD-2248-D-PIPE¦C¦15 | HVAC SYSTEM OF OFFICE BLOCK | 2641 | P&F Ss304 Hg Type Pr Gauge Wth Gm Vlv | 12-12-2019 | 17-03-2022 | EA | 70 | 2020 | 8
1060 | BLD-2248-D-PI¦C¦16¦16'1 | HVAC SYSTEM OF OFFICE BLOCK | 2642 | SITC of GI Drain Pipe 100Mm Dia | 12-12-2019 | 17-03-2022 | M | 140 | 2020 | 8
1061 | BLD-2248-D-PI¦C¦16¦16'2 | HVAC SYSTEM OF OFFICE BLOCK | 2643 | SITC of GI Drain Pipe 50Mm Dia | 12-12-2019 | 17-03-2022 | M | 72 | 2020 | 8
1062 | BLD-2248-D-PI¦C¦16¦16'3 | HVAC SYSTEM OF OFFICE BLOCK | 2644 | SITC of GI Drain Pipe 40Mm Dia | 12-12-2019 | 17-03-2022 | M | 150 | 2020 | 8
1063 | BLD-2248-D-ARDST¦C¦1¦1'1 | HVAC SYSTEM OF OFFICE BLOCK | 2645 | SITC of 26 G GI Sheet Ducts | 12-12-2019 | 17-03-2022 | M2 | 1595 | 2020 | 8
1064 | BLD-2248-D-ARDST¦C¦1¦1'2 | HVAC SYSTEM OF OFFICE BLOCK | 2646 | SITC of 24 G GI Sheet Ducts | 12-12-2019 | 17-03-2022 | M2 | 660 | 2020 | 8
1065 | BLD-2248-D-ARDST¦C¦1¦1'3 | HVAC SYSTEM OF OFFICE BLOCK | 2647 | SITC of 22 G GI Sheet Ducts | 12-12-2019 | 17-03-2022 | M2 | 1280 | 2020 | 8
1066 | BLD-2248-D-ARDST¦C¦1¦1'4 | HVAC SYSTEM OF OFFICE BLOCK | 2648 | SITC of 20 G GI Sheet Ducts | 12-12-2019 | 17-03-2022 | M2 | 200 | 2020 | 8
1067 | BLD-2248-D-ARDST¦C¦1¦1'5 | HVAC SYSTEM OF OFFICE BLOCK | 2649 | SITC of 18 G GI Sheet Ducts | 12-12-2019 | 17-03-2022 | M2 | 1380 | 2020 | 8
1068 | BLD-2248-D-ARDST¦C¦2 | HVAC SYSTEM OF OFFICE BLOCK | 2650 | SITC of Fire Wrapping On Duct | 12-12-2019 | 17-03-2022 | M2 | 0 | 2020 | 8
1069 | BLD-2248-D-ARDST¦C¦3 | HVAC SYSTEM OF OFFICE BLOCK | 2651 | SITC of Flexible Canvas Connection | 12-12-2019 | 17-03-2022 | M2 | 20 | 2020 | 8
1070 | BLD-2248-D-ARDST¦C¦4 | HVAC SYSTEM OF OFFICE BLOCK | 2652 | SITC of GI Dapmers Within Duct | 12-12-2019 | 17-03-2022 | M2 | 0 | 2020 | 8
1071 | BLD-2248-D-ARDST¦C¦5¦5'1 | HVAC SYSTEM OF OFFICE BLOCK | 2653 | SITC of Smoke & Fire Damper | 12-12-2019 | 17-03-2022 | M2 | 55 | 2020 | 8
1072 | BLD-2248-D-ARDST¦C¦5¦5'2 | HVAC SYSTEM OF OFFICE BLOCK | 2654 | SITC of Actuator For Fd | 12-12-2019 | 17-03-2022 | EA | 71 | 2020 | 8
1073 | BLD-2248-D-ARDST¦C¦5¦5'3 | HVAC SYSTEM OF OFFICE BLOCK | 2655 | SITC of Control Panel & Wiring For Fd | 12-12-2019 | 17-03-2022 | EA | 71 | 2020 | 8
1074 | BLD-2248-D-ARDST¦C¦6¦6'1 | HVAC SYSTEM OF OFFICE BLOCK | 2656 | SITC of Al Air Grill With Louvers & Vcd | 12-12-2019 | 17-03-2022 | M2 | 0 | 2020 | 8
1075 | BLD-2248-D-ARDST¦C¦6¦6'2 | HVAC SYSTEM OF OFFICE BLOCK | 2657 | SITC of Al Air Grill With Hrzn Fixed Bar | 12-12-2019 | 17-03-2022 | M2 | 0 | 2020 | 8
1076 | BLD-2248-D-ARDST¦C¦7¦7'1 | HVAC SYSTEM OF OFFICE BLOCK | 2658 | SITC of Al Air Grill With Louvers | 12-12-2019 | 17-03-2022 | M2 | 97 | 2020 | 8
1077 | BLD-2248-D-ARDST¦C¦8 | HVAC SYSTEM OF OFFICE BLOCK | 2659 | SITC of Al Air Transfr Door Grills | 12-12-2019 | 17-03-2022 | M2 | 2 | 2020 | 8
1078 | BLD-2248-D-ARDST¦C¦9 | HVAC SYSTEM OF OFFICE BLOCK | 2660 | SITC of Auto Pr Relief Damper | 12-12-2019 | 17-03-2022 | M2 | 0 | 2020 | 8
1079 | BLD-2248-D-ADT¦C¦10¦10'1 | HVAC SYSTEM OF OFFICE BLOCK | 2661 | SITC of Al Louver With Bird Screen | 12-12-2019 | 17-03-2022 | M2 | 1 | 2020 | 8
1080 | BLD-2248-D-ADT¦C¦10¦10'2 | HVAC SYSTEM OF OFFICE BLOCK | 2662 | SITC of Ms Louver With Bird Screen | 12-12-2019 | 17-03-2022 | M2 | 0 | 2020 | 8
1081 | BLD-2248-D-INSU¦E¦1¦1'1 | HVAC SYSTEM OF OFFICE BLOCK | 2663 | SITC of 15Mm Thk Acoust Lining On Duct | 12-12-2019 | 17-03-2022 | M2 | 300 | 2020 | 8
1082 | BLD-2248-D-INSU¦E¦1¦1'2 | HVAC SYSTEM OF OFFICE BLOCK | 2664 | SITC of 15Mm Thk Acoust Lining On Duct | 12-12-2019 | 17-03-2022 | M2 | 0 | 2020 | 8
1083 | BLD-2248-D-INSU¦E¦2¦2'1 | HVAC SYSTEM OF OFFICE BLOCK | 2665 | SITC Of19Mm Thk Thermal Insl On S&R Duct | 12-12-2019 | 17-03-2022 | M2 | 2765 | 2020 | 8
1084 | BLD-2248-D-INSU¦E¦2¦2'2 | HVAC SYSTEM OF OFFICE BLOCK | 2666 | SITC Of25Mm Thk Thermal Insl On S&R Duct | 12-12-2019 | 17-03-2022 | M2 | 1500 | 2020 | 8
1085 | BLD-2248-D-INSU¦E¦3¦3'1 | HVAC SYSTEM OF OFFICE BLOCK | 2667 | Sit of Nitrile Rubb Wth Coatng 40Mm Dia | 12-12-2019 | 17-03-2022 | M | 430 | 2020 | 8
1086 | BLD-2248-D-INSU¦E¦3¦3'2 | HVAC SYSTEM OF OFFICE BLOCK | 2668 | Sit of Nitrile Rubb Wth Coatng 32Mm Dia | 12-12-2019 | 17-03-2022 | M | 200 | 2020 | 8
1087 | BLD-2248-D-INSU¦E¦3¦3'3 | HVAC SYSTEM OF OFFICE BLOCK | 2669 | Sit of Nitrile Rubb Wth Coatng 25Mm Dia | 12-12-2019 | 17-03-2022 | M | 570 | 2020 | 8
1088 | BLD-2248-D-INSU¦E¦3¦3'4 | HVAC SYSTEM OF OFFICE BLOCK | 2670 | Sit of Nitrile Rubb Wth Coatng 20Mm Dia | 12-12-2019 | 17-03-2022 | M | 0 | 2020 | 8
1089 | BLD-2248-D-INSU¦E¦3¦3'5 | HVAC SYSTEM OF OFFICE BLOCK | 2671 | Sit of Nitrile Rubb Wth Coatng 15Mm Dia | 12-12-2019 | 17-03-2022 | M | 0 | 2020 | 8
1090 | BLD-2248-D-INSU¦E¦3¦3'6 | HVAC SYSTEM OF OFFICE BLOCK | 2672 | Sit of Nitrile Rubb Wth Coatng 50Mm Dia | 12-12-2019 | 17-03-2022 | M | 150 | 2020 | 8
1091 | BLD-2248-D-INSU¦E¦3¦3'7 | HVAC SYSTEM OF OFFICE BLOCK | 2673 | Sit of Nitrile Rubb Wth Coatng 32Mm Dia | 12-12-2019 | 17-03-2022 | M | 1000 | 2020 | 8
1092 | BLD-2248-D-INSU¦E¦3¦3'8 | HVAC SYSTEM OF OFFICE BLOCK | 2674 | Sit of Nitrile Rubb Wth Coatng 25Mm Dia | 12-12-2019 | 17-03-2022 | M | 500 | 2020 | 8
1093 | BLD-2248-D-INSU¦E¦4¦4'1 | HVAC SYSTEM OF OFFICE BLOCK | 2675 | Sit of Nitrile Rubb Wth Coatng 150Mm Dia | 12-12-2019 | 17-03-2022 | M | 330 | 2020 | 8
1094 | BLD-2248-D-INSU¦E¦4¦4'2 | HVAC SYSTEM OF OFFICE BLOCK | 2676 | Sit of Nitrile Rubb Wth Coatng 125Mm Dia | 12-12-2019 | 17-03-2022 | M | 60 | 2020 | 8
1095 | BLD-2248-D-INSU¦E¦4¦4'3 | HVAC SYSTEM OF OFFICE BLOCK | 2677 | Sit of Nitrile Rubb Wth Coatng 100Mm Dia | 12-12-2019 | 17-03-2022 | M | 15 | 2020 | 8
1096 | BLD-2248-D-INSU¦E¦4¦4'4 | HVAC SYSTEM OF OFFICE BLOCK | 2678 | Sit of Nitrile Rubb Wth Coatng 80Mm Dia | 12-12-2019 | 17-03-2022 | M | 715 | 2020 | 8
1097 | BLD-2248-D-INSU¦E¦4¦4'5 | HVAC SYSTEM OF OFFICE BLOCK | 2679 | Sit of Nitrile Rubb Wth Coatng 65Mm Dia | 12-12-2019 | 17-03-2022 | M | 950 | 2020 | 8
1098 | BLD-2248-D-INSU¦E¦4¦4'6 | HVAC SYSTEM OF OFFICE BLOCK | 2680 | Sit of Nitrile Rubb Wth Coatng 50Mm Dia | 12-12-2019 | 17-03-2022 | M | 1360 | 2020 | 8
1099 | BLD-2248-D-INSU¦E¦5¦5'1 | HVAC SYSTEM OF OFFICE BLOCK | 2681 | Sit of Nitrile Rubb Wth Coatng 400Mm Dia | 12-12-2019 | 17-03-2022 | M | 0 | 2020 | 8
1100 | BLD-2248-D-INSU¦E¦5¦5'2 | HVAC SYSTEM OF OFFICE BLOCK | 2682 | Sit of Nitrile Rubb Wth Coatng 350Mm Dia | 12-12-2019 | 17-03-2022 | M | 0 | 2020 | 8
1101 | BLD-2248-D-INSU¦E¦5¦5'3 | HVAC SYSTEM OF OFFICE BLOCK | 2683 | Sit of Nitrile Rubb Wth Coatng 300Mm Dia | 12-12-2019 | 17-03-2022 | M | 0 | 2020 | 8
1102 | BLD-2248-D-INSU¦E¦5¦5'4 | HVAC SYSTEM OF OFFICE BLOCK | 2684 | Sit of Nitrile Rubb Wth Coatng 250Mm Dia | 12-12-2019 | 17-03-2022 | M | 370 | 2020 | 8
1103 | BLD-2248-D-INSU¦E¦5¦5'5 | HVAC SYSTEM OF OFFICE BLOCK | 2685 | Sit of Nitrile Rubb Wth Coatng 200Mm Dia | 12-12-2019 | 17-03-2022 | M | 300 | 2020 | 8
1104 | BLD-2248-D-INSU¦E¦6¦6'1 | HVAC SYSTEM OF OFFICE BLOCK | 2686 | SITC of Acoust Lining On Wall 25Mm Thck | 12-12-2019 | 17-03-2022 | M2 | 350 | 2020 | 8
1105 | BLD-2248-D-T&C¦F | HVAC SYSTEM OF OFFICE BLOCK | 2687 | Charges For System T&C By Third Party | 12-12-2019 | 17-03-2022 | LOT | 1 | 2020 | 8
1106 | BLD-2248-D-¦G¦1'1¦1'1'1 | HVAC SYSTEM OF HOSTEL BLOCK | 2688 | SITC of Odu 22Hp Gf | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
1107 | BLD-2248-D-¦G¦1'1¦1'1'2 | HVAC SYSTEM OF HOSTEL BLOCK | 2689 | SITC of Odu 42Hp 7Th Flr | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
1108 | BLD-2248-D-G¦1'1¦1'1'3¦I | HVAC SYSTEM OF HOSTEL BLOCK | 2690 | SITC of Odu 58Hp 8Th Flr | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
1109 | BLD-2248-D-G¦1'1¦1'1'1II | HVAC SYSTEM OF HOSTEL BLOCK | 2691 | SITC of Odu 66Hp 8Th Flr | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
1110 | BLD-2248-D-VRF¦1'1'4 | HVAC SYSTEM OF HOSTEL BLOCK | 2692 | SITC of Odu 42Hp 9 To 17Th Flr | 12-12-2019 | 17-03-2022 | EA | 9 | 2020 | 8
1111 | BLD-2248-D-VRF¦1'1'5 | HVAC SYSTEM OF HOSTEL BLOCK | 2693 | SITC of Odu 48Hp 18Th Flr | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
1112 | BLD-2248-D-VRF¦1'1'6 | HVAC SYSTEM OF HOSTEL BLOCK | 2694 | SITC of Odu 28Hp 19Th Flr | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
1113 | BLD-2248-D-VRF¦1'1'7 | HVAC SYSTEM OF HOSTEL BLOCK | 2695 | SITC of Odu 66Hp Doas Unit | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
1114 | BLD-2248-D-G¦1'2¦1'2'1 | HVAC SYSTEM OF HOSTEL BLOCK | 2696 | SITC of Hiwall 1.6Tr 8Th Flr | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
1115 | BLD-2248-D-G¦1'2¦1'2'2 | HVAC SYSTEM OF HOSTEL BLOCK | 2697 | SITC of Hiwall 1.6Tr 18Th Flr | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
1116 | BLD-2248-D-G¦1¦1'2¦1'2'3 | HVAC SYSTEM OF HOSTEL BLOCK | 2698 | SITC of Hiwall 2Tr 18Th Flr | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
1117 | BLD-2248-D-G¦1¦1'2¦1'2'4 | HVAC SYSTEM OF HOSTEL BLOCK | 2699 | SITC of Hiwall 2Tr 8Th Flr Vc Room | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
1118 | BLD-2248-D-G¦1¦1'2¦1'2'5 | HVAC SYSTEM OF HOSTEL BLOCK | 2700 | SITC of Hiwall 2Tr 18Th Flr Gym | 12-12-2019 | 17-03-2022 | EA | 7 | 2020 | 8
1119 | BLD-2248-D-G¦1¦1'2¦1'2'6 | HVAC SYSTEM OF HOSTEL BLOCK | 2701 | SITC of Hiwall 2Tr 18Th Flr Bad Court | 12-12-2019 | 17-03-2022 | EA | 5 | 2020 | 8
1120 | BLD-2248-D-G¦1¦1'2¦1'2'7 | HVAC SYSTEM OF HOSTEL BLOCK | 2702 | SITC of Cassette 1.6Tr 8Th Flr Conf | 12-12-2019 | 17-03-2022 | EA | 8 | 2020 | 8
1121 | BLD-2248-D-G¦1¦1'2¦1'2'8 | HVAC SYSTEM OF HOSTEL BLOCK | 2703 | SITC of Cassette 2Tr 8Th Flr Conf | 12-12-2019 | 17-03-2022 | EA | 4 | 2020 | 8
1122 | BLD-2248-D-G¦1¦1'2¦1'2'9 | HVAC SYSTEM OF HOSTEL BLOCK | 2704 | SITC of Dx Fcu 2Tr 10-17Th Flr Hstlrm | 12-12-2019 | 17-03-2022 | EA | 56 | 2020 | 8
1123 | BLD-2248-D-G¦1'2¦1'2'10 | HVAC SYSTEM OF HOSTEL BLOCK | 2705 | SITC of Dx Fcu 2.5Tr 10-17Th Flr Hstlrm | 12-12-2019 | 17-03-2022 | EA | 24 | 2020 | 8
1124 | BLD-2248-D-G¦1¦1'3¦1'3'1 | HVAC SYSTEM OF HOSTEL BLOCK | 2706 | SITC of 20Tr 8000Cfm Csu 8Th Flr | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
1125 | BLD-2248-D-G¦1¦1'3¦1'3'2 | HVAC SYSTEM OF HOSTEL BLOCK | 2707 | SITC of 15Tr 6000Cfm Csu 9Th Flr | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
1126 | BLD-2248-D-G¦1¦1'3¦1'3'3 | HVAC SYSTEM OF HOSTEL BLOCK | 2708 | SITC of 10Tr 4000Cfm Csu 8Th Flr | 12-12-2019 | 17-03-2022 | EA | 3 | 2020 | 8
1127 | BLD-2248-D-G¦1¦1'3¦1'3'4 | HVAC SYSTEM OF HOSTEL BLOCK | 2709 | SITC of 9.5Tr 3800Cfm Csu 8Th Flr | 12-12-2019 | 17-03-2022 | EA | 8 | 2020 | 8
1128 | BLD-2248-D-G¦1¦1'3¦1'3'5 | HVAC SYSTEM OF HOSTEL BLOCK | 2710 | SITC of 9.5Tr 3800Cfm Csu 8Th Flr | 12-12-2019 | 17-03-2022 | EA | 4 | 2020 | 8
1129 | BLD-2248-D-G¦1¦1'3¦1'3'6 | HVAC SYSTEM OF HOSTEL BLOCK | 2711 | SITC of 9Tr 3600Cfm Csu 8Th Flr | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
1130 | BLD-2248-D-G¦1¦1'3¦1'3'7 | HVAC SYSTEM OF HOSTEL BLOCK | 2712 | SITC of 8Tr 3200Cfm Csu 8Th Flr | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
1131 | BLD-2248-D-G¦1¦1'3¦1'3'8 | HVAC SYSTEM OF HOSTEL BLOCK | 2713 | SITC of 7.5Tr 3000Cfm Csu 8Th Flr | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
1132 | BLD-2248-D-G¦1¦1'3¦1'3'9 | HVAC SYSTEM OF HOSTEL BLOCK | 2714 | SITC of 7.5Tr 3000Cfm Csu 8Th Flr | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
1133 | BLD-2248-D-G¦1'3¦1'3'10 | HVAC SYSTEM OF HOSTEL BLOCK | 2715 | SITC of 6.5Tr 2600Cfm Csu 8Th Flr | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
1134 | BLD-2248-D-G¦1'3¦1'3'11 | HVAC SYSTEM OF HOSTEL BLOCK | 2716 | SITC of 4Tr 1600Cfm Csu 10-17Th Flr | 12-12-2019 | 17-03-2022 | EA | 9 | 2020 | 8
1135 | BLD-2248-D-G¦1'3¦1'3'12 | HVAC SYSTEM OF HOSTEL BLOCK | 2717 | SITC of 3Tr 1200Cfm Csu 10-17Th Flr | 12-12-2019 | 17-03-2022 | EA | 8 | 2020 | 8
1136 | BLD-2248-D-VRF¦G¦2 | HVAC SYSTEM OF HOSTEL BLOCK | 2718 | SITC of Crc | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
1137 | BLD-2248-D-VRF¦G¦3¦3'1 | HVAC SYSTEM OF HOSTEL BLOCK | 2719 | SITC of 16G Cu Pipe 6.35Mm Dia | 12-12-2019 | 17-03-2022 | M | 24 | 2020 | 8
1138 | BLD-2248-D-VRF¦G¦3¦3'2 | HVAC SYSTEM OF HOSTEL BLOCK | 2720 | SITC of 16G Cu Pipe 9.5Mm Dia | 12-12-2019 | 17-03-2022 | M | 612 | 2020 | 8
1139 | BLD-2248-D-VRF¦G¦3¦3'3 | HVAC SYSTEM OF HOSTEL BLOCK | 2721 | SITC of 16G Cu Pipe 12.7Mm Dia | 12-12-2019 | 17-03-2022 | M | 365 | 2020 | 8
1140 | BLD-2248-D-VRF¦G¦3¦3'4 | HVAC SYSTEM OF HOSTEL BLOCK | 2722 | SITC of 16G Cu Pipe 15.8Mm Dia | 12-12-2019 | 17-03-2022 | M | 683 | 2020 | 8
1141 | BLD-2248-D-VRF¦G¦3¦3'5 | HVAC SYSTEM OF HOSTEL BLOCK | 2723 | SITC of 16G Cu Pipe 19.1Mm Dia | 12-12-2019 | 17-03-2022 | M | 1158 | 2020 | 8
1142 | BLD-2248-D-VRF¦G¦3¦3'6 | HVAC SYSTEM OF HOSTEL BLOCK | 2724 | SITC of 16G Cu Pipe 22.2Mm Dia | 12-12-2019 | 17-03-2022 | M | 235 | 2020 | 8
1143 | BLD-2248-D-VRF¦G¦3¦3'7 | HVAC SYSTEM OF HOSTEL BLOCK | 2725 | SITC of 16G Cu Pipe 28.5Mm Dia | 12-12-2019 | 17-03-2022 | M | 522 | 2020 | 8
1144 | BLD-2248-D-VRF¦G¦3¦3'8 | HVAC SYSTEM OF HOSTEL BLOCK | 2726 | SITC of 16G Cu Pipe 34.9Mm Dia | 12-12-2019 | 17-03-2022 | M | 778 | 2020 | 8
1145 | BLD-2248-D-VRF¦G¦3¦3'9 | HVAC SYSTEM OF HOSTEL BLOCK | 2727 | SITC of 16G Cu Pipe 41.3Mm Dia | 12-12-2019 | 17-03-2022 | M | 530 | 2020 | 8
1146 | BLD-2248-D-VRF¦G¦4 | HVAC SYSTEM OF HOSTEL BLOCK | 2728 | Charges For Customs Duty On Imprt Eqpmt | 12-12-2019 | 17-03-2022 | LOT | 1 | 2020 | 8
1147 | BLD-2248-D-VRF¦G¦5 | HVAC SYSTEM OF HOSTEL BLOCK | 2729 | Charges For Port Clearance | 12-12-2019 | 17-03-2022 | LOT | 1 | 2020 | 8
1148 | BLD-2248-D-VRF¦G¦6¦6'1 | HVAC SYSTEM OF HOSTEL BLOCK | 2730 | S&I of 25Mm Dia PVC Drain Pipe With Insu | 12-12-2019 | 17-03-2022 | M | 420 | 2020 | 8
1149 | BLD-2248-D-VRF¦G¦6¦6'2 | HVAC SYSTEM OF HOSTEL BLOCK | 2731 | S&I of 32Mm Dia PVC Drain Pipe With Insu | 12-12-2019 | 17-03-2022 | M | 84 | 2020 | 8
1150 | BLD-2248-D-VRF¦G¦6¦6'3 | HVAC SYSTEM OF HOSTEL BLOCK | 2732 | S&I of 40Mm Dia PVC Drain Pipe With Insu | 12-12-2019 | 17-03-2022 | M | 60 | 2020 | 8
1151 | BLD-2248-D-VRF¦G¦7¦7'1 | HVAC SYSTEM OF HOSTEL BLOCK | 2733 | SITC of Hru 22000 Cfm 50Tr Capacity | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
1152 | BLD-2248-D-VRF¦G¦8¦8'1¦I | HVAC SYSTEM OF HOSTEL BLOCK | 2734 | Supply of Vav Min 700Cfm Max 1300Cfm | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
1153 | BLD-2248-D-¦G¦8¦8'1¦II | HVAC SYSTEM OF HOSTEL BLOCK | 2735 | Supply of Vav Min 1000Cfm Max 1900Cfm | 12-12-2019 | 17-03-2022 | EA | 12 | 2020 | 8
1154 | BLD-2248-D-¦G¦8¦8'1¦III | HVAC SYSTEM OF HOSTEL BLOCK | 2736 | Supply of Vav Min 2000Cfm Max 3000Cfm | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
1155 | BLD-2248-D-VRF¦G¦8¦8'2 | HVAC SYSTEM OF HOSTEL BLOCK | 2737 | Port & Handling Charges For Vav | 12-12-2019 | 17-03-2022 | EA | 14 | 2020 | 8
1156 | BLD-2248-D-VRF¦G¦8¦8'3 | HVAC SYSTEM OF HOSTEL BLOCK | 2738 | Customs Duty & Contervailing For Vav | 12-12-2019 | 17-03-2022 | EA | 14 | 2020 | 8
1157 | BLD-2248-D-VRF¦G¦8¦8'4 | HVAC SYSTEM OF HOSTEL BLOCK | 2739 | Shifting & Installing of Vav | 12-12-2019 | 17-03-2022 | EA | 14 | 2020 | 8
1158 | BLD-2248-D-VRF¦G¦9¦9'1 | HVAC SYSTEM OF HOSTEL BLOCK | 2740 | SITC of Axial Fan 28500Cfm | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
1159 | BLD-2248-D-VRF¦G¦9¦9'2 | HVAC SYSTEM OF HOSTEL BLOCK | 2741 | SITC of Axial Fan 11100Cfm | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
1160 | BLD-2248-D-VRF¦G¦9¦9'3 | HVAC SYSTEM OF HOSTEL BLOCK | 2742 | SITC of Axial Fan 11300Cfm | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
1161 | BLD-2248-D-VRF¦G¦9¦9'4 | HVAC SYSTEM OF HOSTEL BLOCK | 2743 | SITC of Axial Fan 11300Cfm | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
1162 | BLD-2248-D-VRF¦G¦10¦10'1 | HVAC SYSTEM OF HOSTEL BLOCK | 2744 | SITC of Propellor Fan 100Mm Dia 100Cfm | 12-12-2019 | 17-03-2022 | EA | 3 | 2020 | 8
1163 | BLD-2248-D-VRF¦G¦10¦10'2 | HVAC SYSTEM OF HOSTEL BLOCK | 2745 | SITC of Propellor Fan 100Mm Dia 100Cfm | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
1164 | BLD-2248-D-VRF¦G¦10¦10'3 | HVAC SYSTEM OF HOSTEL BLOCK | 2746 | SITC of Propellor Fan 400Mm Dia 1050Cfm | 12-12-2019 | 17-03-2022 | EA | 6 | 2020 | 8
1165 | BLD-2248-D-VRF¦G¦10¦10'4 | HVAC SYSTEM OF HOSTEL BLOCK | 2747 | SITC of Propellor Fan 400Mm Dia 1050Cfm | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
1166 | BLD-2248-D-VRF¦G¦10¦10'5 | HVAC SYSTEM OF HOSTEL BLOCK | 2748 | SITC of Propellor Fan 300Mm Dia 700Cfm | 12-12-2019 | 17-03-2022 | EA | 4 | 2020 | 8
1167 | BLD-2248-D-VRF¦G¦10¦10'6 | HVAC SYSTEM OF HOSTEL BLOCK | 2749 | SITC of Propellor Fan 400Mm Dia 1000Cfm | 12-12-2019 | 17-03-2022 | EA | 4 | 2020 | 8
1168 | BLD-2248-D-VRF¦G¦10¦10'7 | HVAC SYSTEM OF HOSTEL BLOCK | 2750 | SITC of Propellor Fan 400Mm Dia 1000Cfm | 12-12-2019 | 17-03-2022 | EA | 4 | 2020 | 8
1169 | BLD-2248-D-VRF¦G¦10¦10'8 | HVAC SYSTEM OF HOSTEL BLOCK | 2751 | SITC of Propellor Fan 100Mm Dia 100Cfm | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
1170 | BLD-2248-D-VRF¦G¦11¦11'1 | HVAC SYSTEM OF HOSTEL BLOCK | 2752 | SITC of Inline Fan 6000Cfm | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
1171 | BLD-2248-D-VRF¦G¦11¦11'2 | HVAC SYSTEM OF HOSTEL BLOCK | 2753 | SITC of Inline Fan 5300Cfm | 12-12-2019 | 17-03-2022 | EA | 4 | 2020 | 8
1172 | BLD-2248-D-ARD¦G¦12¦12'1 | HVAC SYSTEM OF HOSTEL BLOCK | 2754 | SITC of 26G GI Duct | 12-12-2019 | 17-03-2022 | M2 | 110 | 2020 | 8
1173 | BLD-2248-D-ARD¦G¦12¦12'2 | HVAC SYSTEM OF HOSTEL BLOCK | 2755 | SITC of 24G GI Duct | 12-12-2019 | 17-03-2022 | M2 | 260 | 2020 | 8
1174 | BLD-2248-D-ARD¦G¦12¦12'3 | HVAC SYSTEM OF HOSTEL BLOCK | 2756 | SITC of 22G GI Duct | 12-12-2019 | 17-03-2022 | M2 | 170 | 2020 | 8
1175 | BLD-2248-D-ARDIST¦G¦13 | HVAC SYSTEM OF HOSTEL BLOCK | 2757 | SITC of Flexible Duct Connection | 12-12-2019 | 17-03-2022 | M2 | 12 | 2020 | 8
1176 | BLD-2248-D-ARD¦G¦14¦14'1 | HVAC SYSTEM OF HOSTEL BLOCK | 2758 | SITC of Smoke & Fire Dampers | 12-12-2019 | 17-03-2022 | M2 | 23 | 2020 | 8
1177 | BLD-2248-D-ARD¦G¦14¦14'2 | HVAC SYSTEM OF HOSTEL BLOCK | 2759 | SITC of Actuator For Fd | 12-12-2019 | 17-03-2022 | EA | 68 | 2020 | 8
1178 | BLD-2248-D-ARD¦G¦14¦14'3 | HVAC SYSTEM OF HOSTEL BLOCK | 2760 | SITC of Control Panel & Wiring For Fd | 12-12-2019 | 17-03-2022 | EA | 68 | 2020 | 8
1179 | BLD-2248-D-ARD¦G¦15¦15'1 | HVAC SYSTEM OF HOSTEL BLOCK | 2761 | SITC of Al Grill With Dbl Louvers | 12-12-2019 | 17-03-2022 | M2 | 12 | 2020 | 8
1180 | BLD-2248-D-ARD¦G¦15¦15'2 | HVAC SYSTEM OF HOSTEL BLOCK | 2762 | SITC of Al Grill With Fixed Bars | 12-12-2019 | 17-03-2022 | M2 | 2 | 2020 | 8
1181 | BLD-2248-D-ARD¦G¦16¦16'1 | HVAC SYSTEM OF HOSTEL BLOCK | 2763 | SITC of Al Louvers Wth Cowl Brd Screen | 12-12-2019 | 17-03-2022 | M2 | 2 | 2020 | 8
1182 | BLD-2248-D-ARD¦G¦16¦16'2 | HVAC SYSTEM OF HOSTEL BLOCK | 2764 | SITC of Ms Louvers Wth Cowl Brd Screen | 12-12-2019 | 17-03-2022 | M2 | 0 | 2020 | 8
1183 | BLD-2248-D-ARD¦G¦17¦17'1 | HVAC SYSTEM OF HOSTEL BLOCK | 2765 | SITC of Al Sply Grill Wth Vcd | 12-12-2019 | 17-03-2022 | M2 | 0 | 2020 | 8
1184 | BLD-2248-D-ARDIST¦G¦18 | HVAC SYSTEM OF HOSTEL BLOCK | 2766 | SITC of 18G Gss Vcd In Sply Air Duct | 12-12-2019 | 17-03-2022 | M2 | 0 | 2020 | 8
1185 | BLD-2248-D-ARD¦G¦19¦19'1 | HVAC SYSTEM OF HOSTEL BLOCK | 2767 | SITC Al Pwdr Coated Sply Diffusers | 12-12-2019 | 17-03-2022 | M2 | 0 | 2020 | 8
1186 | BLD-2248-D-ARD¦G¦19¦19'2 | HVAC SYSTEM OF HOSTEL BLOCK | 2768 | SITC Ms Pwdr Coated Sply Diffusers | 12-12-2019 | 17-03-2022 | M2 | 0 | 2020 | 8
1187 | BLD-2248-D-ARD¦G¦20¦20'1 | HVAC SYSTEM OF HOSTEL BLOCK | 2769 | SITC Al Pwdr Coated Rtrn Diffusers | 12-12-2019 | 17-03-2022 | M2 | 0 | 2020 | 8
1188 | BLD-2248-D-ARD¦G¦20¦20'2 | HVAC SYSTEM OF HOSTEL BLOCK | 2770 | SITC Ms Pwdr Coated Rtrn Diffusers | 12-12-2019 | 17-03-2022 | M2 | 0 | 2020 | 8
1189 | BLD-2248-D-INS¦G¦21¦21'1 | HVAC SYSTEM OF HOSTEL BLOCK | 2771 | SITC of Cu Pipe Insu 19/13Mm 6.35Mm Dia | 12-12-2019 | 17-03-2022 | M | 24 | 2020 | 8
1190 | BLD-2248-D-INS¦G¦21¦21'2 | HVAC SYSTEM OF HOSTEL BLOCK | 2772 | SITC of Cu Pipe Insu 19/13Mm 9.5Mm Dia | 12-12-2019 | 17-03-2022 | M | 612 | 2020 | 8
1191 | BLD-2248-D-INS¦G¦21¦21'3 | HVAC SYSTEM OF HOSTEL BLOCK | 2773 | SITC of Cu Pipe Insu 19/13Mm 6.35Mm Dia | 12-12-2019 | 17-03-2022 | M | 365 | 2020 | 8
1192 | BLD-2248-D-INS¦G¦21¦21'4 | HVAC SYSTEM OF HOSTEL BLOCK | 2774 | SITC of Cu Pipe Insu 19/13Mm 6.35Mm Dia | 12-12-2019 | 17-03-2022 | M | 683 | 2020 | 8
1193 | BLD-2248-D-INS¦G¦21¦21'5 | HVAC SYSTEM OF HOSTEL BLOCK | 2775 | SITC of Cu Pipe Insu 19/13Mm 6.35Mm Dia | 12-12-2019 | 17-03-2022 | M | 1158 | 2020 | 8
1194 | BLD-2248-D-INS¦G¦21¦21'6 | HVAC SYSTEM OF HOSTEL BLOCK | 2776 | SITC of Cu Pipe Insu 19/13Mm 6.35Mm Dia | 12-12-2019 | 17-03-2022 | M | 235 | 2020 | 8
1195 | BLD-2248-D-INS¦G¦21¦21'7 | HVAC SYSTEM OF HOSTEL BLOCK | 2777 | SITC of Cu Pipe Insu 19/13Mm 6.35Mm Dia | 12-12-2019 | 17-03-2022 | M | 522 | 2020 | 8
1196 | BLD-2248-D-INS¦G¦21¦21'8 | HVAC SYSTEM OF HOSTEL BLOCK | 2778 | SITC of Cu Pipe Insu 19/13Mm 6.35Mm Dia | 12-12-2019 | 17-03-2022 | M | 778 | 2020 | 8
1197 | BLD-2248-D-INS¦G¦21¦21'9 | HVAC SYSTEM OF HOSTEL BLOCK | 2779 | SITC of Cu Pipe Insu 19/13Mm 6.35Mm Dia | 12-12-2019 | 17-03-2022 | M | 530 | 2020 | 8
1198 | BLD-2248-D-INS¦G¦22¦22'1 | HVAC SYSTEM OF HOSTEL BLOCK | 2780 | SITC of Acoustc Lining 15Mm Thck | 12-12-2019 | 17-03-2022 | M2 | 18 | 2020 | 8
1199 | BLD-2248-D-INS¦G¦22¦22'2 | HVAC SYSTEM OF HOSTEL BLOCK | 2781 | SITC of Acoustc Lining 30Mm Thck | 12-12-2019 | 17-03-2022 | M2 | 0 | 2020 | 8
1200 | BLD-2248-D-INS¦G¦23¦23'1 | HVAC SYSTEM OF HOSTEL BLOCK | 2782 | SITC of 19Mm Thck Insl On Duct | 12-12-2019 | 17-03-2022 | M2 | 230 | 2020 | 8
1201 | BLD-2248-D-INS¦G¦23¦23'2 | HVAC SYSTEM OF HOSTEL BLOCK | 2783 | SITC of 25Mm Thck Insl On Duct | 12-12-2019 | 17-03-2022 | M2 | 40 | 2020 | 8
1202 | BLD-2248-D-CPL¦G¦24¦24'1 | HVAC SYSTEM OF HOSTEL BLOCK | 2784 | SITC of 0.75Kw Dol Starter | 12-12-2019 | 17-03-2022 | EA | 39 | 2020 | 8
1203 | BLD-2248-D-CPL¦G¦24¦24'2 | HVAC SYSTEM OF HOSTEL BLOCK | 2785 | SITC of 1.1Kw Star-Delta Starter | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
1204 | BLD-2248-D-CPL¦G¦24¦24'3 | HVAC SYSTEM OF HOSTEL BLOCK | 2786 | SITC of 3.7Kw Star-Delta Starter | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
1205 | BLD-2248-D-CPL¦G¦24¦24'4 | HVAC SYSTEM OF HOSTEL BLOCK | 2787 | SITC of 5.5Kw Star-Delta Starter | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
1206 | BLD-2248-D-CPL¦G¦24¦24'5 | HVAC SYSTEM OF HOSTEL BLOCK | 2788 | SITC of 2.2Kw Star-Delta Starter | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
1207 | BLD-2248-D-CPL¦G¦24¦24'6 | HVAC SYSTEM OF HOSTEL BLOCK | 2789 | SITC of 1.5Kw Star-Delta Starter | 12-12-2019 | 17-03-2022 | EA | 4 | 2020 | 8
1208 | BLD-2248-D-CPL¦G¦24¦24'7 | HVAC SYSTEM OF HOSTEL BLOCK | 2790 | SITC of 0.75Kw Dol Starter | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
1209 | BLD-2248-D-PMGR¦H¦1¦1'01 | CHILLER PLANT OPTIMIZER | 2791 | SITC of Workstation For Cpo | 12-12-2019 | 17-03-2022 | LOT | 1 | 2020 | 8
1210 | BLD-2248-D-PMGR¦H¦1¦1'02 | CHILLER PLANT OPTIMIZER | 2792 | SITC of 24" Led Monitor | 12-12-2019 | 17-03-2022 | LOT | 1 | 2020 | 8
1211 | BLD-2248-D-PMGR¦H¦1¦1'03 | CHILLER PLANT OPTIMIZER | 2793 | Software For Cpo As Per Ts | 12-12-2019 | 17-03-2022 | LOT | 1 | 2020 | 8
1212 | BLD-2248-D-PMGR¦H¦1¦1'04 | CHILLER PLANT OPTIMIZER | 2794 | Software Interfac With Pump Vfd 3Nos | 12-12-2019 | 17-03-2022 | LOT | 1 | 2020 | 8
1213 | BLD-2248-D-PMGR¦H¦1¦1'05 | CHILLER PLANT OPTIMIZER | 2795 | Software Interface For Energy Meter | 12-12-2019 | 17-03-2022 | LOT | 1 | 2020 | 8
1214 | BLD-2248-D-PLNTMNGR¦H¦2 | CHILLER PLANT OPTIMIZER | 2796 | SITC of Ddc Controller | 12-12-2019 | 17-03-2022 | LOT | 1 | 2020 | 8
1215 | BLD-2248-D-PMGR¦H¦2¦2'02 | CHILLER PLANT OPTIMIZER | 2797 | SITC of Dp Transmitter | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
1216 | BLD-2248-D-PMGR¦H¦2¦2'03 | CHILLER PLANT OPTIMIZER | 2798 | SITC of Dp Switch | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
1217 | BLD-2248-D-PMGR¦H¦2¦2'04 | CHILLER PLANT OPTIMIZER | 2799 | SITC of Immersion Temp Sensor | 12-12-2019 | 17-03-2022 | EA | 8 | 2020 | 8
1218 | BLD-2248-D-PMGR¦H¦2¦2'05 | CHILLER PLANT OPTIMIZER | 2800 | SITC of Steam Temp Sensor | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
1219 | BLD-2248-D-PMGR¦H¦2¦2'06 | CHILLER PLANT OPTIMIZER | 2801 | SITC of Level Switch | 12-12-2019 | 17-03-2022 | EA | 4 | 2020 | 8
1220 | BLD-2248-D-PMGR¦H¦2¦2'07 | CHILLER PLANT OPTIMIZER | 2802 | SITC of Outside Temp & Rh Sensor | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
1221 | BLD-2248-D-PMGR¦H¦2¦2'08 | CHILLER PLANT OPTIMIZER | 2803 | SITC of Water Flow Switch | 12-12-2019 | 17-03-2022 | EA | 6 | 2020 | 8
1222 | BLD-2248-D-PMGR¦H¦2¦2'09 | CHILLER PLANT OPTIMIZER | 2804 | SITC of Limit Switch For Bfvlv Actuator | 12-12-2019 | 17-03-2022 | EA | 6 | 2020 | 8
1223 | BLD-2248-D-PMGR¦H¦2¦2'10 | CHILLER PLANT OPTIMIZER | 2805 | SITC of Ph Analyser | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
1224 | BLD-2248-D-PMGR¦H¦2¦2'11 | CHILLER PLANT OPTIMIZER | 2806 | SITC of Tds Analyser | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
1225 | BLD-2248-D-PMGR¦H¦2¦2'12 | CHILLER PLANT OPTIMIZER | 2807 | SITC of Water Hardness Analyser | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
1226 | BLD-2248-D-PMGR¦H¦2¦2'13 | CHILLER PLANT OPTIMIZER | 2808 | SITC of Ultrasonic Flow Meter For Chw | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
1227 | BLD-2248-D-PMGR¦H¦2¦2'14 | CHILLER PLANT OPTIMIZER | 2809 | SITC of 2Cx1Sqmm Atc Ar Cable | 12-12-2019 | 17-03-2022 | LOT | 1 | 2020 | 8
1228 | BLD-2248-D-PMGR¦H¦2¦2'15 | CHILLER PLANT OPTIMIZER | 2810 | SITC 2 Pair 18Awg Atc Ar Comm Cable | 12-12-2019 | 17-03-2022 | LOT | 1 | 2020 | 8
1229 | BLD-2248-D-PMGR¦H¦2¦2'16 | CHILLER PLANT OPTIMIZER | 2811 | SITC 3Cx1.5Sqmm Atc Ar Cable | 12-12-2019 | 17-03-2022 | LOT | 1 | 2020 | 8
1230 | BLD-2248-D-FFPUMP¦A¦1 | FIRE FIGHTING SYSTEM | 2812 | SITC of Multi Stg Main Pump 180/120Mtr H | 12-12-2019 | 17-03-2022 | SET | 2 | 2020 | 8
1231 | BLD-2248-D-FFPUMP¦A¦2 | FIRE FIGHTING SYSTEM | 2813 | SITC of Dg Pump 180/120Mtr H | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
1232 | BLD-2248-D-FFPUMP¦A¦3¦A | FIRE FIGHTING SYSTEM | 2814 | SITC of Jockey Pump 180Lpm 180Mtr H | 12-12-2019 | 17-03-2022 | SET | 2 | 2020 | 8
1233 | BLD-2248-D-FFPUMP¦A¦3¦B | FIRE FIGHTING SYSTEM | 2815 | SITC of Jockey Pump 180Lpm 120Mtr H | 12-12-2019 | 17-03-2022 | SET | 2 | 2020 | 8
1234 | BLD-2248-D-FFPH¦A¦4 | FIRE FIGHTING SYSTEM | 2816 | SITC of Air Vessel | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
1235 | BLD-2248-D-FFPH¦A¦5 | FIRE FIGHTING SYSTEM | 2817 | P&F of 100Mm Dia Pr Gauge | 12-12-2019 | 17-03-2022 | EA | 18 | 2020 | 8
1236 | BLD-2248-D-FFPH¦A¦6 | FIRE FIGHTING SYSTEM | 2818 | P&F of Liquid Level Cntrlr For Pump | 12-12-2019 | 17-03-2022 | SET | 2 | 2020 | 8
1237 | BLD-2248-D-FFPH¦A¦7 | FIRE FIGHTING SYSTEM | 2819 | P&F 25Mm Dia Gm Fitting For Wlg | 12-12-2019 | 17-03-2022 | SET | 2 | 2020 | 8
1238 | BLD-2248-D-FFPH¦A¦8¦A | FIRE FIGHTING SYSTEM | 2820 | Pl&T of 250Mm Dia C Cls Ms Erw Pipe | 12-12-2019 | 17-03-2022 | M | 8 | 2020 | 8
1239 | BLD-2248-D-FFPH¦A¦8¦B | FIRE FIGHTING SYSTEM | 2821 | Pl&T of 200Mm Dia C Cls Ms Erw Pipe | 12-12-2019 | 17-03-2022 | M | 15 | 2020 | 8
1240 | BLD-2248-D-FFPH¦A¦8¦C | FIRE FIGHTING SYSTEM | 2822 | Pl&T of 150Mm Dia C Cls Ms Erw Pipe | 12-12-2019 | 17-03-2022 | M | 25 | 2020 | 8
1241 | BLD-2248-D-FFPH¦A¦8¦D | FIRE FIGHTING SYSTEM | 2823 | Pl&T of 100Mm Dia C Cls Ms Erw Pipe | 12-12-2019 | 17-03-2022 | M | 8 | 2020 | 8
1242 | BLD-2248-D-FFPH¦A¦8¦E | FIRE FIGHTING SYSTEM | 2824 | Pl&T of 80Mm Dia C Cls Ms Erw Pipe | 12-12-2019 | 17-03-2022 | M | 16 | 2020 | 8
1243 | BLD-2248-D-FFPH¦A¦8¦F | FIRE FIGHTING SYSTEM | 2825 | Pl&T of 25Mm Dia C Cls Ms Erw Pipe | 12-12-2019 | 17-03-2022 | M | 15 | 2020 | 8
1244 | BLD-2248-D-FFPH¦A¦9¦A | FIRE FIGHTING SYSTEM | 2826 | P&A 3 Coat Painting On 250Mm Dia Ms Pipe | 12-12-2019 | 17-03-2022 | M | 8 | 2020 | 8
1245 | BLD-2248-D-FFPH¦A¦9¦B | FIRE FIGHTING SYSTEM | 2827 | P&A 3 Coat Painting On 200Mm Dia Ms Pipe | 12-12-2019 | 17-03-2022 | M | 15 | 2020 | 8
1246 | BLD-2248-D-FFPH¦A¦9¦C | FIRE FIGHTING SYSTEM | 2828 | P&A 3 Coat Painting On 150Mm Dia Ms Pipe | 12-12-2019 | 17-03-2022 | M | 25 | 2020 | 8
1247 | BLD-2248-D-FFPH¦A¦9¦D | FIRE FIGHTING SYSTEM | 2829 | P&A 3 Coat Painting On 100Mm Dia Ms Pipe | 12-12-2019 | 17-03-2022 | M | 8 | 2020 | 8
1248 | BLD-2248-D-FFPH¦A¦9¦E | FIRE FIGHTING SYSTEM | 2830 | P&A 3 Coat Painting On 80Mm Dia Ms Pipe | 12-12-2019 | 17-03-2022 | M | 16 | 2020 | 8
1249 | BLD-2248-D-FFPH¦A¦9¦F | FIRE FIGHTING SYSTEM | 2831 | P&A 3 Coat Painting On 25Mm Dia Ms Pipe | 12-12-2019 | 17-03-2022 | M | 15 | 2020 | 8
1250 | BLD-2248-D-FFPH¦A¦10¦A | FIRE FIGHTING SYSTEM | 2832 | P&F CI Y Strainer 200Mm Dia | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
1251 | BLD-2248-D-FFPH¦A¦11 | FIRE FIGHTING SYSTEM | 2833 | P&S Ss Fire Brigade Suction Hose Cplng | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
1252 | BLD-2248-D-FFPH¦A¦12 | FIRE FIGHTING SYSTEM | 2834 | P&S Ss Fire Brigade Connection | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
1253 | BLD-2248-D-FFPH¦A¦13¦A | FIRE FIGHTING SYSTEM | 2835 | P&F CI Foot Valve 200Mm Dia | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
1254 | BLD-2248-D-FFPH¦A¦14 | FIRE FIGHTING SYSTEM | 2836 | P&F Elc Operated Dual Typ Pr Switches | 12-12-2019 | 17-03-2022 | EA | 14 | 2020 | 8
1255 | BLD-2248-D-FFPH¦A¦15¦A | FIRE FIGHTING SYSTEM | 2837 | P&F Ctrl Valve Wth Auto Alrm Gong 150Mm | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
1256 | BLD-2248-D-FFPH¦A¦16 | FIRE FIGHTING SYSTEM | 2838 | P&F Level Switch Wth Var Diffrnt | 12-12-2019 | 17-03-2022 | SET | 2 | 2020 | 8
1257 | BLD-2248-D-FFPH¦A¦17 | FIRE FIGHTING SYSTEM | 2839 | 0 | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
1258 | BLD-2248-D-FFPH¦A¦18¦A | FIRE FIGHTING SYSTEM | 2840 | P&I CI Body 200 Nb Sluice Valve | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
1259 | BLD-2248-D-FFPH¦A¦19¦A | FIRE FIGHTING SYSTEM | 2841 | P&I CI Body Nrv 150 Nb | 12-12-2019 | 17-03-2022 | EA | 12 | 2020 | 8
1260 | BLD-2248-D-FFPH¦A¦19¦B | FIRE FIGHTING SYSTEM | 2842 | P&I CI Body Nrv 80 Nb | 12-12-2019 | 17-03-2022 | EA | 4 | 2020 | 8
1261 | BLD-2248-D-FFPH¦A¦20¦A | FIRE FIGHTING SYSTEM | 2843 | P&F CI Body Btrfly Valve 200Nb | 12-12-2019 | 17-03-2022 | EA | 4 | 2020 | 8
1262 | BLD-2248-D-FFPH¦A¦20¦B | FIRE FIGHTING SYSTEM | 2844 | P&F CI Body Btrfly Valve 150Nb | 12-12-2019 | 17-03-2022 | EA | 20 | 2020 | 8
1263 | BLD-2248-D-FFPH¦A¦20¦C | FIRE FIGHTING SYSTEM | 2845 | P&F CI Body Btrfly Valve 100Nb | 12-12-2019 | 17-03-2022 | EA | 4 | 2020 | 8
1264 | BLD-2248-D-FFPH¦A¦20¦D | FIRE FIGHTING SYSTEM | 2846 | P&F CI Body Btrfly Valve 80Nb | 12-12-2019 | 17-03-2022 | EA | 8 | 2020 | 8
1265 | BLD-2248-D-FFPH¦A¦21¦A | FIRE FIGHTING SYSTEM | 2847 | P&I 25Nb Gm Ball Valve | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
1266 | BLD-2248-D-FFPH¦A¦22¦A | FIRE FIGHTING SYSTEM | 2848 | P&F Dbl Flange Rubber Bellow 200Nb | 12-12-2019 | 17-03-2022 | EA | 3 | 2020 | 8
1267 | BLD-2248-D-FFPH¦A¦22¦B | FIRE FIGHTING SYSTEM | 2849 | P&F Dbl Flange Rubber Bellow 150Nb | 12-12-2019 | 17-03-2022 | EA | 6 | 2020 | 8
1268 | BLD-2248-D-FFPH¦A¦22¦C | FIRE FIGHTING SYSTEM | 2850 | P&F Dbl Flange Rubber Bellow 100Nb | 12-12-2019 | 17-03-2022 | EA | 4 | 2020 | 8
1269 | BLD-2248-D-FFPH¦A¦22¦D | FIRE FIGHTING SYSTEM | 2851 | P&F Dbl Flange Rubber Bellow 80Nb | 12-12-2019 | 17-03-2022 | EA | 8 | 2020 | 8
1270 | BLD-2248-D-FFPH¦A¦23¦A | FIRE FIGHTING SYSTEM | 2852 | P&I Vibration Elimination Pad Typ A | 12-12-2019 | 17-03-2022 | EA | 4 | 2020 | 8
1271 | BLD-2248-D-FFPH¦A¦23¦B | FIRE FIGHTING SYSTEM | 2853 | P&I Vibration Elimination Pad Typ B | 12-12-2019 | 17-03-2022 | EA | 3 | 2020 | 8
1272 | BLD-2248-D-FFMCC¦A¦24 | FIRE FIGHTING SYSTEM | 2854 | SITC of Mcc For Fire Protection Sys | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
1273 | BLD-2248-D-FFHYDS¦B¦1¦A | FIRE FIGHTING SYSTEM | 2855 | Pl&T of 150Nb C Cls Ms Erw Pipes | 12-12-2019 | 17-03-2022 | M | 1070 | 2020 | 8
1274 | BLD-2248-D-FFHYDS¦B¦1¦B | FIRE FIGHTING SYSTEM | 2856 | Pl&T of 80Nb C Cls Ms Erw Pipes | 12-12-2019 | 17-03-2022 | M | 1600 | 2020 | 8
1275 | BLD-2248-D-FFHYDS¦B¦1¦C | FIRE FIGHTING SYSTEM | 2857 | Pl&T of 25Nb C Cls Ms Erw Pipes | 12-12-2019 | 17-03-2022 | M | 100 | 2020 | 8
1276 | BLD-2248-D-FFHYDS¦B¦2¦A | FIRE FIGHTING SYSTEM | 2858 | P&A 3 Coat of Painting On 150Nb Ms Pipe | 12-12-2019 | 17-03-2022 | M | 1070 | 2020 | 8
1277 | BLD-2248-D-FFHYDS¦B¦2¦B | FIRE FIGHTING SYSTEM | 2859 | P&A 3 Coat of Painting On 80Nb Ms Pipe | 12-12-2019 | 17-03-2022 | M | 1600 | 2020 | 8
1278 | BLD-2248-D-FFHYDS¦B¦2¦C | FIRE FIGHTING SYSTEM | 2860 | P&A 3 Coat of Painting On 25Nb Ms Pipe | 12-12-2019 | 17-03-2022 | M | 100 | 2020 | 8
1279 | BLD-2248-D-FFHYDS¦B¦3 | FIRE FIGHTING SYSTEM | 2861 | P&F Ss Single Landing Valve 63Mm Dia | 12-12-2019 | 17-03-2022 | EA | 98 | 2020 | 8
1280 | BLD-2248-D-FFHYDS¦B¦4 | FIRE FIGHTING SYSTEM | 2862 | P&F Rrl Hose | 12-12-2019 | 17-03-2022 | EA | 196 | 2020 | 8
1281 | BLD-2248-D-FFHYDS¦B¦5 | FIRE FIGHTING SYSTEM | 2863 | P&F Gm Short Branch Pipe | 12-12-2019 | 17-03-2022 | EA | 98 | 2020 | 8
1282 | BLD-2248-D-FFHYDS¦B¦6 | FIRE FIGHTING SYSTEM | 2864 | P&F Fully Glazed Fhc 2000X1000Mm | 12-12-2019 | 17-03-2022 | EA | 70 | 2020 | 8
1283 | BLD-2248-D-FFHYDS¦B¦7 | FIRE FIGHTING SYSTEM | 2865 | P&F Ms Hose Cabinet 750X610X255Mm | 12-12-2019 | 17-03-2022 | EA | 28 | 2020 | 8
1284 | BLD-2248-D-FFHYDS¦B¦8 | FIRE FIGHTING SYSTEM | 2866 | P&F Swing Type Hose Reel Drum 36 Mtrs | 12-12-2019 | 17-03-2022 | EA | 70 | 2020 | 8
1285 | BLD-2248-D-FFHYDS¦B¦9 | FIRE FIGHTING SYSTEM | 2867 | SITC of 25Mm Single Actng Arv | 12-12-2019 | 17-03-2022 | EA | 6 | 2020 | 8
1286 | BLD-2248-D-FFHYDS¦B¦10¦A | FIRE FIGHTING SYSTEM | 2868 | P&F CI Body Btrfly Valve 80Nb | 12-12-2019 | 17-03-2022 | EA | 98 | 2020 | 8
1287 | BLD-2248-D-FFHYDS¦B¦10¦B | FIRE FIGHTING SYSTEM | 2869 | P&F CI Body Btrfly Valve 150Nb | 12-12-2019 | 17-03-2022 | EA | 12 | 2020 | 8
1288 | BLD-2248-D-FFHYDS¦B¦11¦A | FIRE FIGHTING SYSTEM | 2870 | P&I CI Body Nrv 150 Nb | 12-12-2019 | 17-03-2022 | EA | 6 | 2020 | 8
1289 | BLD-2248-D-FFHYDS¦B¦12 | FIRE FIGHTING SYSTEM | 2871 | P&F Dial Typ 100Mm Dia Pr Gauge | 12-12-2019 | 17-03-2022 | EA | 70 | 2020 | 8
1290 | BLD-2248-D-FFHYDS¦B¦13¦A | FIRE FIGHTING SYSTEM | 2872 | Pl&T of 150Nb C Cls Ms Erw Ug Pipes | 12-12-2019 | 17-03-2022 | M | 650 | 2020 | 8
1291 | BLD-2248-D-FFHYDS¦B¦13¦B | FIRE FIGHTING SYSTEM | 2873 | Pl&T of 150Nb C Cls Ms Erw Ug Pipes | 12-12-2019 | 17-03-2022 | M | 5 | 2020 | 8
1292 | BLD-2248-D-FFHYDS¦B¦13¦C | FIRE FIGHTING SYSTEM | 2874 | Pl&T of 150Nb C Cls Ms Erw Ug Pipes | 12-12-2019 | 17-03-2022 | M | 20 | 2020 | 8
1293 | BLD-2248-D-FFHYDS¦B¦14¦A | FIRE FIGHTING SYSTEM | 2875 | P&F CI Body Btrfly Valve 150Nb | 12-12-2019 | 17-03-2022 | EA | 3 | 2020 | 8
1294 | BLD-2248-D-FFHYDS¦B¦14¦B | FIRE FIGHTING SYSTEM | 2876 | P&F CI Body Btrfly Valve 80Nb | 12-12-2019 | 17-03-2022 | EA | 9 | 2020 | 8
1295 | BLD-2248-D-FFHYDS¦B¦14 | FIRE FIGHTING SYSTEM | 2877 | P&F Ss Single Ext Hydrant Valve 63Mm Dia | 12-12-2019 | 17-03-2022 | EA | 9 | 2020 | 8
1296 | BLD-2248-D-FFHYDS¦B¦15 | FIRE FIGHTING SYSTEM | 2878 | P&F Rrl Hose | 12-12-2019 | 17-03-2022 | EA | 18 | 2020 | 8
1297 | BLD-2248-D-FFHYDS¦B¦16 | FIRE FIGHTING SYSTEM | 2879 | P&F Gm Short Branch Pipe | 12-12-2019 | 17-03-2022 | EA | 9 | 2020 | 8
1298 | BLD-2248-D-FFHYDS¦B¦17 | FIRE FIGHTING SYSTEM | 2880 | P&F Ms Hose Cabinet 750X610X255Mm | 12-12-2019 | 17-03-2022 | EA | 9 | 2020 | 8
1299 | BLD-2248-D-FFHYDS¦B¦18 | FIRE FIGHTING SYSTEM | 2881 | P&F Ss Fire Brigade Connection | 12-12-2019 | 17-03-2022 | SET | 6 | 2020 | 8
1300 | BLD-2248-D-FFHYDS¦B¦19¦A | FIRE FIGHTING SYSTEM | 2882 | 0 | 12-12-2019 | 17-03-2022 | M | 40 | 2020 | 8
1301 | BLD-2248-D-FFHYDS¦B¦20¦A | FIRE FIGHTING SYSTEM | 2883 | P&C Valve Chamber 1000X1000X1000Mm | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
1302 | BLD-2248-D-FFSPRS¦C¦1¦A | FIRE FIGHTING SYSTEM | 2884 | Pl&T of 25Nb C Cls Ms Pipes | 12-12-2019 | 17-03-2022 | M | 11250 | 2020 | 8
1303 | BLD-2248-D-FFSPRS¦C¦1¦B | FIRE FIGHTING SYSTEM | 2885 | Pl&T of 32Nb C Cls Ms Pipes | 12-12-2019 | 17-03-2022 | M | 1405 | 2020 | 8
1304 | BLD-2248-D-FFSPRS¦C¦1¦C | FIRE FIGHTING SYSTEM | 2886 | Pl&T of 40Nb C Cls Ms Pipes | 12-12-2019 | 17-03-2022 | M | 4175 | 2020 | 8
1305 | BLD-2248-D-FFSPRS¦C¦1¦D | FIRE FIGHTING SYSTEM | 2887 | Pl&T of 50Nb C Cls Ms Pipes | 12-12-2019 | 17-03-2022 | M | 1870 | 2020 | 8
1306 | BLD-2248-D-FFSPRS¦C¦1¦E | FIRE FIGHTING SYSTEM | 2888 | Pl&T of 65Nb C Cls Ms Pipes | 12-12-2019 | 17-03-2022 | M | 4478 | 2020 | 8
1307 | BLD-2248-D-FFSPRS¦C¦1¦F | FIRE FIGHTING SYSTEM | 2889 | Pl&T of 80Nb C Cls Ms Pipes | 12-12-2019 | 17-03-2022 | M | 1770 | 2020 | 8
1308 | BLD-2248-D-FFSPRS¦C¦1¦G | FIRE FIGHTING SYSTEM | 2890 | Pl&T of 100Nb C Cls Ms Pipes | 12-12-2019 | 17-03-2022 | M | 735 | 2020 | 8
1309 | BLD-2248-D-FFSPRS¦C¦1¦H | FIRE FIGHTING SYSTEM | 2891 | Pl&T of 150Nb C Cls Ms Pipes | 12-12-2019 | 17-03-2022 | M | 2000 | 2020 | 8
1310 | BLD-2248-D-FFSPRS¦C¦2¦A | FIRE FIGHTING SYSTEM | 2892 | P&A 3 Coat of Painting On 25Nb Ms Pipe | 12-12-2019 | 17-03-2022 | M | 11250 | 2020 | 8
1311 | BLD-2248-D-FFSPRS¦C¦2¦B | FIRE FIGHTING SYSTEM | 2893 | P&A 3 Coat of Painting On 32Nb Ms Pipe | 12-12-2019 | 17-03-2022 | M | 1405 | 2020 | 8
1312 | BLD-2248-D-FFSPRS¦C¦2¦C | FIRE FIGHTING SYSTEM | 2894 | P&A 3 Coat of Painting On 40Nb Ms Pipe | 12-12-2019 | 17-03-2022 | M | 4175 | 2020 | 8
1313 | BLD-2248-D-FFSPRS¦C¦2¦D | FIRE FIGHTING SYSTEM | 2895 | P&A 3 Coat of Painting On 50Nb Ms Pipe | 12-12-2019 | 17-03-2022 | M | 1870 | 2020 | 8
1314 | BLD-2248-D-FFSPRS¦C¦2¦E | FIRE FIGHTING SYSTEM | 2896 | P&A 3 Coat of Painting On 65Nb Ms Pipe | 12-12-2019 | 17-03-2022 | M | 4478 | 2020 | 8
1315 | BLD-2248-D-FFSPRS¦C¦2¦F | FIRE FIGHTING SYSTEM | 2897 | P&A 3 Coat of Painting On 80Nb Ms Pipe | 12-12-2019 | 17-03-2022 | M | 1770 | 2020 | 8
1316 | BLD-2248-D-FFSPRS¦C¦2¦G | FIRE FIGHTING SYSTEM | 2898 | P&A 3 Coat of Painting On 100Nb Ms Pipe | 12-12-2019 | 17-03-2022 | M | 735 | 2020 | 8
1317 | BLD-2248-D-FFSPRS¦C¦2¦H | FIRE FIGHTING SYSTEM | 2899 | P&A 3 Coat of Painting On 150Nb Ms Pipe | 12-12-2019 | 17-03-2022 | M | 2000 | 2020 | 8
1318 | BLD-2248-D-FFSPRS¦C¦3¦A | FIRE FIGHTING SYSTEM | 2900 | P&F CI Btrfly Valve 100Mm Dia | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
1319 | BLD-2248-D-FFSPRS¦C¦3¦B | FIRE FIGHTING SYSTEM | 2901 | P&F CI Btrfly Valve 150Mm Dia | 12-12-2019 | 17-03-2022 | EA | 152 | 2020 | 8
1320 | BLD-2248-D-FFSPRS¦C¦4¦A | FIRE FIGHTING SYSTEM | 2902 | P&F CI Nrv 150Mm Dia | 12-12-2019 | 17-03-2022 | EA | 12 | 2020 | 8
1321 | BLD-2248-D-FFSPRS¦C¦5¦A | FIRE FIGHTING SYSTEM | 2903 | P&F Upright Sprinkler | 12-12-2019 | 17-03-2022 | EA | 5822 | 2020 | 8
1322 | BLD-2248-D-FFSPRS¦C¦5¦B | FIRE FIGHTING SYSTEM | 2904 | P&F Side Wall Sprinkler | 12-12-2019 | 17-03-2022 | EA | 157 | 2020 | 8
1323 | BLD-2248-D-FFSPRS¦C¦5¦C | FIRE FIGHTING SYSTEM | 2905 | P&F Pendent 79 C Sprinkler | 12-12-2019 | 17-03-2022 | EA | 31 | 2020 | 8
1324 | BLD-2248-D-FFSPRS¦C¦5¦D | FIRE FIGHTING SYSTEM | 2906 | P&F Pendent 68 C Sprinkler | 12-12-2019 | 17-03-2022 | EA | 96 | 2020 | 8
1325 | BLD-2248-D-FFSPRS¦C¦6¦A | FIRE FIGHTING SYSTEM | 2907 | P&F Flow Switch 150Mm Dia | 12-12-2019 | 17-03-2022 | EA | 69 | 2020 | 8
1326 | BLD-2248-D-FFSPRS¦C¦6¦B | FIRE FIGHTING SYSTEM | 2908 | P&F Flow Switch 100Mm Dia | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
1327 | BLD-2248-D-FFSPRS¦C¦7¦A | FIRE FIGHTING SYSTEM | 2909 | P&F Flx Sprinkler Pipe 1000Mm | 12-12-2019 | 17-03-2022 | EA | 45 | 2020 | 8
1328 | BLD-2248-D-FFSPRS¦C¦7¦B | FIRE FIGHTING SYSTEM | 2910 | P&F Flx Sprinkler Pipe 1200Mm | 12-12-2019 | 17-03-2022 | EA | 40 | 2020 | 8
1329 | BLD-2248-D-FFSPRS¦C¦7¦C | FIRE FIGHTING SYSTEM | 2911 | P&F Flx Sprinkler Pipe 1500Mm | 12-12-2019 | 17-03-2022 | EA | 11 | 2020 | 8
1330 | BLD-2248-D-FFSPRS¦C¦8 | FIRE FIGHTING SYSTEM | 2912 | P&F Gm Arv 25Mm Dia | 12-12-2019 | 17-03-2022 | EA | 6 | 2020 | 8
1331 | BLD-2248-D-FFSPRS¦C¦9 | FIRE FIGHTING SYSTEM | 2913 | P&F Pr Gauge 100Mm Dia | 12-12-2019 | 17-03-2022 | EA | 6 | 2020 | 8
1332 | BLD-2248-D-FFSPRS¦C¦10 | FIRE FIGHTING SYSTEM | 2914 | P&F Alarm Gong | 12-12-2019 | 17-03-2022 | EA | 6 | 2020 | 8
1333 | BLD-2248-D-FFSPRS¦C¦11¦A | FIRE FIGHTING SYSTEM | 2915 | P&F Test Valve With Sight Glass 50Mm Dia | 12-12-2019 | 17-03-2022 | EA | 70 | 2020 | 8
1334 | BLD-2248-D-FFSPRS¦C¦12 | FIRE FIGHTING SYSTEM | 2916 | P&F Ss Fire Brigade 4 Way Connection | 12-12-2019 | 17-03-2022 | SET | 6 | 2020 | 8
1335 | BLD-2248-D-FFEXTNG¦D¦A¦1 | FIRE FIGHTING SYSTEM | 2917 | P&I Abc Type Extngshr 6Kg Cap | 12-12-2019 | 17-03-2022 | EA | 70 | 2020 | 8
1336 | BLD-2248-D-FFEXTNG¦D¦A¦2 | FIRE FIGHTING SYSTEM | 2918 | P&I of Water Co2 Extngshr 9Ltr Cap | 12-12-2019 | 17-03-2022 | EA | 70 | 2020 | 8
1337 | BLD-2248-D-FFEXTNG¦D¦A¦3 | FIRE FIGHTING SYSTEM | 2919 | P&I of Co2 Extngshr 4.5 Kg Cap | 12-12-2019 | 17-03-2022 | EA | 70 | 2020 | 8
1338 | BLD-2248-D-FFEXTNG¦D¦A¦4 | FIRE FIGHTING SYSTEM | 2920 | P&I Foam Type Extngshr 9 Ltr Cap | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
1339 | BLD-2248-D-FDA¦A¦1 | FIRE ALARM DETECTION SYSTEM | 2921 | SITC of Ul Listed 10 Loop Fda Panel | 12-12-2019 | 17-03-2022 | SET | 2 | 2020 | 8
1340 | BLD-2248-D-FDA¦A¦2 | FIRE ALARM DETECTION SYSTEM | 2922 | SITC of Control Module | 12-12-2019 | 17-03-2022 | EA | 94 | 2020 | 8
1341 | BLD-2248-D-FDA¦A¦3 | FIRE ALARM DETECTION SYSTEM | 2923 | SITC of Relay Modules | 12-12-2019 | 17-03-2022 | EA | 47 | 2020 | 8
1342 | BLD-2248-D-FDA¦A¦4 | FIRE ALARM DETECTION SYSTEM | 2924 | SITC of Monitor Module | 12-12-2019 | 17-03-2022 | EA | 47 | 2020 | 8
1343 | BLD-2248-D-FDA¦A¦5 | FIRE ALARM DETECTION SYSTEM | 2925 | SITC of Issolator Module | 12-12-2019 | 17-03-2022 | EA | 120 | 2020 | 8
1344 | BLD-2248-D-FDA¦A¦6 | FIRE ALARM DETECTION SYSTEM | 2926 | SITC of Repeater Panel | 12-12-2019 | 17-03-2022 | SET | 42 | 2020 | 8
1345 | BLD-2248-D-FDA¦A¦7 | FIRE ALARM DETECTION SYSTEM | 2927 | SITC of Network Control Station | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
1346 | BLD-2248-D-FDA¦A¦8 | FIRE ALARM DETECTION SYSTEM | 2928 | SITC of Graphics Display Unit | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
1347 | BLD-2248-D-FDA¦A¦9 | FIRE ALARM DETECTION SYSTEM | 2929 | SITC of Adv Cloud Based Software | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
1348 | BLD-2248-D-FDA¦A¦10 | FIRE ALARM DETECTION SYSTEM | 2930 | SITC of Multi Sensor Smoke+Deat Detector | 12-12-2019 | 17-03-2022 | EA | 1200 | 2020 | 8
1349 | BLD-2248-D-FDA¦A¦11 | FIRE ALARM DETECTION SYSTEM | 2931 | SITC of Heat Detector | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
1350 | BLD-2248-D-FDA¦A¦12 | FIRE ALARM DETECTION SYSTEM | 2932 | SITC of Manual Call Point | 12-12-2019 | 17-03-2022 | EA | 94 | 2020 | 8
1351 | BLD-2248-D-FDA¦A¦13 | FIRE ALARM DETECTION SYSTEM | 2933 | SITC of Directional Sounder | 12-12-2019 | 17-03-2022 | EA | 94 | 2020 | 8
1352 | BLD-2248-D-FDA¦A¦14 | FIRE ALARM DETECTION SYSTEM | 2934 | SITC of Telephone Jack | 12-12-2019 | 17-03-2022 | EA | 94 | 2020 | 8
1353 | BLD-2248-D-FDA¦A¦15 | FIRE ALARM DETECTION SYSTEM | 2935 | SITC of Telephone Receiver | 12-12-2019 | 17-03-2022 | EA | 94 | 2020 | 8
1354 | BLD-2248-D-FDA¦A¦16 | FIRE ALARM DETECTION SYSTEM | 2936 | SITC of Telephone Module | 12-12-2019 | 17-03-2022 | EA | 94 | 2020 | 8
1355 | BLD-2248-D-FDA¦A¦17 | FIRE ALARM DETECTION SYSTEM | 2937 | SITC of 2W Ceiling Speakers | 12-12-2019 | 17-03-2022 | EA | 94 | 2020 | 8
1356 | BLD-2248-D-FDA¦A¦18¦18'1 | FIRE ALARM DETECTION SYSTEM | 2938 | SITC of 1.5Sqmmx 2C Frls Cable For Fda | 12-12-2019 | 17-03-2022 | M | 15000 | 2020 | 8
1357 | BLD-2248-D-FDA¦A¦18¦18'2 | FIRE ALARM DETECTION SYSTEM | 2939 | SITC of 1Sqmmx 2C Flxbl Cable For Power | 12-12-2019 | 17-03-2022 | M | 8000 | 2020 | 8
1358 | BLD-2248-D-FDA¦A¦19 | FIRE ALARM DETECTION SYSTEM | 2940 | SITC of 20/25/32 Mm Dia Conduit | 12-12-2019 | 17-03-2022 | M | 7500 | 2020 | 8
1359 | BLD-2248-D-FDA¦A¦20 | FIRE ALARM DETECTION SYSTEM | 2941 | SITC of 24V Dc Power Supply Unit | 12-12-2019 | 17-03-2022 | EA | 30 | 2020 | 8
1360 | BLD-2248-D-FDA¦A¦21 | FIRE ALARM DETECTION SYSTEM | 2942 | SITC of Junction Box | 12-12-2019 | 17-03-2022 | EA | 2340 | 2020 | 8
1361 | BLD-2248-D-CCTV¦A¦1 | CCTC SERVEILLANCE SYSTEM | 2943 | SITC of Ip Fixed Dome Camera | 12-12-2019 | 17-03-2022 | EA | 0 | 2020 | 8
1362 | BLD-2248-D-CCTV¦A¦2 | CCTC SERVEILLANCE SYSTEM | 2944 | SITC of Ip Fixed Box Camera | 12-12-2019 | 17-03-2022 | EA | 25 | 2020 | 8
1363 | BLD-2248-D-CCTV¦A¦3 | CCTC SERVEILLANCE SYSTEM | 2945 | SITC of Ip Ptz Camera | 12-12-2019 | 17-03-2022 | EA | 4 | 2020 | 8
1364 | BLD-2248-D-CCTV¦A¦4 | CCTC SERVEILLANCE SYSTEM | 2946 | SITC Power Supply Unit For Ptz | 12-12-2019 | 17-03-2022 | EA | 4 | 2020 | 8
1365 | BLD-2248-D-CCTV¦A¦5 | CCTC SERVEILLANCE SYSTEM | 2947 | SITC of Network Attached Storage | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
1366 | BLD-2248-D-CCTV¦A¦6 | CCTC SERVEILLANCE SYSTEM | 2948 | SITC of Workstation With Licence | 12-12-2019 | 17-03-2022 | EA | 3 | 2020 | 8
1367 | BLD-2248-D-CCTV¦A¦7 | CCTC SERVEILLANCE SYSTEM | 2949 | SITC of Keybrd & Joystck For Ptz | 12-12-2019 | 17-03-2022 | EA | 4 | 2020 | 8
1368 | BLD-2248-D-CCTV¦A¦8 | CCTC SERVEILLANCE SYSTEM | 2950 | SITC of 49" Led Color Panel | 12-12-2019 | 17-03-2022 | EA | 4 | 2020 | 8
1369 | BLD-2248-D-CCTV¦A¦9 | CCTC SERVEILLANCE SYSTEM | 2951 | S&I of 6Mtr Ms Pole For Ptz | 12-12-2019 | 17-03-2022 | EA | 4 | 2020 | 8
1370 | BLD-2248-D-CCTV¦A¦10 | CCTC SERVEILLANCE SYSTEM | 2952 | S&I of 4Mtr Ms Pole For Ptz | 12-12-2019 | 17-03-2022 | EA | 11 | 2020 | 8
1371 | BLD-2248-D-CCTV¦A¦11 | CCTC SERVEILLANCE SYSTEM | 2953 | SITC of Ethernet Smart Switch 8 Port | 12-12-2019 | 17-03-2022 | EA | 15 | 2020 | 8
1372 | BLD-2248-D-CCTV¦A¦12 | CCTC SERVEILLANCE SYSTEM | 2954 | SITC of Poe Lyr Ii Ethernet Swch 24 Port | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
1373 | BLD-2248-D-CCTV¦A¦13 | CCTC SERVEILLANCE SYSTEM | 2955 | SITC of 19" 42U Rack | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
1374 | BLD-2248-D-CCTV¦A¦14 | CCTC SERVEILLANCE SYSTEM | 2956 | SITC of Ip65/Ip67 Outdr 6U Rack | 12-12-2019 | 17-03-2022 | EA | 11 | 2020 | 8
1375 | BLD-2248-D-CCTV¦A¦15 | CCTC SERVEILLANCE SYSTEM | 2957 | SITC of Cat 6A Utp Cable | 12-12-2019 | 17-03-2022 | M | 600 | 2020 | 8
1376 | BLD-2248-D-CCTV¦A¦16 | CCTC SERVEILLANCE SYSTEM | 2958 | SITC of 6C Sm Fiber Optic Cable | 12-12-2019 | 17-03-2022 | M | 2000 | 2020 | 8
1377 | BLD-2248-D-CCTV¦A¦17 | CCTC SERVEILLANCE SYSTEM | 2959 | SITC of 3X1.5Sqmm Power Cable | 12-12-2019 | 17-03-2022 | M | 600 | 2020 | 8
1378 | BLD-2248-D-CCTV¦A¦18 | CCTC SERVEILLANCE SYSTEM | 2960 | SITC of Other Network Equip | 12-12-2019 | 17-03-2022 | LOT | 1 | 2020 | 8
1379 | BLD-2248-D-CCTV¦A¦19 | CCTC SERVEILLANCE SYSTEM | 2961 | S&L 40Mm Dia Hdpe Conduit | 12-12-2019 | 17-03-2022 | M | 2000 | 2020 | 8
1380 | BLD-2248-D-CCTV¦A¦20 | CCTC SERVEILLANCE SYSTEM | 2962 | S&L 3/4" PVC Conduit | 12-12-2019 | 17-03-2022 | M | 500 | 2020 | 8
1381 | BLD-2248-D-UVSS¦A¦1 | UNDER VEHICLE SCANNER SYSTEM | 2963 | Supply of Uvss Unit | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
1382 | BLD-2248-D-UVSS¦A¦2 | UNDER VEHICLE SCANNER SYSTEM | 2964 | Supply of Central Montrng Console | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
1383 | BLD-2248-D-UVSS¦B¦1 | UNDER VEHICLE SCANNER SYSTEM | 2965 | Civil & Struc Work For Uvss | 12-12-2019 | 17-03-2022 | JOB | 2 | 2020 | 8
1384 | BLD-2248-D-UVSS¦B¦2 | UNDER VEHICLE SCANNER SYSTEM | 2966 | ITC of Uvss & Training | 12-12-2019 | 17-03-2022 | EA | 2 | 2020 | 8
1385 | BLD-2248-D-STP¦A¦1¦1'1 | SEWAGE TREATMENT PLANT (STP) | 2967 | SITC of Bar Screen | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
1386 | BLD-2248-D-STP¦A¦2 | SEWAGE TREATMENT PLANT (STP) | 2968 | Const of Grease Trap | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
1387 | BLD-2248-D-STP¦A¦3 | SEWAGE TREATMENT PLANT (STP) | 2969 | Supply of Ms Hot Dip GI Puddle Flange | 12-12-2019 | 17-03-2022 | LOT | 1 | 2020 | 8
1388 | BLD-2248-D-STP¦A¦4 | SEWAGE TREATMENT PLANT (STP) | 2970 | Supply of Plastic Manhole Step | 12-12-2019 | 17-03-2022 | LOT | 1 | 2020 | 8
1389 | BLD-2248-D-STP¦ | SEWAGE TREATMENT PLANT (STP) | 2971 | SITC of CI Mh Cover Wth Frame 600X900 | 12-12-2019 | 17-03-2022 | LOT | 1 | 2020 | 8
1390 | BLD-2248-D-STP¦A¦6 | SEWAGE TREATMENT PLANT (STP) | 2972 | Supply of Vent Pipe 100Mm Dia | 12-12-2019 | 17-03-2022 | LOT | 1 | 2020 | 8
1391 | BLD-2248-D-STP¦A¦7 | SEWAGE TREATMENT PLANT (STP) | 2973 | SITC of Elec Type Level Indicator | 12-12-2019 | 17-03-2022 | LOT | 1 | 2020 | 8
1392 | BLD-2248-D-STP¦A¦8 | SEWAGE TREATMENT PLANT (STP) | 2974 | SITC of Sight Tube Wth Isso Vlv | 12-12-2019 | 17-03-2022 | LOT | 1 | 2020 | 8
1393 | BLD-2248-D-STP¦A¦9¦9'1 | SEWAGE TREATMENT PLANT (STP) | 2975 | SITC of Submersible Sewage Pump | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
1394 | BLD-2248-D-STP¦A¦9¦9'2 | SEWAGE TREATMENT PLANT (STP) | 2976 | SITC of Sludge Disposal Pump | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
1395 | BLD-2248-D-STP¦A¦9¦9'3 | SEWAGE TREATMENT PLANT (STP) | 2977 | SITC of Plant Room Sump Pump | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
1396 | BLD-2248-D-STP¦A¦9¦9'4 | SEWAGE TREATMENT PLANT (STP) | 2978 | SITC of Irrigation Pump | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
1397 | BLD-2248-D-STP¦A¦9¦9'5 | SEWAGE TREATMENT PLANT (STP) | 2979 | SITC of Recirculation Pump | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
1398 | BLD-2248-D-STP¦A¦9¦9'6 | SEWAGE TREATMENT PLANT (STP) | 2980 | SITC of Anoxic Tank Agitator | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
1399 | BLD-2248-D-STP¦A¦10¦10'1 | SEWAGE TREATMENT PLANT (STP) | 2981 | SITC of Twin Type Rotary Air Blower | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
1400 | BLD-2248-D-STP¦A¦10¦10'2 | SEWAGE TREATMENT PLANT (STP) | 2982 | SITC of Air Piping | 12-12-2019 | 17-03-2022 | LOT | 1 | 2020 | 8
1401 | BLD-2248-D-STP¦A¦10¦10'3 | SEWAGE TREATMENT PLANT (STP) | 2983 | SITC of Non Clog Air Dispersion System | 12-12-2019 | 17-03-2022 | LOT | 1 | 2020 | 8
1402 | BLD-2248-D-STP¦A¦10¦10'4 | SEWAGE TREATMENT PLANT (STP) | 2984 | SITC of Brnz Vlv & Air Dispersion Grid | 12-12-2019 | 17-03-2022 | LOT | 1 | 2020 | 8
1403 | BLD-2248-D-STP¦A¦11 | SEWAGE TREATMENT PLANT (STP) | 2985 | P&F All Piping & Isolation Ctrl Vlvs | 12-12-2019 | 17-03-2022 | JOB | 1 | 2020 | 8
1404 | BLD-2248-D-STP¦A¦12 | SEWAGE TREATMENT PLANT (STP) | 2986 | SITC of Mbbr Media | 12-12-2019 | 17-03-2022 | LOT | 1 | 2020 | 8
1405 | BLD-2248-D-STP¦A¦13 | SEWAGE TREATMENT PLANT (STP) | 2987 | SITC of Tube Setler Tank | 12-12-2019 | 17-03-2022 | LOT | 1 | 2020 | 8
1406 | BLD-2248-D-STP¦A¦14¦14'1 | SEWAGE TREATMENT PLANT (STP) | 2988 | SITC of Uv Unit Flow Rate 2.5Lps Ifl | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
1407 | BLD-2248-D-STP¦A¦14¦14'2 | SEWAGE TREATMENT PLANT (STP) | 2989 | SITC of Uv Unit Flow Rate 12Lps Fwtl | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
1408 | BLD-2248-D-STP¦A¦14¦14'3 | SEWAGE TREATMENT PLANT (STP) | 2990 | SITC of Uv Unit Flow Rate 12Lps Mwtl | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
1409 | BLD-2248-D-STP¦A¦14¦14'4 | SEWAGE TREATMENT PLANT (STP) | 2991 | Ft&C of Stp | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
1410 | BLD-2248-D-STP¦A¦15¦A'1 | SEWAGE TREATMENT PLANT (STP) | 2992 | SITC of Flshng Water Trnsfr Pump 110M H | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
1411 | BLD-2248-D-STP¦A¦15¦A'2 | SEWAGE TREATMENT PLANT (STP) | 2993 | SITC of Flshng Water Trnsfr Pump 75M H | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
1412 | BLD-2248-D-STP¦A¦15¦B'1 | SEWAGE TREATMENT PLANT (STP) | 2994 | SITC of Nonclog Hrznt Water Pump 30M H | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
1413 | BLD-2248-D-STP¦A¦15¦B'2 | SEWAGE TREATMENT PLANT (STP) | 2995 | SITC of Nonclog Hrznt Water Pump 10M H | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
1414 | BLD-2248-D-STP¦A¦15¦B'3 | SEWAGE TREATMENT PLANT (STP) | 2996 | SITC of Nonclog Hrznt Water Pump 30M H | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
1415 | BLD-2248-D-STP¦A¦16 | SEWAGE TREATMENT PLANT (STP) | 2997 | P&L GI Pipe Hd Wth All Fittings | 12-12-2019 | 17-03-2022 | LOT | 1 | 2020 | 8
1416 | BLD-2248-D-STP¦A¦17 | SEWAGE TREATMENT PLANT (STP) | 2998 | P&F Ball Vlv & Btrfly Vlv of Rqd Sizes | 12-12-2019 | 17-03-2022 | LOT | 1 | 2020 | 8
1417 | BLD-2248-D-STP¦A¦18 | SEWAGE TREATMENT PLANT (STP) | 2999 | P&F CI Dual Plate Nrv of Reqd Sizes | 12-12-2019 | 17-03-2022 | LOT | 1 | 2020 | 8
1418 | BLD-2248-D-STP¦A¦19¦19'1 | SEWAGE TREATMENT PLANT (STP) | 3000 | SITC of Vertcl Msep Multi Grade Filter | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
1419 | BLD-2248-D-STP¦A¦19¦19'2 | SEWAGE TREATMENT PLANT (STP) | 3001 | SITC of Activated Carbon Filter | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
1420 | BLD-2248-D-STP¦A¦20 | SEWAGE TREATMENT PLANT (STP) | 3002 | SITC of 18 Plate Filter Press | 12-12-2019 | 17-03-2022 | SET | 1 | 2020 | 8
1421 | BLD-2248-D-STP¦A¦21¦21'1 | SEWAGE TREATMENT PLANT (STP) | 3003 | P&F Flow Meter 100Mm Dia Mdl | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
1422 | BLD-2248-D-STP¦A¦21¦21'2 | SEWAGE TREATMENT PLANT (STP) | 3004 | P&F Flow Meter 80Mm Dia Ftl | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
1423 | BLD-2248-D-STP¦A¦21¦21'3 | SEWAGE TREATMENT PLANT (STP) | 3005 | P&F Flow Meter 65Mm Dia Mkupwtr Line | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
1424 | BLD-2248-D-STP¦A¦21¦21'4 | SEWAGE TREATMENT PLANT (STP) | 3006 | P&F Flow Meter 65Mm Dia Irrigation Line | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
1425 | BLD-2248-D-STP¦A¦22 | SEWAGE TREATMENT PLANT (STP) | 3007 | SITC of Manual & Auto Lvl Switch | 12-12-2019 | 17-03-2022 | LOT | 1 | 2020 | 8
1426 | BLD-2248-D-STP¦A¦23 | SEWAGE TREATMENT PLANT (STP) | 3008 | SITC of Softner Plant | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8
1427 | BLD-2248-D-STP¦A¦24 | SEWAGE TREATMENT PLANT (STP) | 3009 | Approval From Pollution Board | 12-12-2019 | 17-03-2022 | JOB | 1 | 2020 | 8
1428 | BLD-2248-D-STP¦MCC¦B¦1 | SEWAGE TREATMENT PLANT (STP) | 3010 | SITC of Mcc For Stp | 12-12-2019 | 17-03-2022 | EA | 1 | 2020 | 8